# AQUAPLAN 2022-2027 - Progress Report 1 2025

## Progress snapshot

| Activity status (total 28 activities) |  |  |
| --- | --- | --- |
| Yet to commence | In-progress | Complete |
| 2 | 19 | 7 |

## Progress Update

### Objective 1 Border biosecurity and trade

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 1.1 | Two-way engagement on import policy and decision-making processes. | In progress. | Expected outcome: Increased stakeholder understanding of, and engagement with, import policy setting processes, including risk analyses. Progress: A webinar series was delivered to increase shared understanding and create the opportunity for two-way engagement on trade and import policy and decision-making processes. Six webinars were delivered, covering aspects of Australian seafood production and trade, understanding international standards, the risk analysis process for import of aquatic animal commodities, verification of import biosecurity measures, and biosecurity and compartmentalisation for market access. Webinar recordings are available to view on the AQUAPLAN GovTEAMS. To access the recordings, contact aquaplan@aff.gov.au. |
| 1.2 | R&D strategic priorities for aquatic risk analyses and import policies. | In progress. | Expected outcome: Strategic research priorities are identified to address significant gaps in aquatic animal health knowledge to inform import biosecurity policies. Progress: R&D priorities are being considered by the FRDC Aquatic Animal Health and Biosecurity Coordination Program in consultation with stakeholders and through the process developed for activity 7.1. |
| 1.3 | Strategic approach to meet technical requirements and support market access. | Complete. | Expected outcome: A strategic approach to address technical market access opportunities and vulnerabilities is developed collaboratively by industries and governments. Progress: Industry and government representatives collaboratively developed the Seafood Market Access Prioritisation Framework to better manage market access priorities, ensuring effective allocation of resources, and to provide transparency to industry regarding progress of market access requests and market maintenance work actioned by the Department of Agriculture, Fisheries and Forestry (DAFF). |

### Objective 2 Enterprise and regional biosecurity

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 2.1 | Enterprise biosecurity plan writing workshops. | In progress. | Expected outcome: Workshop attendees have developed or refined an enterprise biosecurity plan that is specific to their business. Progress: Consultation to gauge sector interest in participating in this activity is underway. |
| 2.2 | Enterprise biosecurity plan implementation support program. | In progress. | Expected outcome: Farm managers have worked with subject-matter experts to refine their biosecurity plan and solve challenges in implementing the plan. Progress: The Australian Barramundi Farmers Association (ABFA) alongside subject-matter experts are creating and establishing individual biosecurity plans across member farms. See FRDC project 2023-046. |
| 2.3 | Evaluating and improving enterprise biosecurity plans. | Yet to commence. | Expected outcome: Farm managers and other interested industry members have been trained in tools to evaluate the effectiveness of their biosecurity plan and improve and adapt the plan over time to meet changing risks. Progress: To be informed by activities 2.1 and 2.2. |

| 2.4 | Translocation of broodstock and genetic material. | Complete. | Expected outcome: Opportunities, needs, and barriers to domestic translocation of high value animals and genetic material have been clarified, and options for developing a national approach to domestic translocation have been identified. Progress: Industry and government collaboratively worked to identify opportunities, needs, and barriers to domestic translocation of high value animals and genetic material. The parties involved were farmed abalone, prawn and oyster sectors and relevant jurisdictions. Through this work, recommendations on a national approach to domestic translocation have been provided to decision makers for consideration to inform policy. |
| --- | --- | --- | --- |

| 2.5 | Review current approaches for managing ornamental fish in Australia. | In progress. | Expected outcome: Aquatic animal health issues are considered in the review of the ‘strategic approach to the management of ornamental fish in Australia’ and where appropriate, the strategy is revised to support sound management of aquatic animal health risks associated with ornamental fish. Progress: Government aquatic animal health representatives are considering national strategic approaches to manage aquatic animal health risks associated with ornamental fish. Any approaches would complement a national freshwater pest plan that has been drafted by the Environment and Invasives Committee. |
| --- | --- | --- | --- |
| 2.6 | National ornamental fish communication campaign. | Yet to commence. | Expected outcome: Target stakeholder groups have an increased understanding of the disease risks posed by ornamental fish species in Australia and have the information available to help them take greater responsibility for effectively managing those risks. Progress: Yet to be commenced. |

### Objective 3 Surveillance

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 3.1 | National surveillance strategy. | Complete. | Expected outcome: A national surveillance strategy is developed that guides how investors in aquatic animal health surveillance will strengthen the system and address changing needs and technologies. Progress: A National aquatic animal disease surveillance strategy has been developed. The strategy is an industry-government initiative providing clarity on surveillance objectives, roles and responsibilities, and principles for investment in the national surveillance system. It recognises the strengths of the existing surveillance system and provides an agreed framework from which improvements can be made. The strategy supports a coordinated and collaborative approach to surveillance by industry and governments. |
| 3.2 | Sector-specific surveillance plans. | In progress. | Expected outcome: Interested industry sectors have identified and prioritised their surveillance objectives (including data sharing) in cooperation with governments and have a plan for how they will achieve these. Progress: A farmed prawn disease surveillance plan is being jointly developed by industry in cooperation with government aquatic animal health representatives. The purpose of the plan is to provide nationally agreed guidance for an efficient and effective disease surveillance system for the prawn farming industry. Drafting of the surveillance plan is underway in collaboration with APFA, state, territory and Commonwealth governments. |
| 3.3 | Sensitivity of the passive surveillance system. | In progress. | Expected outcome: The sensitivity of passive surveillance is quantified for an example sector and disease as a pilot study, and strengths and weaknesses of the system are identified. Progress: Industry, government, and modelling experts have collaboratively quantified the sensitivity of Australia’s passive surveillance system for white spot disease in the prawn farming industry using scenario tree modelling. Scenario tree modelling for megalocytivirus in the barramundi industry has been constructed with final modelling, validation, and reporting scheduled for delivery by the end of December 2025. See FRDC project 2019-193. |

### Objective 4 Diagnostic capability

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 4.1 | Assess the future needs of Australia’s diagnostic system. | In progress. | Expected outcome: The capability and capacity of Australia’s diagnostic system for aquatic animal diseases is assessed and the future needs of its end-users and service providers are identified. Progress: Key strategic priorities to strengthen Australia’s aquatic animal health diagnostics system have been identified by industry and government stakeholders through a Diagnostic Futures Workshop (May 2025), Delphi survey, and targeted one-on-one interviews. Insights on current gaps and future needs of Australia’s diagnostic system for aquatic animal diseases have been presented at an AQUAPLAN webinar (September 2025). See FRDC project 2023-006. |
| 4.2 | Technical guidelines for validation of aquatic animal disease diagnostic tests. | In progress. | Expected outcome: National technical guidelines for validation of aquatic animal disease molecular diagnostic tests are developed. Progress: National technical guidelines for validation of aquatic animal disease molecular diagnostic tests are being jointly developed by the CSIRO – Australian Centre for Disease Preparedness (ACDP) Fish Diseases Laboratory and Australian Government to align with the validation dossier requirements of WOAH. |
| 4.3 | Diagnostic accuracy studies for priority aquatic animal diseases. | In progress. | Expected outcome: The validation status of priority aquatic animal disease diagnostic tests is identified, and diagnostic accuracy studies are conducted for prioritised tests. Progress: This activity is in the early stages of development. A project plan is being developed by CSIRO ACDP in consultation with key collaborators. |
| 4.4 | Novel and emerging diagnostic methods. | In progress. | Expected outcome: New and emerging diagnostic methods are prioritised for further assessment based on their suitability to address the needs of Australia’s aquatic animal health management system, and where warranted, national guidelines are developed for their evaluation, interpretation, and use. Progress: A scoping review and framework for the assessment of new diagnostic tools has been developed as a component of FRDC project 2023-006. This work will be presented at an AQUAPLAN webinar in February 2026. |
| 4.5 | Improve Neptune and its database. | In progress. | Expected outcome: Neptune’s database is enhanced to incorporate additional content and is promoted within the aquatic animal health community to increase access and contributions to its resources. Progress: Industry and governments are co-designing enhancements to support diagnostic accuracy, workforce capability, and national biosecurity resilience by implementing Neptune Mark II and a digital histopathology proficiency testing program. See Diagnostic capability and resources - DAFF. |

### Objective 5 Emergency preparedness

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 5.1 | National priority aquatic animal disease list. | Complete. | Expected outcome: Priority aquatic animal diseases have been identified and agreed by industry and governments. A priority disease list has been developed. Progress: Industry and government worked together to identify the highest priority exotic diseases that require coordinated investment and activity to improve risk mitigation and emergency preparedness. The national priority aquatic animal disease list was endorsed by aquatic animal industries and governments in June 2023. |
| 5.2 | Biosecurity action plans for priority aquatic animal diseases. | In progress. | Expected outcome: Biosecurity action plans have been collaboratively developed for each priority disease, and gaps identified where resources need to be applied to improve preparedness or risk mitigation. Progress: Industry and governments have jointly developed the priority disease action plan for Megalocytivirus pagrus1 which is in its final stage of review. Draft action plans for additional priority diseases are in development. |
| 5.3 | Sector-specific simulation exercises. | In progress. | Expected outcome: A series of sector-specific simulation exercises have tested existing contingency planning arrangements and identified opportunities to strengthen arrangements. Progress: Two exercises have been held through the national simulation exercise program. Exercise FlyWheel (2023) was held in collaboration with the barramundi industry and Exercise Black Tiger (2024) was held in collaboration with prawn industry. Each exercise aimed to test the technical response arrangements for an exotic disease outbreak. Planning for a third exercise with the salmon industry has commenced for delivery in 2026. See FRDC project 2021-048. |
| 5.4 | New or revised contingency planning arrangements. | In progress. | Expected outcome: A work plan to review and revise existing AQUAVETPLAN manuals and develop new manuals or guidance documents (where they are prioritised) is developed and delivered. Progress: The AQUAVETPLAN disease strategy manual (DSM) for white spot disease (WSD) has been revised by industry and governments. The manual provides guidance for an aquatic animal emergency disease response where WSD has been confirmed in wild or cultured crustaceans. The AQUAVETPLAN manual endorsement processes have been updated providing efficiency in the development and review of manuals. New DSMs and Response Policy Briefs are in development to provide consistency, and improve useability and fitness for purpose. |
| 5.5 | Practical disease investigation guidelines for new and emerging diseases. | Complete. | Expected outcome: Practical disease investigation guidelines are developed that outline the investigation process for new and emerging aquatic animal diseases. Progress: The ‘Outbreak!’ handbook presents guidelines to use in the event of a disease outbreak in aquatic animals including finfish, molluscs and crustaceans. It helps stakeholders understand if a disease event is an outbreak, what may be causing the disease, what controls to apply and ideally, how to prevent future outbreaks. The handbook and its associated e-learning modules are available to view and download from the Agriculture Victoria website. Refer to FRDC project 2021-061. |

### Objective 6 Veterinary medicines

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 6.1 | Understand existing veterinary medicine use. | In progress. | Expected outcome: A cross-sectoral survey is undertaken to better understand veterinary medicine use and priorities across the aquaculture industry. Progress: A survey was sent to aquaculture industry stakeholders in August 2025 to understand veterinary medicine use and future needs in aquaculture. The survey will gather from industry an up-to-date list of AgVet products used under APVMA permit and those desired for future permit applications. See FRDC project 2024-014. |
| 6.2 | Aquatic animal minor use permit applications. | Complete. | Expected outcome: A nationally coordinated approach to facilitate applications for aquatic animal minor use permit applications to the APVMA and to maintain existing permits and registrations. Progress: This project developed a nationally coordinated approach to facilitate applications for aquatic animal minor use permit applications to the APVMA and to maintain existing permits and registrations. This contributes to future proof access to high priority veterinary medicines (e.g. medicines, vaccines and antimicrobials). Refer to FRDC project 2020-094. A news article on the project is available at: Streamlined process improves access to aquaculture medicines (FRDC 2023). As an extension of this activity, planning is underway for the ongoing National Coordination of access to AgVet chemicals to support minor use permit applications beyond 2026. |
| 6.3 | Establish antimicrobial resistance baselines for aquaculture sectors. | In progress. | Expected outcome: Baseline AMR data is established for interested sectors within the Australian aquaculture industry. The importance and key benefits of AMR surveillance in aquaculture are communicated with industry in an effective and collaborative manner. Progress: Aquatic animal industries, government and research representatives are collaboratively progressing AMR activities. An AQUAPLAN webinar will be held in November 2025 to provide an overview of antimicrobial stewardship in aquaculture and AMR. |

### Objective 7 Research and innovation

| Activity | Short title | Status | Expected outcome and progress |
| --- | --- | --- | --- |
| 7.1 | Research priority setting, engagement, and communication. | Complete. | Expected outcome: An efficient research priority setting, engagement and communication process is collaboratively developed. Progress: A process to consult with stakeholders to identify R&D needs and develop national research priorities for aquatic animal health has been collaboratively developed. This process ensures that identified needs are addressed through the whole R&D lifecycle and provide meaningful outputs for adoption by end users. |
| 7.2 | Extension and adoption of aquatic animal health research. | In progress. | Expected outcome: Barriers to and opportunities for extension and adoption inform research development and extension system improvements that ensure that research is not considered complete until it is extended by end-users, and opportunities for adoption identified, maximising return on investment. Progress: The project is in the early stages of development. A project outline defining the purpose, scope and need has been developed and is being discussed with key stakeholders. |
| 7.3 | AQUAPLAN webinar series. | In progress. | Expected outcome: A webinar series is delivered for Australia’s aquatic animal health community that provides meaningful engagement and extension opportunities for AQUAPLAN activities. Progress: Sixteen AQUAPLAN webinars have been delivered for the aquatic animal health community providing meaningful engagement and extension opportunities for AQUAPLAN activities. Webinars have included presentations on ‘Exercise Black Tiger (2024)’ (Activity 5.3), Future needs of aquatic animal diagnostics’ (Activity 4.1), ‘Updates on international activities’ and ‘human behaviour and biosecurity’. Several webinar recordings are available to view on the AQUAPLAN GovTEAMS. To access the recordings, contact aquaplan@aff.gov.au. |