National Television and Computer Recycling Scheme

Outcomes 2013–14

June 2015

Contents

Executive Summary	3

Background	4

Developing the National Television and Computer Recycling Scheme	4

Consultation and stakeholder engagement	4

Implementing the scheme	5

Enhancements to the scheme	6

Scheme outcomes 2013–14	7

Recycling of televisions and computers	7

Performance of co-regulatory arrangements against recycling targets	7

Provision of e-waste collection services	9

Participation of television and computer importers and manufacturers	12

Material recovery	13

The scheme’s third target year: 2014–15	15

Appendix A – List of liable parties 2013–14, by co-regulatory arrangement	16

Appendix B – Data table	20

# Executive Summary

52,736 tonnes of e-waste were recycled under the scheme

879 longer-term and 302 event-based collection services were made available around Australia

141 TV and computer importers and manufacturers were liable; by 30 June 2014, 137 of these parties had met their obligation to participate in the scheme

The National Television and Computer Recycling Scheme requires the television and computer industries to fund collection and recycling of a proportion of the televisions and computers disposed of in Australia each year. The scheme’s long-term goals include the diversion of potentially hazardous television and computer waste from landfill, an increase in the recovery of useable materials and greater access to recycling for communities across Australia.

The scheme’s design includes a stepped implementation over a number of years, with industry taking responsibility for a progressively higher proportion of total waste televisions and computers each year, from 30 per cent in 2012–13 to 80 per cent in 2021–22. In 2013–14, industry’s responsibility was to fund the recycling of 33 per cent of waste arising. Management of television and computer e-waste beyond these targets, as well as management of other e-waste, is the responsibility of state and territory governments and, through them, local governments.

Companies importing or manufacturing over a threshold amount of television or computer products are liable under the scheme and must join and fund an approved co-regulatory arrangement to provide collection and recycling services on their behalf. There were 141 liable parties in 2013–14.  Liable party compliance as a proportion of the weight of liable imports was 99.2 per cent at 30 June 2014.

Five approved co-regulatory arrangements were operating in 2013–14: Australia and New Zealand Recycling Platform Limited (ANZRP), DHL Supply Chain (Australia) Pty Limited, Ecycle Solutions Pty Ltd, Electronic Product Stewardship Australasia (EPSA) and Reverse E-waste.  A total of 1181 collection services were provided by the five co-regulatory arrangements in 2013–14. These included longer-term services, such as drop off points at major electronics retailers and local government waste transfer stations, as well as temporary collection events.

An estimated total of 131,607 tonnes of televisions and computers reached end-of-life in Australia in 2013–14. Industry’s target under the scheme was to recycle 33 per cent of this amount, or 43,430 tonnes. A total of 52,736 tonnes of recycling was achieved, in excess of the scheme target by approximately 9,304 tonnes. Each co-regulatory arrangement exceeded its recycling target.

# Background

## Developing the National Television and Computer Recycling Scheme

In 2007–08 it was estimated that around 106,000 tonnes of televisions, computers and computer products (including printers, scanners, keyboards and mice) reached end-of-life in Australia. This figure represents approximately five kilograms of television and computer waste generated per capita. At that time, it was estimated that only 10 per cent of these products were recycled, with the remainder either stockpiled or sent to landfill. The amount of waste arising each year was also increasing due to rapid technological change, shorter life-spans of products and increasing ownership of electrical goods.

Waste management is primarily the responsibility of state and territory governments and, through them, local governments. The involvement of the Australian Government arose through the Council of Australian Governments (COAG), in response to the growing e-waste challenge and the desire of industry, the community and governments for a more consistent national approach to recycling.

Australian environment ministers agreed in 2009 that televisions and computers should be the first products to be regulated under the proposed national legislative framework for product stewardship. Product stewardship is an approach that acknowledges that those involved in producing, importing, selling, using and disposing of products have a shared responsibility to reduce the impact that those products and their use and disposal have on the environment and human health and safety.

The decision to implement a product stewardship scheme for televisions and computers was informed by a thorough analysis of the impact of a national regulated recycling scheme. This analysis demonstrated that an industry run and funded recycling scheme for televisions and computers would provide a significant net benefit to society over the period from 2008–09 to 2030–31.

A key design feature is that the television and computer industries take on increasing proportion of the responsibility for managing television and computer e-waste over a number of years. In endorsing the design, COAG recognised that continued management of television and computer e-waste beyond the scheme targets would be needed in support of industry’s efforts in the early years of the scheme.

Work to develop the scheme was informed by a number of studies, which are available on the Department’s website at http://www.environment.gov.au/resource/national-waste-policy-publications-and-resources#research-ps.

## Consultation and stakeholder engagement

In July 2009, a consultation package was released on options for a national recycling scheme for televisions and computers. A total of 130 submissions were received from a broad range of stakeholders including television and computer manufacturers, industry associations, state and territory governments, local governments, environmental organisations and individuals. Submissions provided almost unanimous support for the introduction of a national scheme for television and computer recycling, underpinned by Australian Government regulation.

To inform the operational aspects of the scheme, the Australian Government established a Stakeholder Reference Group of representatives from the television, computer and recycling industries, environmental and community groups and state, territory and local governments. Between May 2010 and May 2012, the Stakeholder Reference Group facilitated engagement between key stakeholders and the government on the development and implementation of regulations for television and computer recycling.

The Australian Government also undertook a national programme of facilitated discussion sessions with local government, recyclers and charities. A total of 360 councils, representing 84 per cent of Australia’s population, took part in these sessions.

To assist with managing community expectations relating to demand for television and computer recycling, local governments were provided tailored communications and educational material on the scheme. The Australian Government also wrote to the mayors of all councils to provide information on the expected rollout timeframes, and to reiterate the importance of local governments continued involvement in the management of televisions and computer e-waste in the scheme’s early years.

The Department is committed to continued consultation and stakeholder engagement, and is currently undertaking a range of communication and consultation activities as part of the operational review of the scheme.  The operational review is discussed further on page 12 of this report.

## Implementing the scheme

The Product Stewardship Act 2011 (the Act) provides a legislative framework for national product stewardship, and the Product Stewardship (Televisions and Computers) Regulations 2011 (the Regulations) establish the National Television and Computer Recycling Scheme. The Regulations require all importers and manufacturers of above threshold volumes of televisions and computers to join and fund an approved co-regulatory arrangement. Co-regulatory arrangements are responsible for meeting scheme outcomes on behalf of their members.

The Regulations require industry to fund collection and recycling services to meet progressively increasing annual recycling targets, set as a proportion of the estimated total television and computer waste arising in Australia. These targets started at 30 per cent in 2012–13 and will increase to 80 per cent at the peak of the scheme’s rollout.

Each of the five approved co-regulatory arrangements must achieve its portion of the total scheme recycling target, based on the import or manufacture share of its members. Each co-regulatory arrangement must also provide access to recycling services for communities across metropolitan, regional and rural Australia, in line with metrics described in the Regulations.

Organisations applying to establish co-regulatory arrangements are assessed by the Department, and are required to demonstrate capacity to achieve collection and recycling outcomes, address environmental, health and safety matters, and administer governance arrangements for liable importers and manufacturers.

To provide consistent environmental guidance for the e-waste recycling industry, the Australian Government supported Standards Australia to develop Australian Standard 5377:2013 ‘Collection, storage, transport and treatment of end-of-life electrical and electronic equipment’. This standard was finalised and published in February 2013, followed by the Department working with the Joint Accreditation System of Australia and New Zealand (JAS-ANZ) to develop an accreditation process for certifying bodies to administer certification. This process was finalised and the requirements published in March 2015.

## Enhancements to the scheme

The Australian Government has actively monitored and sought feedback on the implementation of the Scheme. As the first scheme established under the Act and the largest product stewardship scheme ever rolled out in Australia, it has always been anticipated that opportunities would arise to enhance the scheme, and this has been achieved through regulatory amendments.

Product codes and conversion factors, which enable allocation of responsibility for recycling to individual companies and estimation of the weight of waste arising in a given year by reference to the quantities of new products imported in recent years, have been updated regularly to account for changes to the products imported over time.

The product codes and conversion factors developed prior to implementation of the scheme are included in Schedule 1 of the Regulations, and apply to products imported up to 31 December 2011.

Schedule 1A was added to the Regulations June 2012. It includes product codes and conversion factors for products imported between 1 January and 30 June 2012.

The product codes and conversion factors were updated again in 2012–13, and Schedule 1B was added to the Regulations in June 2013. It includes product codes and conversion factors imported from 1 July 2012.

As part of the operational review of the scheme, new conversion factors are under consideration for products imported between 1 July 2014 and 30 June 2015 (proposed Schedule 1C), and product codes and conversion factors are under consideration to apply to products imported from 1 July 2015 (proposed Schedule 1D).

In April 2013 the Department released a discussion paper outlining other potential opportunities to improve the scheme, based on experience and feedback received throughout the first year of operations. Following consultation, amendments were made to the scheme, including:

- Moving to a single target for all products covered by the scheme, where previously separate targets had been set for televisions and computers

- Updating the scheme’s product codes to align with changes made to Australia’s Customs Tariff Classifications

- Changes to enable co-regulatory arrangements to better manage financial risk.

These changes came into effect in 2013–14.

A significant event occurring in 2014–15 is an operational review of the scheme. On 22 September 2014, Environment Minister Greg Hunt announced an operational review of the scheme to consider options to strengthen the scheme and ensure that its settings will continue to support good outcomes over the coming years.

An operational review paper setting out options and proposals for enhancing the scheme’s operation was made available for consultation in December 2014. The paper noted three core issues to be addressed through the review. These were a shortfall in funded recycling over the next two to three years, instability in the recycling sector and equitable regulatory outcomes for the television and computer industries.

Written submissions to the review paper closed on 6 February 2015, and a total of 85 submissions were received. The submissions have been assessed, and will inform the outcome of the review process. The review paper and accompanying submissions are available at www.environment.gov.au/ewaste.  Analysis and costing of options is now underway, and any amendments to the scheme are expected to be in place by 1 July 2015.

# Scheme outcomes 2013–14

Details on scheme outcomes included in this report are drawn from information provided in annual reports by each of the co-regulatory arrangements on their activities for 2013–14. Copies of the annual reports provided to the Department are available at www.environment.gov.au/ewaste.

## Recycling of televisions and computers

Total waste arising 2013–14:			131,607 tonnes

Total scheme recycling target 2013–14: 		43,430 tonnes

Total scheme recycling 2013–14: 			52,736 tonnes

In 2013–14 an estimated 131,607 tonnes of televisions and computers reached end-of-life in Australia. This is calculated as the average converted weight of the previous three years’ total imports and manufacturing of televisions and computers, multiplied by a scaling factor of 0.9. This scaling factor is used as not all imports replace an existing product, causing it to enter the waste stream. A weight-based conversion factor is applied to each imported product to allow liability to be expressed in tonnage rather than number of units. The total converted weight of all television and computers imported or manufactured in Australia was 159,165 tonnes in 2010–11, 143,324 tonnes in 2011–12, and 136,200 tonnes in 2012–13. Further data on imports and waste arising is available in Table B1 of Appendix B.

The total scheme recycling target in 2013–14 was 33 per cent of total waste arising, or 43,430 tonnes of waste televisions and computers.

A total of 52,736 tonnes of televisions and computers were recycled under the Scheme in 2013-14. The scheme recycling target was exceeded by approximately 9,304 tonnes, equivalent to 21.4 per cent of the target. This is a substantial increase on the scheme’s first target year, 2012–13, in which 40,813 tonnes was recycled. Annual recycling of televisions and computers in Australia prior to the commencement of the scheme was estimated at around 21,200 tonnes in 2009–10.

## Performance of co-regulatory arrangements against recycling targets

Each of the five co-regulatory arrangements exceeded its recycling target in 2013–14.

Figure 1, below, shows each co-regulatory arrangement’s recycling target and their performance against this target. Data on the performance of the co-regulatory arrangements against their recycling targets are given in Table 1 below.

Figure 1: Recycling target and recycling achieved for each approved co-regulatory arrangement in 2013–14.

Table 1: Performance against 2013–14 co-regulatory arrangement recycling targets (all figures rounded to nearest tonne)

|  | Televisions and computers (tonnes) |  | 2013–14 excess recycling (tonnes) |
| --- | --- | --- | --- |
|  | Target | Recycled |  |
| ANZRP | 26,134 | 27,894 | 1,760 |
| DHL Supply Chain | 14,614 | 14,874 | 260 |
| Ecycle Solutions | 1,735 | 2,037 | 302 |
| EPSA | 973 | 2,918 | 1,945 |
| Reverse E-waste | 4,992 | 5,013 | 21 |
| Total | 48,448* | 52,736 | N/A |

*The sum of co-regulatory arrangements’ recycling targets is greater than the scheme target for 2013–14 because ANZRP’s 2013–14 recycling target included a 5,239 tonne shortfall carried over from 2012–13.

Excess recycling undertaken by co-regulatory arrangements may be carried forward and acquitted against future targets. The results against recycling targets are as follows:

- ANZRP exceeded its recycling target in 2013–14 and will carry forward total excess recycling of 1,760 tonnes. ANZRP’s target of 26,134 tonnes included 5,239 tonnes carried forward as a shortfall against its 2012–13 target, and 20,895 arising from its 2013–14 liable party members’ import/manufacture share.

- DHL Supply Chain exceeded its recycling target in 2013–14 and will carry forward total excess recycling of 260 tonnes. In addition, DHL carried forward 4,348 tonnes of excess recycling from 2012–13, giving it a total of 4,608 tonnes of excess recycling at 1 July 2014.

- Ecycle Solutions exceeded its recycling target in 2013–14 and will carry forward total excess recycling of 302 tonnes. In addition, Ecycle Solutions carried forward 377 tonnes of excess recycling from 2012–13, giving it a total of 679 tonnes of excess recycling at 1 July 2014.

- EPSA exceeded its recycling target in 2013–14 and will carry over total excess recycling of 1,945 tonnes.

- Reverse E-waste exceeded its recycling target in 2013–14 and will carry over total excess recycling of 21 tonnes.

## Provision of e-waste collection services

A total of 879 longer term and 302 event-based collection locations were made available to households and small businesses across Australia

Each co-regulatory arrangement is required to provide access to collection services for waste televisions and computers to communities across metropolitan, regional and remote Australia. A co-regulatory arrangement may do this in a variety of ways, such as by partnering with an existing recycling service or facility or holding periodic collection events. Temporary or event-based collection services are treated the same as ongoing collection services, provided that they meet reasonable access requirements.

Householders and small businesses must not be charged for the disposal of television and computer e-waste to a scheme collection service. This requirement does not prevent local councils from charging customers for disposal as part of their management of e-waste outside of scheme targets.

Table 2: Scheme collection locations and weight of products collected from 1 July 2013 to end June 2014 in each state and territory.

| State/Territory | Number of longer term services | Number of event based services | Total collected weight (tonnes)* |
| --- | --- | --- | --- |
| Australian Capital Territory | 7 | 0 | 873.17 |
| New South Wales | 269 | 42 | 8772.47 |
| Northern Territory | 6 | 10 | 21.69 |
| Queensland | 161 | 206¹ | 4419.28 |
| South Australia | 70 | 9 | 3962.92 |
| Tasmania | 14 | 0 | 768.15 |
| Victoria | 297 | 11 | 8529.03 |
| Western Australia | 62 | 24 | 1737.97 |
| Total | 879 | 302 | 29,084.68 |

* Excludes television and computer e-waste collected outside of publicly available scheme collection services.

¹ Includes kerbside collections for 183 Brisbane suburbs.

In addition to the e-waste disposed of by the community and collected through scheme collection services, total scheme recycling also includes recycling which is undertaken independently by members of the co-regulatory arrangements (i.e. television and computer companies), or e-waste which is sourced directly from businesses. This recycling is also counted against scheme targets. The weight of material collected through business and directly by liable parties is shown in Table 3.

Collection locations have been provided at local government waste facilities, other transfer stations and recycling facilities and at a number of major retailers. The total number of collection services provided by the co-regulatory arrangements in each state and territory and the total television and computer e-waste collected in 2013–14 is given in Table 2, above.

Table 3: Weight of material collected through business and directly by liable parties from 1 July 2013 to end June 2014 in each state and territory

| State/Territory | Total weight of collections by business (tonnes) | Total weight of collections by members (tonnes) |
| --- | --- | --- |
| Australian Capital Territory | 1 | 102.18 |
| New South Wales | 8478.72 | 5295.2 |
| Northern Territory | 0 | 0.36 |
| Queensland | 168.31 | 762.10 |
| South Australia | 869.41 | 380.65 |
| Tasmania | 51 | 2.24 |
| Victoria | 995.95 | 1932.64 |
| Western Australia | 357.54 | 519.49 |
| Total | 10921.93 | 8994.86 |

Table 3 does not reflect material that was collected from businesses or members in an earlier financial year and stored for recycling in 2013–14. For this reason, total recycling reported under the scheme for 2013–14 is greater than the sum of material from public collections and material from businesses and members. Additional information on the collection services provided by the arrangements is given in each co-regulatory arrangement’s annual report, available at www.environment.gov.au/ewaste.

Each arrangement is required to deliver reasonable access to collection services to communities in metropolitan, regional and remote Australia. The Department’s assessment of each arrangement’s performance against the requirement to deliver reasonable access is complete for the period to 30 June 2014. The assessment found that:

- DHL met the reasonable access requirement by 31 December 2013, and for financial year 2013–14.

- ANZRP did not meet the reasonable access requirement by 31 December 2013 by a small number of sites, but met the requirement for financial year 2013–14.

- Ecycle Solutions did not meet the reasonable access requirement by 31 December 2013 by a small number of sites, but met the requirement for financial year 2013–14.

- EPSA did not meet the requirement to provide reasonable access to collections by 3 April 2013 and for financial year 2013-14, having failed to provide collections to two remote locations. EPSA has since provided collection services at those locations.

- Reverse E-Waste failed to provide reasonable access to collection services by both 25 June 2014 and for financial year 2013-14, having failed to provide collections to a significant proportion of the required sites.

Table 4: Number of services delivered by co-regulatory arrangements, by geographical region and percentage of total reasonable access achieved.

|  | Metropolitan | Inner Regional | Outer regional | Remote |  |
| --- | --- | --- | --- | --- | --- |
| Minimum required collection services | 59 | 64 | 62 | 32 | Reasonable access achieved (%) |
| ANZRP | 59 | 64 | 62 | 32 | 100 |
| DHL | 59 | 64 | 62 | 32 | 100 |
| Ecycle Solutions | 59 | 64 | 62 | 32 | 100 |
| EPSA | 59 | 64 | 62 | 30 | 99.08 |
| Reverse E-waste | 6 | 15 | 5 | 3 | 13.36 |

Activities to address non-compliance with reasonable access requirements are outlined in the Compliance section of this report. Map 1, below, depicts scheme collection locations and reasonable access areas for 2013–14.

The coloured polygons in Map 1 indicate the areas in which collection services must be provided.  The actual collections that have been provided by all co-regulatory arrangements are shown by the grey dots. Some metropolitan areas are hidden by their collections.

Map 1: Scheme collection services provided to the public in 2013-14 by all co-regulatory arrangements.

## Participation of television and computer importers and manufacturers

141 television and computer importers and manufacturers were liable in 2013–14

Liable parties responsible for 99.2 per cent of total imports by liable parties complied with their obligations to join a co-regulatory arrangement in  2013–14

- Companies importing or manufacturing over a specified threshold of television or computer products are liable under the scheme. The Regulations specify liability thresholds for the products covered by the scheme. These thresholds are:

for televisions – 5000 units

for computers – 5000 units

for computer parts or peripherals – 15,000 units.

- Importers or manufacturers that exceeded one of these thresholds were required to join and fund an approved co-regulatory arrangement, which undertook collection and recycling services on their behalf.  Liability for 2013–14 was determined by the number of products imported or manufactured in 2012–13.

- A total of 141 companies were identified as liable in 2013–14. These liable parties imported or manufactured a total of 136,200 tonnes of televisions and computers in 2012–13, which was 91.4 per cent of the total televisions and computers imported or manufactured in Australia that year. By 30 June 2014, liable parties responsible for 99.2 per cent of liable parties met their obligations under the scheme to join an approved co-regulatory arrangement for 2013–14.

## Material recovery

Recycling processes result in the separation of a range of commodities and components that are sent for further processing into useable materials. In addition, there are normally small amounts of unusable or low-value materials are separated and disposed, often to landfill. Material recovery refers to the proportion of material that is sent for further processing into useable materials.

From 1 July 2014, the Regulations require a minimum material recovery rate of 90 per cent, in order to minimise the amount of television and computer material that is disposed of to landfill and maximise the recovery of resources. A methodology to simplify reporting of material recovery has been provided to each of the co-regulatory arrangements. The Department anticipates that the introduction of this methodology will increase the consistency of material recovery calculations for all co-regulatory arrangements.

The material recovery reporting requirement under the Regulations was not in effect during 2013–14. Information on the co-regulatory arrangements’ material recovery rates for 2013–14 is available in their annual reports.

Compliance activity since 1 July 2013

The Department undertakes monitoring, compliance and enforcement activities to detect and respond to non-compliance under the Product Stewardship Act 2011 and the Product Stewardship (Televisions and Computers) Regulations 2011.

The activities of co-regulatory arrangements are monitored by the Department through regular meetings and reports provided on a quarterly and annual basis. Co-regulatory arrangement annual reports to the Department are required to be audited, and the matters that they must address are specified in the Regulations. Arrangements also provide a version of their annual report for publication on the Department’s website. Approved arrangements in 2013–14 were required to deliver two key outcomes:

- provide reasonable access to collection services in metropolitan, inner regional, outer regional and remote areas, and

- meet annual recycling targets.

Provision of Reasonable Access

During 2013–14, the Department undertook a range of activities to inform co-regulatory arrangements of their reasonable access requirements and monitor their achievement of this outcome. The Department is undertaking targeted compliance action to address failure to meet the reasonable access outcome, and it is expected that this will be finalised in 2014–15. Future assessment of the reasonable access outcome will occur on a financial year basis.

Annual Recycling Targets

All arrangements reported complying with their recycling targets for financial year 2013–14.

Improvement Notices

The Department issued an improvement notice under section 29 of the Product Stewardship Act 2011 to ANZRP in June 2014 in relation to its recycling target in the 2012–13 financial year, requirement to provide reasonable access to collection services by 31 December 2013 and requirement to take all reasonable steps to ensure the arrangement achieves its required outcomes. ANZRP has complied fully with the improvement notice.

The Department issued an improvement notice under section 29 of the Product Stewardship Act 2011 to Ecycle Solutions in August 2014 in relation to its requirement to provide reasonable access to collection services by 31 December 2013 and requirement to take all reasonable steps to ensure the arrangement achieves its required outcomes. Ecycle Solutions has complied fully with the improvement notice.

Review of the operations of a co-regulatory arrangement

On 27 April 2015, the Department announced that it was undertaking a formal review of the operation of Reverse E-Waste, under section 27 of the Product Stewardship Act 2011, with the review scheduled for completion in June 2015.

Liable Parties

The Department utilises a range of tools and strategies to encourage liable party compliance with the scheme. These include education and persuasion, formal written notices, enforceable undertakings, civil penalty orders, and injunctions. In 2013–14, the Department provided letters advising parties of their liability, issued formal notices requiring liable parties to join an arrangement, issued warning letters, as well as made follow-up phone calls and inspector visits. As a result, a high level of liable party compliance was achieved.

The members of each co-regulatory arrangement in 2013–14 are included in Appendix A. Liable parties that fail to comply with their obligation to join a co-regulatory arrangement during 2013–14 are subject to compliance action, which may include substantial civil penalties, and remain liable for any outstanding liability in future years.

Table 5 below provides further information on liable party compliance.

Table 5: Liable Party compliance statistics 2013-14

| Actions/Outcomes in 2013–14 |  |
| --- | --- |
| Number of Liable Parties | 141 |
| Liable Party compliance as a proportion of weight of liable imports (%) | 99.2 |
| Number of inspector visits to premises of Liable Parties | 7 |
| Regulatory notices issued: |  |
| - Section 18 – the requirement for a liable party to be a member of approved co-regulatory arrangement | 33 |
| - Section 90 – the provision which allows the Minister to require a person who has product stewardship information to provide requested information | 1 |

# The scheme’s third target year: 2014–15

In 2014–15 all approved co-regulatory arrangements are again required to provide access to recycling services across metropolitan, regional and remote areas of Australia.

Television and computer waste arising for 2014–15 is 121,869 tonnes. This is calculated from the average converted weight of the previous three years’ total imports and manufacturing of televisions and computers, multiplied by a scaling factor of 0.9.

The scheme target in 2014–15 is 35 per cent of the total waste arising, or 42,654 tonnes.

As industry achieves its target over the course of the year, it will be important that this effort is supported by the continuation of e-waste management by state, territory and local governments of waste televisions and computers falling outside scheme targets.

By May 2015, liable parties responsible for 99.8 per cent of liable imports, had met their obligation to be a member of a co-regulatory arrangement for 2014–15.

## Appendix A – List of liable parties 2013–14, by co-regulatory arrangement

ANZRP:

Amicroe Holdings Ltd & Desert Computer Design Inc

Anyware Corporation Pty Ltd

Apple Pty Ltd

Bluechip Infotech Pty Ltd

Brother International (Australia) Pty Ltd

Cablelist Pty Ltd

Canon Australia Pty Ltd

Catchoftheday.com.au Pty Ltd

Cherry Australia Pty Ltd

Chimei Innolux Corporation

Cisco Systems Australia Pty Ltd

Com 1 International Pty Ltd

Competition Team Ireland Ltd

Datalogic ADC Pty Ltd

Dell Asia Pacific SDN

Dell Australia Pty Ltd

Dell Global B.V. (Singapore Branch)

Dicker Data Ltd

DMA Unit Trust

DSG Holdings Australia Pty Ltd

EMC Information Systems International

Epson Australia Pty Ltd

Express Data Holdings Pty Ltd

Foxteq Australia Pty Ltd

Fuji Xerox Asia Pacific Pte Ltd

Fuji Xerox Australia Pty Ltd

Goodson Imports Pty Ltd

Hewlett-Packard Australia Pty Ltd

Hitachi Data Systems Australia Pty Ltd

Hon Hai Precision Industry Co Ltd

Huawei Technologies (Australia) Pty Ltd

IBM Australia Ltd Just Group Ltd

King World Developments Pty Ltd

Konica Minolta Business Solutions Australia Pty Ltd

Kyocera Document Solutions Australia Pty Ltd

Laser Corporation Holdings Pty Ltd

Lenovo (Australia & New Zealand) Pty Ltd

Lexmark International (Australia) Pty Ltd

Medion AG Microsoft Regional Sales Corporation

Multimedia Technology Pty Ltd

NEC Australia Pty Ltd

Panasonic Australia Pty Ltd

Pegatron Corporation

Pioneer Electronics Australia Pty Ltd

PLE Computers Pty Ltd

Primax Electronics Ltd

Quanta Computer Inc Qisda Corporation

Rectron Electronics Pty Ltd

Scholastic Australia Pty Ltd

Sharp Corporation of Australia Pty Ltd

Soanar Pty Ltd

Super-Mem Pty Ltd

Suzhou Raken Technology Co Ltd

Targus Australia Pty Ltd

Teleplan Service Solutions Asia B.V.

The Leader Computer Wholesale Trust

The Trustee for the Coast RV Unit Trust

The Trustee for Thermal Take Unit Trust

Top Victory Investments Ltd

Toshiba (Australia) Pty Ltd

Uniden Australia Pty Ltd

Wacom Australia Pty Ltd

Wistron Corporation

Yetimo Marketing Pty Ltd

DHL:

A Royale & Co (Aust) Pty Ltd

Acco Australia Pty Ltd

Advantech Australia Pty Ltd

Anabelle Bits Pty Ltd

Audion Innovision Pty Ltd

Australia I.T. Pty Ltd

Avnet (Australia Pty Ltd

Avnet Pacific Pty Ltd

Avnet Technology Solutions (Australia) Ltd

BCI International Development Pty Ltd

Belkin Ltd

Brightpoint Australia Pty Ltd

Bush Australia Pty Ltd

Cellnet Group Ltd

Dick Smith (Wholesale) Pty Ltd

Electus Distribution Pty Ltd

Element14 Pty Ltd

Fujitsu Australia Ltd

Imation ANZ Pty Ltd

Ingram Micro Pty Ltd

Intermec Technologies Australia Pty Ltd

Kmart Australia Ltd

Kogan Australia Pty Ltd

LG Electronics Australia Pty Ltd

Motorola Solutions Australia Pty Ltd

Pendo Industries Pty Ltd

POS – P.O.S Pty Ltd

Samsung Electronics Australia Pty Ltd

Sony Australia Ltd

Target Australia Pty Ltd

TEAC Australia Pty Ltd

Teco Australia Pty Ltd

Tempo (Aust) Pty Ltd

The Trustee for Systemax Trust

Verbatim Australia Pty Ltd

Viano Corporation Pty Ltd

Woolworths Ltd

Ecycle Solutions:

Benq Australia Pty Ltd

Changhong Electric (Australia) Pty Ltd

Compucon Computers (NSW) Pty Ltd

Eternal Asia (Australia) Pty Ltd

Hisense Australia Pty Ltd

La Cie Australia Pty Ltd

Phoenix Distribution (Australia) Pty Ltd

TCL Electronics Australia Pty Ltd

Technicolor Delivery Technologies Aust Pty Ltd

Ultra Imagination Technology Pty Ltd

V.B Distributors Pty Ltd

EPSA:

D-Link Australia Pty Ltd

J2 Retail Systems Pty Ltd

Newell Australia Pty Ltd

Oracle Corporation Australia Pty Ltd

Ricoh Australia Pty Ltd

VMax Pty Ltd

Reverse E-waste:

Acer Computer Australia Pty Ltd

Achieva Technology Australia Pty Ltd

Altech Computers Corporation Pty Ltd

Asus Service Australia Pty Ltd

Avico Electronics Pty Ltd

BPM Australia Pty Ltd

Demaltic Pty Ltd

Forwell Trading Pty Ltd

Gemalto Pty Ltd

Home Entertainment Suppliers Pty Ltd

Hyundai Electronics (Australia) Pty Ltd

ICT Century Pty Ltd

One Laptop Per Child Australia Ltd

PowerhousePC Australia Pty Ltd

Powertek International Pty Ltd

Quatius Aust Pty Ltd

Synnex Australia Pty Ltd

The Reject Shop Ltd

## Appendix B – Data table

Table B1: Scheme data 2009–10 to 2014–15

| Financial year | Total imports |  | Imports by all liable parties |  |  |  | Waste arising (tonnes | Scheme recycling target |  | Liable parties |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Units | Converted weight (tonnes) | Units | Proportion of total units | Converted weight (tonnes) | Proportion of total converted weight |  | Percentage target | Recycling target (tonnes) | Number of liable parties | Compliance by converted weight of imports |
| 2009–10 |  | 156,696.0 |  |  |  |  |  |  |  |  |  |
| 2010–11 | 41,152,643 | 159,165.4 | 38,197,909 | 92.82% | 152,390.4 | 95.74% |  |  |  |  |  |
| 2011–12 | 40,529,607 | 143,324.1 | 37,612,652 | 92.80% | 136,607.7 | 95.31% |  |  |  | 168 | 100.0% |
| 2012–13 | 38,222,952 | 136,200.5 | 34,718,616 | 90.83% | 124,196.8 | 91.18% | 137,755.7 | 30% | 41,326.7 | 131 | 100.0% |
| 2013–14 | 34,353,813 | 126,705.2 | 31,540,256 | 91.81% | 118,588.4 | 93.59% | 131,607.0 | 33% | 43,430.3 | 141 | 99.2% |
| 2014–15 | TBC | TBC | TBC | TBC | TBC | TBC | 121,868.9 | 35% | 42,654.1 | 132 | 99.7% |