# Threatened Species

# STRATEGY ACTION PLAN
2021-2026

© Commonwealth of Australia 2022

Ownership of intellectual property rights
Unless otherwise noted, copyright (and any other intellectual property rights) in this publication is owned by the Commonwealth of Australia (referred to as the Commonwealth).

Creative Commons licence
All material in this publication is licensed under a Creative Commons Attribution 4.0 International Licence except content supplied by third parties, logos and the Commonwealth Coat of Arms.

Inquiries about the licence and any use of this document should be emailed to copyright@awe.gov.au.

Cataloguing data

This publication (and any material sourced from it) should be attributed as: DAWE 2022, Threatened Species Strategy Action Plan 2021 - 2026, Department of Agriculture, Water and the Environment, Canberra, February. CC BY 4.0.

ISBN 978-1-76003-524-2

This publication is available at awe.gov.au/environment/biodiversity/threatened/publications/strategy-home

Department of Agriculture, Water and the Environment
GPO Box 858 Canberra ACT 2601
Telephone 1800 900 090

Disclaimer

The Australian Government acting through the Department of Agriculture, Water and the Environment has 
exercised due care and skill in preparing and compiling the information and data in this publication. Notwithstanding, the Department of Agriculture, Water and the Environment, its employees and advisers disclaim all liability, 
including liability for negligence and for any loss, damage, injury, expense or cost incurred by any person as a result 
of accessing, using or relying on any of the information or data in this publication to the maximum extent permitted 
by law.

Acknowledgements

Many people have contributed to the development of this first Action Plan under the Threatened Species Strategy 2021-2031.

We thank all the people who contributed ideas to the conversation. In particular, we thank all who gave their time to participate in the online workshops. We also acknowledge and appreciate the detailed, constructive feedback from all who took time to consider the Action Plan consultation paper and responded to the survey.

Finally, thanks to members of the Threatened Species Scientific Committee, threatened species experts, practitioners and the various officials from across the Australian Government who have supported the development of this plan.

Front cover images:

Red-tailed Black Cockatoo, Craig RJD, iStock by Getty Images
Giant Andersonia, Leonie Monks, DAWE 
Female Red Handfish with baby, Molly Christensen 
Yinnietharra Rock-dragon, DAWE
Jacinta Riley Koala

We acknowledge the traditional owners of country throughout Australia and their continuing 
connection to land, sea and community. We pay our respects to them and their cultures 
and to their elders past, present and future.

Contents

1	Summary of Action Plan Objectives  and Targets	4

2	Introduction	6

3	Overview	8

4	Priority species and priority places	9

5	Mitigating established and  emerging threats	11

6	Conserving, restoring and  improving habitat	15

7	Emergency preparedness and  response	17

8	Climate change and  adaptation	20

9	Effective conservation planning	22

10	Knowledge and tools	25

11	Forging stronger partnerships	28

12	Community leadership and  engagement	31

13	Tracking progress and  reporting	33

14	Definitions	34

15	Links	37

Appendix 1: 100 Priority species	39

Appendix 2: Priority places	46

## Summary of Action Plan Objectives 
and Targets

Objective 1: By 2026, all priority species on track for improved trajectory by 2031

Objective 2: By 2026, all priority places on track for improved condition by 2031

Target 1: Implement feral cat and fox management across 100% of the important habitat for susceptible priority species, using methods identified as best-practice 
by 2026

Target 2: Implement feral cat and fox management in 100% of priority places where feral cats and foxes are identified as a key threat to condition, using best practice methods selected for the location by 2026

Target 3: Reduce Gamba Grass to an area less than its 2021 range by 2026

Target 4: Secure 100% of nationally listed species impacted by Myrtle Rust in insurance collections and populations by 2026

Target 5: Reduce introduction and establishment of new exotic environmental pests, weeds and diseases by 2026

Target 6: Increase the area managed for conservation by 50 million hectares by 2026

Target 7: Add 5 new species across the national safe haven network to improve representation of invasive predator-susceptible threatened species by 2026

Target 8: Secure at least 80% of nationally listed threatened plant species in insurance collections by 2026

Target 9: All jurisdictions and the Commonwealth improve and increase the overall inclusion 
of critical biodiversity assets into emergency response management and planning 
systems by 2026

Target 10: Actions are underway to support the resilience and adaptive capacity of 100% of priority species and places at risk from climate change impacts by 2026

Target 11: Track and publish the implementation of priority actions identified in conservation advices, recovery plans and relevant threat abatement plans for 100% of priority species by 2026

Target 12: Develop at least 5 new tools to mitigate impact of broad-scale threats on threatened species by 2026

Target 13: Establish a monitoring program to fill critical data and information gaps for 50% of priority species by 2026

Target 14: Proactively engage Aboriginal and Torres Strait Islander people in the preparation of 100% of EPBC Act conservation planning documents for culturally significant threatened species and ecological communities by 2026

Target 15: Partners and/or private investment will support 50% of projects that benefit priority species and priority places by 2026

Target 16: Citizen science or community groups will lead activities for 50% of priority species and places, to help increase information base and assist recovery by 2026

## Introduction

The Threatened Species Strategy Action Plan 2021- 2026 identifies the priority species, places, actions and targets that underpin the Australian Government’s Threatened Species Strategy 2021-2031 vision.

This Action Plan introduces 100 priority threatened species and 20 priority places, representing Australia’s diverse land, sea and freshwater environments. The Plan also includes specific actions, outcomes, and targets for priority species, places and output targets for each of the 8 action areas identified in the Strategy as fundamental to the recovery of threatened species.

These species, places, actions and targets will be the focus of national efforts and investments from 2021 to 2026 and beyond. Actions to improve the recovery and condition of priority species and places will also benefit other threatened species and ecological communities.

Actions include new and existing initiatives and policies from across the Australian Government to benefit threatened plants, animals and ecosystems and contribute to Australia meeting its national and international responsibilities.

These include:

Programs that can benefit threatened species and threatened ecological communities

Policies including Australia’s Strategy for Nature 2019 - 2030 (which enacts Australia’s obligations under the Convention for Biological Diversity and is the overarching policy umbrella for all biodiversity related efforts), Biosecurity 2031, National Agreement on Closing the Gap

The objectives and operation of the Environment Protection and Biodiversity Conservation Act 1999 (EPBC Act).

The Action Plan was developed with input from the community, land managers, scientists, conservation groups, Indigenous land and sea managers and other stakeholders.

We recognise Aboriginal and Torres Strait Islander peoples’ continuing connection to land, sea and community, and in implementing this Action Plan, we aim to work in partnership to advance their aspirations to maintain and protect their culture and custodianship of Australia’s native plants and animals.

This Plan is just the beginning. The Australian Government plays an important role to coordinate national efforts to conserve and protect our native plants and animals, but we cannot do this alone. Success relies on the collective effort and expertise contributed by partners. This 
Action Plan is an invitation for all Australians to collaborate on the recovery of our threatened species and places.

Implementation

Since 2014, the Australian Government has mobilised more than $660 million for projects directly supporting outcomes for threatened species and threatened ecological communities.

These investments are complemented by other Australian Government environment spending, such as more than $2 billion in commitments through the National Landcare Program alone since 2014.

This Action Plan will be supported by continuing and new Australian Government funding programs.

• National Landcare Program

• Bushfire Recovery for Wildlife and Habitat package

• Koala Conservation and Protection package

• Supporting Communities Manage Pest Animals and Weeds Program

• Ocean Leadership package

• Great Barrier Reef package

• Environment Restoration Fund

• National Environmental Science Program

Conservation is everyone’s business and the Australian Government will support or build on contributions from other important partners working to help recover threatened species, including state and territory governments, land and sea managers, Aboriginal and Torres Strait Islander peoples, scientists, environmental non-government organisations, businesses and community.

## Overview

The 5 year targets and key actions set out in this Action Plan are based on significant input from experts and the community.

The objectives to improve the trajectories of 100 priority species and 20 priority places set a focus for targeted actions and reflect the Strategy’s prioritisation principles. These priorities are listed in Appendix 1 and 2.

The targets ensure accountability, provide a measure for tracking progress under the Action Plan, and a common set of actions to coordinate collective efforts. They help focus action where it is needed most, where we know we can be effective, and where the greatest benefit to threatened species can be achieved.

Connected and complementary in nature, each target and range of actions will help us track toward achieving the Strategy’s high-level 10 year objectives.

Figure 1: 	Diagram depicting the relationship between the Threatened Species Strategy and the Action Plan.

[The image shows how the main elements of the Strategy (Vision, Objectives, Prioritisation principles and Action Areas (abbrieviated to AA), have informed the Action Plan’s 5 year 100 priority species, 20 priority places and 16 targets and specific actions.

The Action Plan includes targets and specific actions for the priority species and places, and for each of the 8 action areas, covering.

Direct		AA1	Mitigating established and emerging threats

AA2	Conserving, restoring and improving habitat

AA3	Emergency preparedness and response

AA4	Climate change adaptation and resilience

Supporting 	AA5	Effective planning for conservation

AA6	Knowledge and tools

AA7	Forging stronger partnerships

AA8	Community leadership and engagement

Reporting on progress of the targets and specific actions will help inform future actions, where we need to adjust priorities, targets or where we need to adapt actions, and in turn inform the next 5 year Action Plan and progress toward achieving the Strategy 10 year objectives.]

## Priority species and priority places

This first 5 year Action Plan of the Strategy sets actions in motion towards meeting these objectives

##### Objective 1:

By 2026, all priority species on track for improved trajectory by 2031

##### Objective 2:

By 2026, all priority places on track for improved condition by 2031

#### Why is this important?

While all threatened species and natural environments are important, focusing on a limited number of priority species and priority places helps target effort and resources so that tangible outcomes can be achieved, measured and shared.

A key finding from the Australian Government’s first Threatened Species Strategy – launched in 2015 – was that recovery for many species takes time, especially for species that take many years to reproduce. To get priority species and places ‘on track’ for achieving improved trajectories when the Strategy expires in 2031, this Action Plan strives to ensure that a range of activities will be underway to support each priority species and place by at least 2026.

The 100 priority species and 
20 priority places were carefully and strategically selected to ensure a good balance between the important prioritisation principles of extinction risk, multiple benefits, feasibility, importance to people, uniqueness and representativeness across Australia’s widely varied species, landscapes and seascapes.  Improving the trajectories of these priority species and places will not only have direct benefits for the identified species and places, but should also benefit many other threatened species, ecological communities and native wildlife that share the same range or have similar threats.

The Action Plan will begin by establishing baseline status and trends for each priority species and place, then guided by relevant conservation planning documents, identify key recovery actions to prioritise and finally measure and report on progress.

#### What will we do?

By 2022
Collate and publish 2021 baseline information, define measures of success, and identify key activities for all priority species, including:

population and distribution for the 2021 Strategy baseline year

habitat that is important and threats that need to be addressed for the species’ long-term survival and recovery

define for each species how we will measure whether it is successfully on track at 2026* for an improved trajectory by 2031*

key recovery actions to be supported are prioritised, guided by relevant species conservation planning documents and review of activities already underway by other partners.

##### By 2022

Collate and publish 2021 baseline information and identify key actions for all priority places, including:

key indicators for condition, to measure against the 2021 Strategy baseline year

habitat that is important for threatened species and threatened ecological communities and threats that need to be addressed to secure or improve this habitat

threats that need to be addressed to improve the place’s overall condition for threatened species

define for each place how we will measure whether it is successfully on track at 2026 for improved condition by 2031

key recovery actions to be supported are prioritised, guided by existing conservation management and/or regional environmental plans and review of activities already underway by other partners.

##### By 2022-26

Commence or continue key recovery actions and/or build on activities underway, expanding collective recovery and threat management.

##### By 2026

Assess the trajectories of all priority species and condition of all priority places against 
the publicly available 2021/22 baselines and the measures of success.

#### How does this fit with other work?

27 of the 100 priority species were also priority species under the first Threatened Species Strategy. Continuing to work on these species will build on previous actions and baseline information to achieve longer-term outcomes.

#### What can you do?

After the baseline assessments of each species and place are completed in 2022, information on key actions needed to improve their trajectories and condition will be shared on the Strategy home web page at: awe.gov.au/environment/biodiversity/threatened/publications/strategy-home. Check back regularly to stay involved.

## Mitigating established and 
emerging threats – Action Area 1

Reduce the impact of feral cats, foxes, Gamba Grass, Myrtle Rust and new environmental invasives on priority species and places

##### Target 1:

Implement feral cat and fox management across 100% of the important habitat for susceptible priority species, using methods identified as best-practice by 2026

##### Target 2:

Implement feral cat and fox management in 100% of priority places where feral cats and foxes are identified as a key threat to condition, using best practice methods selected for the location by 2026

##### Target 3:

Reduce Gamba Grass to an area less than its 2021 range by 2026

##### Target 4:

Secure 100% of nationally listed species impacted by Myrtle Rust in insurance collections and populations by 2026

##### Target 5:

Reduce introduction and establishment of new exotic environmental pests, weeds and diseases by 2026

#### Why is this important?

Across Australia, feral cats and European red foxes kill native wildlife for food and threaten more than 120 nationally listed threatened species with extinction, and through impacting the balance of fauna species, can degrade the condition of threatened ecological communities.

In northern Australia, the spread of exotic Gamba Grass is threatening native plants by displacing them and threatening native animals by fuelling intense fires. On our east coast, the exotic Myrtle Rust fungus is causing death and disease in many species of Australian trees, including eucalypts, tea trees and bottle brushes.

Reducing the impact of these invasive predators, plants and pathogens will support the recovery of at least 80 priority species and many more nationally listed threatened species in priority places and across the landscape. Looking ahead, reducing the risk of new exotic, invasive species potentially entering Australia will help prevent future losses of native wildlife. We need to find out more about the 168 priority exotic pests, weeds and diseases known to pose significant environmental risk and their potential impact on Australia’s threatened species and ecological communities.

#### What will we do?

| Feral cats and foxes | When |
| --- | --- |
| Define best practice landscape-scale feral predator control for the priority species and/or locations targeted for action through to 2026. This includes locations identified within priority places and important habitat for predator-susceptible priority species. | 2022 |
| Promote best practice landscape-scale feral predator management across priority places and important habitat for predator-susceptible priority species. | 2022-2026 |
| Promote best practice management through the National Feral Cat and Fox Coordinator and Feral Cat Taskforce to coordinate consistent on-ground action. | 2022-2026 |
| Gamba Grass |  |
| Develop a best practice management manual for the control of Gamba Grass and promote to land managers and governments. | 2022 |
| Promote best practice control activities to tackle the threat of Gamba Grass and other invasive grasses in priority places. | 2022-2026 |
| Support Aboriginal and Torres Strait Islander peoples and the community to take action to manage invasive grasses, through programs including Indigenous Protected Areas. | 2022-2026 |
| Work with Western Australia to eradicate Gamba Grass from the known location/s within the state. | 2022-2026 |
| Myrtle Rust |  |
| Undertake a stocktake of nationally listed Myrtle Rust-affected Myrtaceae species held as specimens in seed/germplasm banks/botanical gardens, and their availability for research, recovery and restoration. | 2022 |
| Commence work with relevant groups to include missing specimens held in seed/germplasm banks/botanical gardens. | 2023 |
| Commence ex situ conservation actions, based on relevant conservation planning documents, for all nationally listed Myrtle Rust-affected species. | 2022-2026 |
| Support a national coordinated approach to addressing the risks posed by Myrtle Rust, including through community action to prevent spread and raise awareness. | 2022-2026 |
| New exotic pests, weeds and diseases |  |
| Establish a 2021 baseline for annual introductions and establishment of new exotic environmental pests, weeds and diseases. | 2022 |
| In partnership with state and territory governments, industry, and the community, prioritise activities that will reduce introduction and establishment of new exotic environmental pests, weeds and diseases. | 2026 |

#### How does this fit with other work?

This action area builds on progress under the first Threatened Species Strategy to manage feral cats and extends to other established and emerging invasive species. It focuses on areas where Commonwealth leadership can improve landscape-scale outcomes, including complementing the work of the Chief Environmental Biosecurity Officer and linking efforts between state and territory government and other environment conservation managers.

This includes work to assess risks to threatened species posed by pathogens identified by the National Priority List of Exotic Environmental Pests, Weeds and Disease Implementation Plan.

The assessment of the impact of invasive species and pathogens on priority species and priority places will happen in 2022, under work to establish baseline information for priority species and places for Objective 1 and 2.

#### What can you do?

As the actions listed above are completed, resources to help Australians mitigate these threats will be shared on the Strategy home web page. Check back regularly to stay involved!

In the meantime, simple actions like keeping your cat inside or in a fenced cat run helps our native wildlife to thrive. You can also stop the spread of invasive plants and disease by buying seed locally, don’t buy on-line and when planning to go bushwalking, set time aside to clean your footwear and camping equipment before leaving home.

#### Resources

National Priority List of Exotic Environmental Pests, Weeds and Diseases: awe.gov.au/biosecurity-trade/policy/environmental/priority-list

Approved threat abatement planning documents: awe.gov.au/environment/biodiversity/threatened/threat-abatement-plans/approved

Feral cats control: awe.gov.au/biosecurity-trade/invasive-species/feral-animals-australia/feral-cats

Best practice manual for Gamba Grass (in development)

## Conserving, restoring and 
improving habitat – Action Area 2

Increase the restoration and conservation of important habitat for priority species and places and expand Indigenous-led approaches to managing threatened species

##### Target 6:

Increase the area managed for conservation by 50 million hectares by 2026

#### Why is this important?

Habitat loss, fragmentation and degradation (such as from weeds) diminishes the area that threatened plants and animals need to survive. It has a major impact on nationally listed threatened species, including at least 70 of the priority species.

Working with communities, organisations and land managers to restore and conserve habitat, including restoring connectivity where it’s beneficial, will help threatened species and threatened ecological communities to persist in the landscape and adapt to climate change.

Increasing Indigenous-led land and sea management will make a significant contribution to restoring habitat and achieving healthy ecosystems and continue Traditional Owners’ custodianship of land and sea country.

Existing conservation planning documents, environmental management plans and healthy country plans already in place, will guide where to take action to restore and conserve habitat.

#### What will we do?

|  | When |
| --- | --- |
| Identify habitat important to the survival of priority species and identify actions required to improve this habitat, including whether habitat could be connected to improve the trajectory. | 2022 |
| Identify key actions to restore habitat in priority places where this will be a key measure of condition change using conservation planning documents and other relevant conservation management plans. | 2022 |
| Support 45 million hectares of Indigenous-led place-based planning for integrated land and sea management, such as through Indigenous Protected Areas, and activities to improve habitat for priority culturally-important species and places. | 2026 |
| Focus activities on at least 5 million hectares of important habitat for priority species and within priority places. | 2026 |
| Coordinate activities across jurisdictional and regional borders to improve habitat and connectivity where appropriate. | 2022-2026 |

#### How does this fit with other work?

This action area will build on existing work under the Australian Government’s Indigenous Protected Areas program and the National Landcare Program and can be supported by new measures such as the Supporting Communities Manage Pest Animals and Weeds Program and the Oceans Leadership package. This action area also complements the national environment law, the EPBC Act, by supporting activities to rehabilitate habitat and undertake landscape-scale restoration.

#### What can you do?

As the actions listed above are completed, resources to help Australians restore and rehabilitate habitat will be shared on the Strategy home web page. Check back regularly to stay involved!

You can help our native species by planting your own wildlife garden with native plants, restoring the native habitat on your property, and by donating or volunteering your support to restore and maintain the patch of bushland or coast close to where you live. Find and join a ‘friends of’ group active in your community.

#### Resources

National standards for the practice of ecological restoration in Australia, Society of Ecological Restoration Australasia: seraustralasia.com/standards/home.html

Landcare Australia’s find a group: landcareaustralia.org.au/landcare-get-involved/findagroup/

## Emergency preparedness and 
response – Action Area 3

Prepare for and respond to future emergencies to protect threatened species

Target 7:

Add 5 new species across the national safe haven network to improve representation of invasive predator-susceptible threatened species by 2026

Target 8:

Secure at least 80% of nationally listed threatened plant species in insurance collections by 2026

Target 9:

All jurisdictions and the Commonwealth improve and increase the overall inclusion of critical biodiversity assets into emergency response management and planning systems by 2026

#### Why is this important?

Catastrophic events can push species dangerously close to extinction. Being better prepared, such as through establishing insurance populations or collections, or having systems in place to respond to emergencies, can help avert extinctions.

Safe havens are mainland exclosures or islands which act as arks of safety for our precious wildlife. They provide the long term protection and resources needed to recover and increase species populations, through the permanent removal and exclusion of invasive predators. Safe havens were a key component of the first Threatened Species Strategy and we want to build upon this work to protect more species in more places in a strategic way.

Securing nationally listed plant species in managed populations and collections can provide some protection for these species from future natural disasters, and can complement research, recovery or restoration efforts.

Emergency events, such as bushfires and disease outbreaks, can significantly impact Australia’s threatened species. We want to be better prepared going forward by reflecting upon and learning from the 2019 - 2020 Black Summer bushfires, to help improve our understanding and improve emergency response systems.

#### What will we do?

| Threatened species insurance – animals | When |
| --- | --- |
| Undertake a stocktake of threatened species susceptible to invasive predators that are not adequately represented in the national safe havens network, using the 2020 baseline list prepared for safe havens grants opportunity and other research as a reference, and identify the appropriate actions required to improve species representation. | 2022 |
| Convene a national ‘Safe Haven Network’ working group to build collaboration, coordination and focus effort on improving species representativeness in the national safe haven network during the life of the Action Plan. | 2022 |
| Undertake targeted translocations of underrepresented predator-susceptible species and relevant works to strategically establish safe havens that will improve representation across the network during the life of the Action Plan. | 2026 |
| Threatened species insurance – plants |  |
| Establish a national inventory of living collections (ex situ) of EPBC Act listed plants, including records of availability of material for research, recovery and restoration to ensure we focus effort on threatened plant species that are not currently represented in insurance collections. | 2023 |
| Support research and actions that will increase the number of EPBC Act listed plant species included in insurance collections, and ensure that 30% of these species will be available to support on-ground restoration activities. | 2022-2026 |
| Emergency response |  |
| Capture the actions taken and the lessons learnt from the 2019-20 bushfire response to develop a preparedness framework that can support responses to future environmental emergencies across all jurisdictions. | 2022 |
| Undertake a national stocktake of the approaches by jurisdictions to include critical assets in emergency response management and planning systems. | 2022 |
| Support Commonwealth, state and territory government efforts to identify and incorporate critical biodiversity assets into emergency response management and planning systems to guide future responses to bushfires and other extreme events. | 2024 |
| Determine the risk of different extreme events, including bushfires, impacting priority species and priority places, and build this into Australian Government decision-making and response tools. | 2026 |

#### How does this fit with other work?

This action area builds on progress under the first Threatened Species Strategy. At year 5, it was reported that 10 safe havens were established protecting 9 threatened mammal species; more than 67% of Australia’s listed threatened species were stored in seed banks; and there was increased understanding of many threatened species populations through targeted survey and monitoring.

#### What can you do?

As the actions listed above are completed, resources and information to help Australians get involved and stay up to date with our work will be shared on the Strategy home web page. Check back in regularly.

#### Resources

Bushfire recovery for wildlife and their habitat: awe.gov.au/environment/biodiversity/
bushfire-recovery

## Climate change and 
adaptation – Action Area 4

Improving the resilience and adaptive capacity of priority species and places to climate change

Target 10:

Actions are underway to support the resilience and adaptive capacity of 100% of priority species and places at risk from climate change impacts by 2026

#### Why is this important?

The changing climate is driving changes in species distribution and the composition and function of Australia’s ecosystems and ecological communities. Climatic shifts can exacerbate the impacts of existing pressures, such as habitat fragmentation and invasive species, on threatened species 
and places.

Targeted actions are needed to assist our species and places to adapt to a changing climate and ensure their persistence into the future. However, there is a paucity of information on how climate change will affect many of our species and ecosystems, making it difficult to know where and how on-ground management efforts should be directed.

As such, a critical first step in tackling climate change for our threatened species will be improving our understanding of how changes in climate are projected to affect threatened species and places, as well as their threats.

#### What will we do?

|  | When |
| --- | --- |
| Support relevant research to improve our understanding of how climate change will impact priority species and places, as well as the threats they face. | 2022-2026 |
| Update conservation planning documents where required to include active consideration of climate change risk. | 2022-2026 |
| Identify and undertake management activities to build resilience and/or improve adaptive capacity of priority species and places vulnerable to climate change. Actions to enhance resilience and adaptability could include restoring habitat that will be refugia in the future, re-establishing habitat corridors to help migration and addressing other threats to reduce pressures. | 2026 |

#### How does this fit with other work?

This action area will complement the National Climate Resilience and Adaptation Strategy and can be supported by programs such as the National Environmental Science Program Climate Adaptation cross-cutting mission and the National Landcare Program.

#### What can you do?

As the actions listed above are completed, resources and information to help Australians get involved and stay up to date with our work will be listed on the Strategy home web page. Please check in regularly, and in the meantime scientific guidance on which actions to mitigate the impacts of climate change on susceptible threatened species is listed in relevant conservation advices and recovery plans, also available on the Department of Agriculture, Water and the Environment website.

#### Resources

National Environmental Science Program: awe.gov.au/science-research/nesp

National Climate Resilience and Adaptation Strategy: awe.gov.au/science-research/climate-change/adaptation/strategy

Department of Agriculture, Water and the Environment’s Species Profile and Threats Database: environment.gov.au/cgi-bin/sprat/public/sprat.pl

## Effective conservation
planning – Action Area 5

Maximising the effectiveness of conservation planning for species and places

Target 11:

Track and publish the implementation of priority actions identified in conservation advices, recovery plans and relevant threat abatement plans for 100% of priority species by 2026

#### Why is this important?

Effective conservation planning is critical for recovery of threatened species and threatened ecological communities. Conservation planning documents provide a detailed, evidence-based and objective framework to direct action that will halt decline and/or support recovery of threatened species and ecological communities.

Having contemporary conservation and threat abatement plans will ensure that coordinated actions can be taken to support each priority species and place, enabling new approaches to be included as appropriate. Contemporary plans may also support landscape and marine based approaches such as regional planning. As these actions are undertaken by recovery teams and other groups, having these activities and related data reported consistently will allow progress towards recovery to be monitored.

#### What will we do?

|  | When |
| --- | --- |
| Develop and publish best practice governance for effective coordination and reporting of recovery team actions and implementation of threat abatement plans. | 2024 |
| Support the ongoing development of ‘fit-for-purpose’ conservation planning documents, including: conservation advices and recovery plans for single, multiple or regionally clustered groups of threatened species and ecological communities that include information about key actions that will drive recovery, important habitat and climate susceptibility where appropriate trial development of place-based plans to improve habitat condition for multiple threatened species found within priority places threat abatement planning documents, including threat abatement plans, advices or action plans ensure conservation and threat abatement planning documents that inform management of priority species and places are reviewed and updated in line with the Department of Agriculture, Water and the Environment’s modernisation process. | 2022-2026 |
| Support recovery coordinators for priority species/species clusters that have complex recovery needs and multiple partners supporting recovery efforts. | 2022-2026 |
| Support and promote best practice guidelines for key recovery actions (including the use of standardised national monitoring protocols and data management standards, wildlife health guidance and protocols for translocations, ex situ conservation and seed collection). | 2022-2026 |
| Strengthen integration of conservation planning with other planning processes, and across levels of government and community initiatives, to maximise conservation outcomes. | 2022-2026 |

#### How does this fit with other work?

This work will build on baselines determined in 2022 to clearly articulate priority conservation objectives for priority species and priority places, under Objectives 1 and 2.  Actions will complement initiatives, including delivery of a pilot regional plan, as set out in A pathway for reforming national environmental law and accompanying Proposed timeline for EPBC Act reforms and the work being delivered by the Threatened Species Scientific Committee.

#### What can you do?

As the actions listed above are completed, updated resources to support recovery action will be shared on Strategy home web page. Check back regularly to stay involved or visit the Species Profiles and Threats database to learn more about conservation planning activities relevant to the threatened species of interest to you.

#### Resources

Best practice manual for effective coordination and reporting of recovery team actions and Threat Abatement Plan implementation (in development)

A pathway for reforming national environmental law: awe.gov.au/environment/epbc/about/environmental-law-reform

Proposed timeline for EPBC Act reforms: awe.gov.au/environment/epbc/publications/proposed-timeline-for-epbc-act-reforms

Species Profiles and Threats database: environment.gov.au/cgi-bin/sprat/public/sprat.pl

Monitoring, Evaluation, Reporting and Improvement Tool (MERIT) online reporting tool: fieldcapture.ala.org.au/home/about

## Knowledge and tools – Action Area 6

Having the best available information and tools

Target 12:

Develop at least 5 new tools to mitigate impact of broad-scale threats on threatened species 
by 2026

Target 13:

Establish a monitoring program to fill critical data and information gaps for 50% of priority species by 2026

#### Why is this important?

Many of our threatened species and ecological communities are poorly understood with a continuing need to improve our knowledge base through long-term monitoring and research. By modernising technologies and systems, national-level data and information can be more efficiently consolidated into a leading source of biodiversity information that is readily accessible to governments, conservation managers, industry and the community.

Better quality information that is easily accessible can underpin more informed decision making.

With real-time access to the best available information, and with the right tools, we can target actions most likely to succeed in order to recover priority species and restore priority places.

#### What will we do?

|  | When |
| --- | --- |
| Support a national program of research to develop new tools to support threatened species recovery and threat management. | 2022-2026 |
| Refine and promote a national standardised monitoring protocol and best practice guidelines fit for priority species and places. | 2022 |
| Undertake a stocktake of nationally listed threatened species to identify and prioritise the critical information and data gaps relating to distribution, population and critical habitat requirements to inform the establishment of a national monitoring program. | 2022 |
| Establish national monitoring programs for species identified as requiring activities to fill critical data and information gaps. | 2024 |
| Promote Indigenous-led research and two-way knowledge transfer to benefit priority species and places. | 2022-2026 |

#### How does this fit with other work?

This Action Area can be supported by programs such as the Australian Government’s National Environmental Science Program. It can also contribute to delivering components of the new national environmental standards and digital transformation initiatives as set out in A pathway for reforming national environmental law and the accompanying Proposed timeline for EPBC Act reforms.

#### What can you do?

As the actions listed above are completed, resources to support access to data, information and tools, best practice guidelines and protocols will be shared on the Strategy home web page.

If you have threatened species data to share or want to be involved in monitoring for species, head to the Atlas of Living Australia citizen science portal to find data and information being captured from across Australia.

#### Resources

The national program of research and national monitoring protocols (in development)

Atlas of Living Australia – Open access to Australia’s biodiversity data: ala.org.au

Australian Citizen Science Association - Project Finder: citizenscience.org.au/ala-project-finder

##### Coordinating national research to support threatened species

There are a range of scientific and Indigenous-led institutions, agencies and groups across Australia conducting important research and data collection to support threatened species recovery and threat management.

Through supporting and coordinating actions in this Action Plan, the Australian Government is striving to:

Improve our understanding about priority species, priority places and threats, in particular:

species resilience, response and susceptibility to extreme events (e.g. bushfires) and a changing climate

how species and threats are likely to move or change in response to climate change

what place-based and ex situ management actions are needed, including for example future seed banking, germplasm collection and storage, gene banking, captive breeding, ex situ conservation and translocation or reintroduction.

Support development of new and improved tools and techniques to better monitor, protect and recover priority species and improve condition at priority places.

Support development of new and improved tools and techniques to better detect, track and suppress one or more invasive grasses, feral predators and Myrtle Rust.

Streamline and improve access to search and share national threatened species data and spatial information, research and published information, including digitising conservation planning and threat abatement documents.

#### What will monitoring protocols do?

Monitoring protocols will be used to capture consistent baseline and ongoing time-series data for all priority species and places compatible with the national data standards.

The protocols will be available and used for threatened species projects funded through Australian Government investments and progressively included in updates to conservation planning documents.

Data captured through monitoring will be compatible with national environmental standards for data and available on the national environmental systems and biodiversity data repositories managed by the Australian Government.

## Forging stronger partnerships – Action Area 7

Strengthening relationships with existing conservation partners and helping forge new partnerships

Target 14:

Proactively engage Aboriginal and Torres Strait Islander people in the preparation of 100% of EPBC Act conservation planning documents for culturally significant threatened species and ecological communities by 2026

Target 15:

Partners and/or private investment will support 50% of projects that benefit priority species and places, to help increase information base and assist recovery by 2026

#### Why is this important?

Conservation is everybody’s business and it’s only by working together that we can use collective expertise and resources to best effect. Strong partnerships between all levels of government, conservation land and sea managers, business, researchers, the community and with Aboriginal and Torres Strait Islander peoples are essential to effectively coordinate action and link recovery efforts.

Previous reporting on the 2015 Threatened Species Strategy demonstrated the extensive contribution of all partners to improving the trajectory of priority species and tackling the impacts of feral cats. By setting more explicit targets, this Action Plan helps drive increased collaboration and partnerships.

#### What will we do?

| Strengthening partnerships with Aboriginal and Torres Strait Islander peoples | When |
| --- | --- |
| Incorporate Indigenous ecological knowledge of priority species and places, as appropriate, into baseline assessments and development of indicators under Objectives 1 and 2 of the Action Plan. | 2022 |
| Undertake a stocktake of Indigenous-led recovery activities supporting culturally significant threatened species and ecological communities funded by the Australian Government. | 2022 |
| Incorporate Indigenous ecological knowledge and engage Indigenous land and sea managers in conservation activities and planning documents relating to culturally significant threatened species and ecological communities. | 2022-2026 |
| Design biodiversity conservation and natural resource management programs to actively facilitate Indigenous-led and Indigenous partnership projects. | 2022-2026 |
| Funding partnerships and private financing |  |
| Work with the financial and agricultural sectors to increase private financing of landscape conservation and restoration. | 2022-2026 |
| Support innovative market mechanisms for increasing biodiversity and conservation of remnant native vegetation in productive landscapes. | 2022-2026 |
| Promote initiatives to direct private and philanthropic investment in threatened species recovery projects and support collaborative partnerships. | 2022-2026 |
| Conservation partnerships with private land and water managers |  |
| Support long-term stewardship of high value habitat for threatened species and ecological communities by land and water managers contributing to landscape-scale conservation priorities. | 2022-2026 |
| Encourage and provide extension advice and support to land and water managers who are interested in long term stewardship of their lands. | 2022-2026 |

#### How does this fit with other work?

This action area recognises the existing collaboration and contributions being delivered by existing partners who are leading threatened species conservation initiatives, both in Australia and internationally. It also complements emerging Australian Government programs on improving private sector investment in natural capital and increasing collaboration with Australia’s agriculture sector through the Agriculture Biodiversity Stewardship Package. We will continue to support and promote the work of partners, create opportunities to build more awareness and capacity across a growing network of threatened species practitioners, acknowledging the collective efforts of all helping to put species on the path to recovery. Australia’s Nature Hub provides an interactive platform for all biodiversity conservation actions underway being led by various organisations.

#### What can you do?

After the baseline assessments of each species and place are completed in 2022, information 
on partnership opportunities will be shared on the Strategy home web page. Check back regularly to stay involved!

#### Resources

Agriculture Biodiversity Stewardship: awe.gov.au/agriculture-land/farm-food-drought/natural-resources/landcare/sustaining-future-australian-farming

Australia’s Nature Hub: australiasnaturehub.gov.au/

Australia’s Strategy for Nature: awe.gov.au/environment/biodiversity/conservation/strategy

Natural capital - unlocking private sector investment: awe.gov.au/science-research/climate-change/adaptation/publications/natural-capital

## Community leadership and 
engagement – Action Area 8

Educating and empowering the community to participate in and lead on recovery efforts for priority species

Target 16:

Citizen science or community groups will lead activities for 
50% of priority species and places to increase information base and assist recovery by 2026

#### Why is this important?

Successful conservation relies on collaboration. The knowledge, support and engagement of dedicated individuals, volunteers, Aboriginal and Torres Strait Islander peoples, community groups and the business sector are integral for the successful conservation of Australia’s threatened species and ecosystems.

While there is much work to do to ensure our threatened species and ecosystems thrive in the future, by working collectively we can build on shared aspirations and bring together our unique values and strengths to solve complex environmental challenges.

Community connection to the local environment, participation and capacity building underpin all action areas and associated targets.

#### What will we do?

|  | When |
| --- | --- |
| Require community involvement in Australian Government projects where appropriate. | 2022-2026 |
| Work with the community to improve understanding of environmental threats and promote behavioural change to benefit threatened species through social media channels and engagement programs. | 2022-2026 |
| Support citizen science partners and initiatives to increase community engagement in threatened species monitoring and management. | 2022-2026 |
| Support schools, community groups, businesses and individuals to champion threatened species and undertake activities for local threatened plants and animals. | 2022-2026 |
| Share success stories online of the community members who champion threatened species or play a role in the stewardship of threatened species and ecological communities. | 2022-2026 |

#### How does this fit with other work?

This Action Area builds on progress under the first Threatened Species Strategy to raise awareness and encourage action to recover threatened species.

#### What can you do?

You can volunteer for conservation work or visit the Australian Citizen Science Association for more ideas on how you can help scientists and field experts to collect and analyse data, contributing to real-time citizen scientist projects underway across Australia.

You can become a champion for threatened species in your school, your business and your community.

You can keep up to date with the latest news on threatened species management and implementation of this Action Plan by following the Threatened Species Commissioner’s social media channels or the Strategy home webpage.

#### Resources

Stay connected:

Follow the Threatened Species Commissioner on Facebook, Instagram or twitter: facebook.com/TSCommissioner, instagram.com/tscommissioner/, @TSCommissioner - Twitter

Visit the Australian Citizen Science Association: citizenscience.org.au

## Tracking progress and 
reporting

Reporting on the Action Plan objectives and targets will occur at the end of 
this plan in 2026 with a progress report prepared at the end of 2024.

A review will also be undertaken in 2026 to identify any improvements needed in developing the next 5 year Action Plan to meet the Strategy’s 10 year objectives.

The Threatened Species Commissioner will work with existing and new partners to implement the Action Plan, providing guidance to support the design and delivery of projects aligned to the identified actions.

By the end of 2022, the Threatened Species Commissioner will publish priority species and places profiles, including assessments of the baseline information. Profiles for priority species and places will also identify key indicators for measuring success to assess whether species and places are on track for improving trajectory and condition respectively by 2031.

Priority species and places profiles, progress reports, and all related assessments, plans and reports supporting implementation of this Action Plan will be published and shared on the Strategy home webpage at awe.gov.au/environment/biodiversity/threatened/publications/strategy-home.

## Definitions

Action

Activities listed under the ‘What will we do?’ section of each action area, to be undertaken during the period of the Action Plan.

Adequate representativeness

Six or more genetically and demographically viable populations of species protected within the national safe haven network (See AA1 and AA3).

Climate susceptibility (AA4)

A measure of a species or places’ susceptibility to climate change. Some species are at more risk from climate change than others due to ecological or physiological traits. The IUCN has a developed a framework for determining whether a species is ‘climate change-susceptible’: www.iucn.org/downloads/climate_change_and_species.pdf.

Condition (of places)

Key characteristics and functions of an ecosystem at a point in time, describing the state of the environment’s physical features, species composition, community structure, ecosystem function, presence/absence of threats and external exchanges/influences.

Conservation planning documents

Statutory conservation plans provide guidance on the management and research actions to support the recovery of particular entities. The two types of planning documents under the EPBC Act include conservation advices and recovery plans. These documents can also extend in scope to include multi-entity conservation plans and bioregional plans.

Critical biodiversity assets

Biodiversity assets identified by jurisdictions, environment management agencies or environmental law as important to preserve during emergencies or natural disasters e.g., species, ecological communities, habitat features.

Ecological function

The collective term for the roles and processes that arise from interactions among living and non-living components of ecosystems. Examples include nutrient cycling and sequestration (through biomass accumulation, food production, herbivory, predation and decomposition), water filtration and cycling, soil formation, succession, disturbance regimes (fire, flooding and drying), water filtration and storage, provision of habitat, predation, dispersal, pollination, reproduction, disturbance and resilience.

EPBC Act

The Environment Protection and Biodiversity Conservation Act 1999 – also known as national environment law.

Important habitat

Habitat described in conservation planning documents or research as being important to the survival of EPBC listed species or Threatened Ecological Communities.

Indicators of success – improved condition

A semi-quantitative rating system based on biotic and abiotic characteristics that provide comparative assessment of how well the attributes of an ecosystem are recovering after treatment, e.g. species composition, habitat integrity (structure, ecosystem function), presence to absence of threats, external influences – future prospects (Society for Ecological Restoration - National Restoration Standards 5-star recovery).

Insurance collections and populations

Relating to ex situ conservation of plant species including seed banking, tissue culture, cryopreservation and living plant collections in botanical gardens and plant populations in situ.

Myrtle Rust impacted

Myrtle Rust is a disease caused by the exotic fungus Austropuccinia psidii (formerly Puccinia psidii, initially identified as Uredo rangelii). There is only one strain of rust in Australia. Myrtle rust threatens trees and shrubs in the Myrtaceae family of plants which includes Australian natives like bottle brush (Callistemon spp.), tea tree (Melaleuca spp.) and eucalypts (Eucalyptus spp., Angophora spp., and Corymbia spp.). The disease can cause deformed leaves, heavy defoliation of branches, reduced fertility, dieback, stunted growth, and plant death.

Objectives

Overarching goals for this Action Plan, to be achieved in 2026.

Predator-susceptible species

Threatened species that are at risk of extinction due to predators such as feral cats and foxes. A list of predator-susceptible mammals is attached to the safe havens grants opportunity – see resources for links.

Recovery

The process of an ecosystem regaining its composition, structure and function relative to the levels identified for the reference ecosystem. In restoration, recovery is assisted by restoration activity—and recovery can be described as partial or full.

Resilience

The degree, manner and pace of recovery of species after a disturbance or stress, or the potential or capacity for such recovery. This property is developed by natural selection under conditions of exposure of the species to disturbance over evolutionary time scales—and enables a species or population to persist despite disturbance.

Restoration

The process of returning of a degraded habitat to its original species composition, structure and function.

Target

Specific achievements to be completed within articulated timeframes, to support achievement of the Action Plan objectives.

Trajectory

A pathway of recovery over time, defined and monitored using sequential measurements pre-determined baseline parameters/indicators, e.g. species population, management actions (species, habitat, threats and research) and future prospects.

## Links

A pathway for reforming national environmental law
awe.gov.au/environment/epbc/about/environmental-law-reform

Agriculture Biodiversity Stewardship Package 
awe.gov.au/agriculture-land/farm-food-drought/natural-resources/landcare/sustaining-future-australian-farming

Atlas of Living Australia
ala.org.au

Australian Bureau of Agricultural and Resource Economics and Sciences
awe.gov.au/abares

Australian Biological Resources Study
awe.gov.au/science-research/abrs

Australia’s international role in conserving biodiversity
awe.gov.au/environment/biodiversity/international and awe.gov.au/environment/water/wetlands/ramsar

Australia’s Nature Hub
australiasnaturehub.gov.au

Australia’s Strategy for Nature 2019-2030
australiasnaturehub.gov.au/national-strategy

Australian Weeds Strategy and the Australian Pest Animal Strategy
awe.gov.au/biosecurity-trade/pests-diseases-weeds/pest-animals-and-weeds

Chief Environmental Biosecurity Officer
awe.gov.au/biosecurity-trade/environmental/cebo

Commonwealth Biosecurity 2030
awe.gov.au/ biosecurity-trade/policy/commonwealth-biosecurity-2030

Commonwealth Environmental Water Holder
awe.gov.au/water/cewo

Commonwealth Marine Parks
parksaustralia.gov.au/marine

Emissions Reduction Fund
cleanenergyregulator.gov.au/ERF

Environment and Invasives Committee 
awe.gov.au/ biosecurity-trade /pests-diseases-weeds/pest-animals-and-weeds/eic

Environmental Restoration Fund
awe.gov.au/environment/environment-restoration-fund

Environmental law reform
awe.gov.au/environment/epbc/about/environmental-law-reform

Indigenous Ranger programs
niaa.gov.au/indigenous-affairs/environment/indigenous-ranger-program

Indigenous Protected Areas
awe.gov.au/agriculture-land/land/indigenous-protected-areas

National Agreement on Closing the Gap
closingthegap.gov.au/national-agreement

Natural capital: unlocking private sector investment  
awe.gov.au/science-research/climate-change/adaptation/publications/natural-capital

National Collaborative Research Infrastructure Strategy
dese.gov.au/ncris

National Environmental Science Program
awe.gov.au/science-research/nesp

National Indigenous Australians Agency 
niaa.gov.au

National Landcare Program
nrm.gov.au/national-landcare-program

National Priority List of Exotic Environmental Pests, Weeds and Diseases
awe.gov.au/biosecurity-trade/policy/environmental/priority-list

National Recovery and Resilience Agency
recovery.gov.au

National Reserve System
awe.gov.au/agriculture-land/land/nrs

National Standards for Ecological Restoration
seraustralasia.com/pages/standards.html

Parks Australia
parksaustralia.gov.au

Royal Commission into National Natural Disaster Arrangements
naturaldisaster.royalcommission.gov.au

Safe havens grant opportunity – list of predator susceptible mammals
awe.gov.au/environment/biodiversity/threatened/publications/strategy-home

Species of National Environmental Significance
awe.gov.au/environment/environmental-information-data/databases-applications/snes

Species Profile and Threat Database 
environment.gov.au/cgi-bin/sprat/public/sprat.pl

The Reef Trust
awe.gov.au/parks-heritage/great-barrier-reef/reef-trust

Threat Abatement Plans: feral cats, foxes, invasive grasses and others
awe.gov.au/environment/biodiversity/threatened/threat-abatement-plans/approved

Threatened Species Commissioner
awe.gov.au/environment/biodiversity/threatened/commissioner

Threatened Species Strategy
awe.gov.au/environment/biodiversity/threatened/publications/strategy-home

Threatened Species Scientific Committee
awe.gov.au/environment/biodiversity/threatened/tssc

## Appendix 1: 100 Priority species

Focused efforts will contribute to the Strategy’s high-level objective:

To improve the trajectories of priority threatened species by 2031

The priority species list includes plants and animals found across Australia in a range of environments, from the arid deserts to rainforests, forests to grasslands, and inland waters to the sea. All taxonomic groups listed under the EPBC Act are included. Recovery actions for many of the priority species will also benefit other threatened species that share their habitat.

#### Selecting priorities

The 100 priority species were selected using a multi-criteria decision analysis process, using scores against the Threatened Species Strategy’s 6 prioritisation principles. Over 1800 species listed under the EPBC Act as either Critically Endangered, Endangered or Vulnerable during the first quarter of 2021 were reviewed as part of this prioritisation process. Species were scored using national-scale data sets by independent ecologists and the Australian community was also invited to have a say on species important to them.

Birds

Australasian Bittern 
Botaurus poiciloptilus

Black-eared Miner 
Manorina melanotis

Carnaby’s Cockatoo 
Zanda latirostris

Christmas Island Goshawk 
Accipiter hiogaster natalis

Eastern Curlew 
Numenius madagascariensis

Golden-shouldered Parrot, Alwal 
Psephotus chrysopterygius

Hooded Plover (eastern) 
Thinornis cucullatus cucullatus

King Island Brown Thornbill 
Acanthiza pusilla magnirostris

Malleefowl 
Leipoa ocellata

Night Parrot 
Pezoporus occidentalis

Norfolk Island Green Parrot 
Cyanoramphus cookii

Orange-bellied Parrot 
Neophema chrysogaster

Plains-wanderer 
Pedionomus torquatus

Princess Parrot 
Polytelis alexandrae

Red Goshawk 
Erythrotriorchis radiatus

Red-tailed Black Cockatoo (SE) 
Calyptorhynchus banksii graptogyne

Regent Honeyeater 
Anthochaera phrygia

Swift Parrot 
Lathamus discolor

Western Ground Parrot, Kyloring Pezoporus flaviventris

White-throated Grasswren, Yirlinkirrkirr 
Amytornis woodwardi

Mammals

Australian Sea-lion 
Neophoca cinerea

Brush-tailed Rock-wallaby 
Petrogale penicillata

Central Rock-rat, Antina 
Zyzomys pedunculatus

Chuditch, Western Quoll 
Dasyurus geoffroii

Eastern Quoll, Luaner 
Dasyurus viverrinus

Gilbert’s Potoroo, Ngilkat 
Potorous gilbertii

Greater Bilby 
Macrotis lagotis

Kangaroo Island Echidna 
Tachyglossus aculeatus multiaculeatus

Koala (Qld, NSW, ACT) 
Phascolarctos cinereus

Leadbeater’s Possum 
Gymnobelideus leadbeateri

Mountain Pygmy-possum 
Burramys parvus

New Holland Mouse, Pookila 
Pseudomys novaehollandiae

Northern Brushtail Possum 
Trichosurus vulpecula arnhemensis

Northern Hairy-nosed Wombat, Yaminon 
Lasiorhinus krefftii

Northern Hopping-mouse, Woorrentinta 
Notomys aquilo

Northern Quoll 
Dasyurus hallucatus

Numbat 
Myrmecobius fasciatus

Quokka 
Setonix brachyurus

Spectacled Flying-fox 
Pteropus conspicillatus

Western Ringtail Possum 
Pseudocheirus occidentalis

Fish

Freshwater Sawfish 
Pristis pristis

Grey Nurse Shark (eastern) 
Carcharias taurus

Maugean Skate 
Zearaja maugeana

Murray Hardyhead 
Craterocephalus fluviatilis

Red Handfish 
Thymichthys politus

Redfin Blue-eye 
Scaturiginichthys vermeilipinnis

Stocky Galaxias 
Galaxias tantangara

Swan Galaxias 
Galaxias fontanus

White’s Seahorse 
Hippocampus whitei

Frogs

Growling Grass Frog, Southern Bell Frog 
Litoria raniformis

Kroombit Tinker Frog 
Taudactylus pleione

Southern Corroboree Frog
Pseudophryne corroboree

Invertebrates

Ammonite Snail 
Ammoniropa vigens

Cauliflower Soft Coral 
Dendronephthya australis

Eltham Copper Butterfly 
Paralucia pyrodiscus lucida

Giant Gippsland Earthworm 
Megascolides australis

Lord Howe Island Phasmid 
Dryococelus australis

Margaret River Burrowing Crayfish 
Engaewa pseudoreducta

Mount Lidgbird Charopid Land Snail 
Pseudocharopa ledgbirdi

Pink Underwing Moth 
Phyllodes imperialis smithersi

Tasmanian Giant Freshwater Crayfish 
Astacopsis gouldi

Reptiles

Arnhem Land Gorges Skink 
Bellatorias obiri

Bellinger River Snapping Turtle 
Wollumbinia georgesi

Collared Delma, Adorned Delma 
Delma torquata

Great Desert Skink, Tjakura, Warrarna, Mulyamiji 
Liopholis kintorei

Green Turtle 
Chelonia mydas

Olive Ridley Turtle 
Lepidochelys olivacea

Pygmy Blue-tongue Lizard 
Tiliqua adelaidensis

Short-nosed Sea Snake 
Aipysurus apraefrontalis

Yinnietharra Rock-dragon 
Ctenophorus yinnietharra

Plants

Adamson’s Blown-grass 
Lachnagrostis adamsonii

Angle-stemmed Myrtle 
Gossia gonoclada

Arckaringa Daisy 
Olearia arckaringensis

Border Ranges Lined Fern 
Antrophyum austroqueenslandicum

Bulberin Nut 
Macadamia jansenii

Carrington Falls Pomaderris 
Pomaderris walshii

Davies’ Waxflower 
Phebalium daviesii

Eremophila subangustifolia

Foote’s Grevillea 
Grevillea calliantha

Forked Spyridium 
Spyridium furculentum

Giant Andersonia 
Andersonia axilliflora

Graveside Leek-orchid 
Prasophyllum taphanyx

Imlay Mallee 
Eucalyptus imlayensis

King Blue-grass 
Dichanthium queenslandicum

Lax Leek Orchid 
Prasophyllum laxum

Little Mountain Palm 
Lepidorrhachis mooreana

MacDonnell Ranges Cycad 
Macrozamia macdonnellii

Native Guava 
Rhodomyrtus psidioides

Pimelea cremnophila

Bolivia Hill Rice-flower
Pimelea venosa

Scaly-butt Mallee 
Eucalyptus leprophloia

Small-flowered Snottygobble 
Persoonia micranthera

Smooth Davidson’s Plum 
Davidsonia johnsonii

Stiff Groundsel 
Senecio behrianus

Stirling Range Dryandra 
Banksia montana

Tangled Wattle 
Acacia volubilis

Waddy, Waddi, Waddy-wood, Birdsville Wattle 
Acacia peuce

Wollemi Pine 
Wollemia nobilis

Wongan Eriostemon 
Philotheca wonganensis

Woods Well Spyridium 
Spyridium fontis-woodii

These top-ranking species were selected using a multi-criteria decision analysis process that reviewed all species listed under the EPBC Act categories of Vulnerable, Endangered or Critically Endangered and their score against the Strategy’s 6 prioritisation principles. Species were scored with input from independent ecologists who are experts in their field and the latest available data.

## Appendix 2: Priority places

Twenty priority places will be the focus for targeted actions over 5 years from 2021 to 2026, contributing to the Strategy’s objective:

To improve the condition of priority places by 2031

#### Why priority places?

All threatened species share habitat with other species. Priority places under the Threatened Species Strategy 2021-2031 will provide a place-based focus for research, support and recovery action for threatened species and threatened ecological communities that are present within identified places. The Strategy’s objective is to improve the condition of priority places by 2031, benefiting both threatened and non-threatened species and ecological communities.

#### How are priority places selected?

Twenty priority places are being selected using prioritisation principles established in the Strategy. Nearly 2000 potential places have been considered, including all biogeographic (IBRA) subregions, all Key Biodiversity Areas, all Ramsar and Nationally Significant wetlands, as well as places identified by the Department of Agriculture, Water and the Environment and threatened species managers from state and territory governments.

These sites were initially scored by density of threatened species and ecological communities likely present, and the proportion of each site under Indigenous management. High scoring places were further refined by considering spread across different jurisdictions and biomes.

The final list will include a range of places across Australia, extending into our marine environment. Most places will have high densities of threatened species and threatened ecological communities, others will have significant cultural values for the Indigenous groups that manage them, and others will be places where targeted action on particular threats will benefit multiple threatened species.

#### What will happen in priority places?

During 2022, a profile for each priority place will be developed that describes key natural values for its threatened species and threatened ecological communities. Place profiles will identify important areas for support and recovery that the Strategy will focus on, including goals to meet to improve the place’s condition and the actions needed to achieve these. Actions will be specific for each place and may include elimination of particular invasive pests or weeds, implementation of Indigenous ecological management practices, habitat restoration and/or augmentation and research to inform actions.

Support for these actions will be prioritised through relevant Australian Government policies and programs. State and territory governments, natural resource managers, land and sea managers and community groups will be encouraged to partner with us in working towards these goals. Our combined achievements will be measured in 2026 to determine if the Strategy’s objectives are being met.

#### What does it mean for landholders and managers?

Land and sea managers at a priority place will be invited to participate in improving the condition of the place for threatened species and threatened ecological communities. Identification as a priority place is non-statutory – it does not involve a change in regulatory requirements under the EPBC Act at that location.  Rather, designation as a priority place signals a focus in effort by the Australian Government in collaboration with willing partners, through on-ground management and complementary research to improve the condition of that place. As with any voluntary arrangement, the nature of the partnerships and the extent of engagement of land managers, is expected to vary within and between places.

#### Which places?

Finalisation of all 20 priority places is underway, with all places to be announced by early 2022.

Six places that have already been confirmed are natural islands, where actions to address particular threats are underway and there is strong interest in continuing. These islands are:

Bruny Island, Tasmania

Christmas Island, Indian Ocean

French Island, Victoria

Kangaroo Island, SA

Norfolk Island, Tasman Sea

Raine Island, Queensland