INTERIM RECOVERY PLAN NO. 304

SHY FEATHERFLOWER

(Verticordia fimbrilepis subsp. fimbrilepis)

INTERIM RECOVERY PLAN

2010-2015

December 2010

Department of Environment and Conservation

Kensington

FOREWORD

Recovery plans (RPs) and Interim Recovery Plans (IRPs) are developed within the framework laid down in Department of Conservation and Land Management (CALM) Policy Statements Nos. 44 and 50. Note: the Department of CALM formally became the Department of Environment and Conservation (DEC) in July 2006. DEC will continue to adhere to these Policy Statements until they are revised and reissued.

Plans outline the recovery actions that are required to urgently address those threatening processes most affecting the ongoing survival of threatened taxa or ecological communities, and begin the recovery process.

DEC is committed to ensuring that Threatened taxa are conserved through the preparation and implementation of plans and by ensuring that conservation action commences as soon as possible and, in the case of Critically Endangered (CR) taxa, always within one year of endorsement of that rank by the Minister.

This plan will operate from December 2010 to November 2015 but will remain in force until withdrawn or replaced. It is intended that, if the taxon is still ranked as Vulnerable in WA under IUCN (2001) criteria the plan will be reviewed after five years and the need for further recovery actions assessed.

This plan was approved by the Director of Nature Conservation on 2 December 2010. The provision of funds identified in this plan is dependent on budgetary and other constraints affecting DEC, as well as the need to address other priorities. Information in this plan was accurate at December 2010.

Note: although the plan was written and endorsed as an IRP in Western Australia it is treated as a Plan under the EPBC Act.

PLAN PREPARATION

This plan was prepared by Robyn Luu1 and Andrew Brown2.

# 1 Project Officer, Species and Communities Branch, DEC, Locked Bag 104, Bentley Delivery Centre, WA 6983.

2 Threatened Flora Coordinator, DEC Species and Communities Branch, Locked Bag 104, Bentley Delivery Centre, WA 6983.

ACKNOWLEDGMENTS

The following people provided assistance and advice in the preparation of this IRP:

Kristine Brooks	Flora Conservation Officer, DEC Great Southern District

Anne Cochrane	Senior Research Scientist, Threatened Flora Seed Centre, DEC Science Division

Colin Crane	Technical Officer, DEC Science Division

Andrew Crawford	Principal Technical Officer, Threatened Flora Seed Centre, DEC Science Division

Jessica Donaldson	Threatened Flora Database Officer, DEC SCB

Greg Durell	District Manager, DEC Great Southern District

Fred and Jean Hort	Volunteers

Peter Lacey	Program Leader Nature Conservation, DEC Great Southern District

Amanda Shade	Assistant Curator (Nursery) Botanic Gardens and Parks Authority

Marnie Swinburn	Flora Conservation Officer, DEC Perth Hills District

Thanks also to the staff of the W.A. Herbarium for providing access to Herbarium databases and specimen information, and DEC's Species and Communities Branch for assistance.

Cover photograph by Bethea Loudon.

CITATION

This Recovery plan should be cited as:

Department of Environment and Conservation (2010) Verticordia fimbrilepis subsp. fimbrilepis Interim Recovery Plan 2010-2015. Interim Recovery Plan No. 304. Department of Environment and Conservation, Western Australia.

# SUMMARY

| Scientific Name: Verticordia fimbrilepis subsp. fimbrilepis | Common Name: Shy Featherflower |
| --- | --- |
| Family: Myrtaceae | Flowering Period: July to December |
| DEC Regions: Wheatbelt, Swan | DEC Districts: Perth Hills, Great Southern |
| Shires: Woodanilling, West Arthur, Brookton, Kojonup, Narrogin, Pingelly, Beverley, Wandering, Cuballing | NRM Regions: Avon, South West |
| Recovery Teams: Swan Region Threatened Flora and Communities Recovery Team (SRTFCRT); Great Southern District Threatened Flora Recovery Team (GSDTFRT) |  |

Illustrations and/or further information: Brown, A., Thomson-Dans, C. and Marchant, N. (Eds). (1998) Western Australia’s Threatened Flora. Department of Conservation and Land Management, Western Australia; George, A.S. (1991) New taxa, combinations and typifications in Verticordia (Myrtaceae: Chamelaucieae). Nuytsia 7 (3): 231–394; George, A.S. (2002) Verticordia: the turner of hearts. University of Western Australia Press, Crawley; Western Australian Herbarium (1998−) FloraBase − The Western Australian Flora. Department of Environment and Conservation. http://florabase.dec.wa.gov.au/.

Current status: Verticordia fimbrilepis subsp. fimbrilepis was declared as Rare Flora under the Western Australian Wildlife Conservation Act 1950 in September 1987 and is currently ranked Vulnerable in Western Australia against World Conservation Union (IUCN 2001) criteria. The subspecies is listed under the Environment Protection and Biodiversity Conservation Act 1999 (EPBC Act 1999) as Endangered. The main threats to the subspecies are insecure land tenure, road maintenance activities, weed invasion, poor recruitment, inappropriate fire regimes, grazing, trampling, feral pigs, Phytophthora dieback, powerline maintenance, salinity, farming activities and gravel extraction.

Description: Verticordia fimbrilepis subsp. fimbrilepis is a small bushy shrub, 30–70 cm tall and 20–70 cm wide. It has pale-pink or occasionally white flowers on short peduncles. Flowers are in small rounded groups at the tips of branches. The petals are markedly narrowed towards the tip with margins finely fringed. The staminodes are fringed across their broad apex, and a single hair in the centre is much longer than the others (George 2002).

Habitat requirements: Verticordia fimbrilepis subsp. fimbrilepis is widely distributed from southeast of Armadale to Brookton and Kojonup. It grows in low-lying shallow grey sand and yellowish-white sandy loam over gravel, sometimes with clay, in heath and scrubland and open wandoo woodland (George 2002).

Habitat critical to the survival of the species, and important populations: It is considered that the habitat for populations 4, 5, 7, 8, 10, 11, 12, 14 and 16 is critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis and that these populations are important populations. Habitat critical to the survival of V. fimbrilepis subsp. fimbrilepis includes the area of occupancy of these populations, areas of similar habitat surrounding these populations (these providing potential habitat for population expansion and for pollinators), additional occurrences of similar habitat that may contain undiscovered populations of the subspecies or be suitable for future translocations, and the local catchment of these populations for the surface and/or groundwater that maintains the habitat of the subspecies.

Benefits to other species or ecological communities: Recovery actions implemented to improve the quality or security of the habitat of Verticordia fimbrilepis subsp. fimbrilepis will also improve the status of associated native vegetation including four Declared Rare Flora, 16 Priority flora and one Priority Ecological Community.

International obligations: This plan is fully consistent with the aims and recommendations of the Convention on Biological Diversity, ratified by Australia in June 1993, and will assist in implementing Australia’s responsibilities under that Convention. The subspecies is listed under Appendix II in the United Nations Environment Program World Conservation Monitoring Centre (UNEP-WCMC) Convention on International Trade in Endangered Species (CITES), however this plan does not affect Australia’s obligations under any other international agreements.

Indigenous Consultation: A search of the Department of Indigenous Affairs Aboriginal Heritage Sites Register has identified two sites of Aboriginal significance within Populations 3 and 7. These sites are listed as Measles Bridge Camp (#19933) a historical camp (open, no restrictions) and Nalya/Brookton (#5718) man-made structure (open, no restrictions).

Social and economic impacts: As Subpopulation 5b occurs on private property and Population 13 occurs on land where gravel is extracted, the protection of Verticordia fimbrilepis subsp. fimbrilepis may affect future development on these sites.

Affected interests: The protection of the subspecies may impact on maintenance operations conducted by local Shires, Western Power, Main Roads WA, Water Corporation and private landholders.

Evaluation of the Plan’s Performance: The DEC in conjunction with the Swan Region Threatened Flora and Communities Recovery Team (SRTFCRT) and Great Southern District Threatened Flora Recovery Team (GSDTFRT) will evaluate the performance of the plan. In addition to annual reporting on progress and evaluation against the criteria for success and failure, the plan will be reviewed following five years of implementation.

Existing Recovery Actions: The following recovery actions have been or are currently being implemented and have been considered in the preparation of this plan:

- All relevant stakeholders have been made aware of the existence of this subspecies and its locations.

- Declared Rare Flora (DRF) markers have been installed at Populations 1, 2, 4, 5a, 5b, 6 and 12.

- Dashboard stickers and posters describing the significance of DRF markers have been produced and distributed.

- In July 1998, 150 plants of Verticordia fimbrilepis subsp. fimbrilepis were planted into a proposed Timber Reserve near Beaufort, in accordance with an approved Translocation Proposal.

- Weed control trials were conducted by DEC Katanning District at Population 1 of Verticordia fimbrilepis subsp. fimbrilepis following an uncontrolled fire in 1990.

- In 1997, surveys were conducted for new populations of Verticordia fimbrilepis subsp. fimbrilepis by Robert Buehrig.

- In 2009, a new population of Verticordia fimbrilepis subsp. fimbrilepis was found south east of Armadale by volunteers Fred and Jean Hort.

- A research study on six Acacia and five Verticordia DRF taxa was undertaken by DEC Science Division.

- A total of 31,535 Verticordia fimbrilepis subsp. fimbrilepis seeds collected between 1996 and 2004 are stored in DEC’s Threatened Flora Seed Centre at –18C and 4C.

- Cutting material from Verticordia fimbrilepis subsp. fimbrilepis was collected from Population 3 in 1994, 1997, 1998, 1999 and 2000 and forwarded to BGPA for propagation.

- Staff from DEC’s Perth Hills and Great Southern Districts regularly monitor populations.

- The SRTFCRT and GSDTFRT are overseeing the implementation of this plan and will include information on progress in their annual report to DEC’s Corporate Executive and funding bodies.

Recovery Plan Objective: The objective of this recovery plan is to abate identified threats and maintain or enhance in situ populations to ensure the long-term preservation of the subspecies in the wild.

## Recovery Criteria

Criteria for success: The number of populations has increased and/or the number of mature individuals has increased by ten percent or more over the term of the plan.

Criteria for failure: The number of populations has decreased and/or the number of mature individuals has decreased by ten percent or more over the term of the plan.

Recovery actions

| - Coordinate recovery actions | - Implement feral pig control where necessary |
| --- | --- |
| - Stimulate germination | - Develop and implement a fire response strategy |
| - Install Declared Rare Flora (DRF) markers or replace where necessary | - Conduct further surveys |
| - Undertake weed control and follow up with additional control if required | - Ensure long-term protection of habitat |
| - Maintain disease hygiene | - Map habitat critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis |
| - Monitor populations | - Liaise with relevant land managers and Indigenous groups |
| - Rehabilitate habitat | - Promote awareness |
| - Collect seed and other material to preserve genetic diversity | - Review the recovery plan and assess the need for further recovery actions |
| - Implement rabbit control where necessary |  |

# 1.	BACKGROUND

### History

Verticordia fimbrilepis subsp. fimbrilepis was first collected by James Drummond in the 1840’s and for more than a century was known only from that collection. In November 1983 the subspecies was rediscovered near Woodanilling by Norm Stevens. Due to the low number of plants and threats associated with growing on narrow, degraded road reserves and small areas of remnant vegetation, a translocation was undertaken in 1998 by the then Conservation and Land Management (CALM) Katanning District.

In 2000, two large populations were discovered in State Forest near Wandering by DEC volunteer Fred Hort. The area had been burnt in 1998/99 and many thousands of seedlings were present. A resurvey in 2003 found that the populations occupied a much greater area than realised when surveyed in 2000. Over 20,000 plants of the subspecies were estimated to be present.

Currently Verticordia fimbrilepis subsp. fimbrilepis is known from 16 populations consisting of approximately 36,128 mature plants.

Description

Named from the Latin fimbria (fringe) and lepis (a scale), referring to its staminodes (George 2002), Verticordia fimbrilepis subsp. fimbrilepis is a small bushy shrub, 30–70 cm tall and 20–70 cm wide. It has pale pink or occasionally white flowers on short peduncles. Flowers are in small rounded groups at the tips of branches. The petals are markedly narrowed towards the tip with margins finely fringed. The staminodes are fringed across their broad apex, and a single hair in the centre is much longer than the others.

Verticordia fimbrilepis subsp. fimbrilepis is distinguished by its flowers which have persistent bracteoles, fringed staminodes, and a very short style. In particular it differs from subspecies australis in having flowers borne on shorter peduncles, petals with a broader lamina, a shorter finer fringe and staminodes bearing one long terminal hair (George 2002).

###### Distribution and habitat

Verticordia fimbrilepis subsp. fimbrilepis is widely distributed from southeast of Armadale to Brookton and Kojonup, with an extent of occurrence of 7,794 km2. The subspecies grows in low-lying shallow grey sand and yellowish-white sandy loam over gravel, sometimes with clay, in heath and scrubland and open wandoo woodland (George 2002). Associated species include Adenanthos cygnorum subsp. cygnorum, Banksia sphaerocarpa, B. grandis, B. armata, B. drummondii, B. nivea, Hakea incrassata, H. trifurcata, Isopogon teretifolius, Allocasuarina campestris, A. huegeliana, A. humilis, A. microstachya, Caustis dioica, Mesomelaena pseudostygia, Epilobium hirtigerum, Cassytha glabella, Acacia leptospermoides, A. saligna, Daviesia benthamii, D. cardiophylla, D. hakeoides, Gastrolobium spinosum, Jacksonia racemosa, Dodonaea pinifolia, Astroloma pallidum, Desmocladus fasciculatus, Callistemon phoeniceus, Calothamnus quadrifidus, Eucalyptus wandoo, Leptospermum erubescens, Melaleuca systena, Verticordia acerosa var. preissii, V. brachypoda, V. densiflora, V. eriocephala, V. habrantha, V. huegelii, V. multiflora, V. pennigera and V. picta.

## Table 1. Summary of population land vesting, purpose and manager

| Pop. No. & Location | DEC District | Shire | Vesting | Purpose | Manager |
| --- | --- | --- | --- | --- | --- |
| 1. West of Woodanilling | Great Southern | Woodanilling | Shire of Woodanilling | Road Reserve | Shire of Woodanilling |
| 2. West of Woodanilling | Great Southern | Woodanilling | Shire of Woodanilling | Road Reserve | Shire of Woodanilling |
| 3. South of Arthur River | Great Southern | West Arthur | Conservation Commission of WA | Conservation of Flora and Fauna | DEC |
| 4. SE of Aldersyde | Great Southern | Brookton | Shire of Brookton | Road Reserve | Shire of Brookton |
| 5a. NE of Kojonup | Great Southern | Kojonup | Shire of Kojonup | Road Reserve | Shire of Kojonup |
| 5b. NE of Kojonup | Great Southern | Kojonup | Freehold | Private Property | Landowners |
| 6. East of Narrogin | Great Southern | Narrogin | Shire of Narrogin | Road Reserve | Shire of Narrogin |
| 7a. SE of Aldersyde | Great Southern | Pingelly | Shire of Pingelly | Road Reserve | Shire of Pingelly |
| 7b. SE of Aldersyde | Great Southern | Pingelly | Conservation Commission of WA | Conservation of Flora and Fauna | DEC |
| 8a. Aldersyde | Great Southern | Brookton | Shire of Brookton | Road Reserve | Shire of Brookton |
| 8b. West of Aldersyde | Great Southern | Brookton | Shire of Brookton | Road Reserve | Shire of Brookton |
| 8c. West of Aldersyde | Great Southern | Brookton | Shire of Brookton | Reserve (Parkland & Recreation) | Shire of Brookton |
| 8d. West of Aldersyde | Great Southern | Brookton | Shire of Brookton | Reserve (Golf) | Shire of Brookton |
| 8e. West of Aldersyde | Great Southern | Brookton | Shire of Brookton | Reserve (Golf) | Shire of Brookton |
| 9. West of Brookton | Perth Hills | Beverley | Minister for Water Resources | Water Reserve | Department of Water |
| 10. NE of North Bannister | Perth Hills | Wandering | Land and Forests Commission | State Forest | DEC |
| 11. NE of North Bannister | Perth Hills | Wandering | Land and Forests Commission | State Forest | DEC |
| 12. West of Woodanilling | Great Southern | Woodanilling | Shire of Woodanilling | Road Reserve | Shire of Woodanilling |
| 13. East of Aldersyde | Great Southern | Brookton | Shire of Brookton | Reserve (gravel pit) | Shire of Brookton |
| 14a. South of Pingelly | Great Southern | Cuballing | Conservation Commission of WA | Conservation of Flora and Fauna | DEC |
| 14b. South of Pingelly | Great Southern | Cuballing | Conservation Commission of WA | Conservation of Flora and Fauna | DEC |
| 14c. South of Pingelly | Great Southern | Cuballing | Conservation Commission of WA | Conservation of Flora and Fauna | DEC |
| 15. North of Kojonup | Great Southern | Woodanilling | MRWA | Road Reserve | MRWA |
| 16. SE of Armadale | Perth Hills | Armadale | Land and Forests Commission | State Forest | DEC |

Note: Populations in bold text are considered to be important populations, MRWA = Main Roads Western Australia.

Biology and ecology

Research conducted into the reproductive biology and ecology of Verticordia fimbrilepis subsp. fimbrilepis by Yates and Ladd (2005) found that insect visitors to the taxon included wasps, bees, flies, beetles and butterflies. The diversity of insect visitors to flowers, rates of pollination, and seed production were equal or greater for small populations on road reserves compared with the larger populations in conservation reserves.

Yates and Ladd (2005) also concluded that seeds of Verticordia fimbrilepis subsp. fimbrilepis remained dormant in the soil for at least 30 months. Germination of soil-stored seed was stimulated by the use of smoke. Adult plants were killed by fire but mass recruitment from soil-stored seed occurred in the first and second winters following. Seedling survival depended on water availability, nutrient levels and grazing pressure. Fire suppression may adversely affect the Verticordia as most populations are declining and cannot recover without the occurrence of fire. Small, fragmented populations however, are more affected by weeds which are also abundant after fire, thereby outweighing any positive effects of fire without intervention management.

Verticordia fimbrilepis subsp. fimbrilepis is considered susceptible to dieback caused by Phytophthora cinnamomi with 80% mortality observed after testing 20 individuals.

Threats

Verticordia fimbrilepis subsp. fimbrilepis was declared as Rare Flora under the Western Australian Wildlife Conservation Act 1950 on 25 September 1987 and is currently ranked Vulnerable in WA against IUCN (2001) criteria. The subspecies is listed under the Environment Protection and Biodiversity Conservation Act 1999 (EPBC Act 1999) as Endangered. The main threats to the subspecies are insecure land tenure, road maintenance activities, weed invasion, poor recruitment, inappropriate fire regimes, grazing, trampling, feral pigs, Phytophthora dieback, powerline maintenance, salinity, farming activities and gravel extraction.

- Insecure land tenure. The majority of populations are found on land tenure that is not consistent with conservation and is of poor and deteriorating quality.

- Road maintenance activities threaten Populations 1, 2, 4, 5, 6, 7, 8, 12, 13 and 15. Threats include grading, chemical spraying, construction of drainage channels and the mowing/maintenance of roadside vegetation. Several of these actions also encourage weed invasion.

- Habitat degradation by weed invasion is a threat to Populations 1, 2, 3, 4, 5, 6, 7, 8, 12 and 13. Weeds suppress early plant growth by competing for soil moisture, nutrients and light. They also increase the fire hazard due to the easy ignition of high fuel loads, which are produced annually by many grass weed species.

- Poor recruitment has been observed in all populations, possibly due to a reduction of fire or other factors that may influence reproduction.

- Inappropriate fire regimes may affect the viability of populations. As seeds of Verticordia fimbrilepis subsp. fimbrilepis germinate following fire, occasional fires are needed for reproduction, however, the soil seed bank would rapidly be depleted if fires recurred before regenerating or juvenile plants reached maturity. Fire may facilitate weed invasion and should be followed up with appropriate weed control.

- Grazing and trampling by stock (sheep) and rabbits (Oryctolagus cuniculus) are a threat to Populations 3, 4, 7, 8, 13 and 14. As well as directly grazing Verticordia fimbrilepis subsp. fimbrilepis, the animals impact on the habitat by potentially spreading dieback and also by digging, trampling and breaking foliage. An increased nutrient level in the soil from droppings is likely and may encourage weed invasion. Grazing would have an impact on the establishment of young plants of V. fimbrilepis subsp. fimbrilepis thereby limiting natural recruitment.

- Feral Pigs (Sus scrofa) have been recorded in Population 16. Feral Pigs can directly damage the subspecies and its habitat when digging in search of food. They can also introduce weed seeds and nutrients. Soil disturbance also encourages the establishment of weeds.

- Phytophthora dieback caused by Phytophthora cinnamomi, a pathogen that causes root rot resulting in susceptible plants dying of drought stress, is a threat to Verticordia fimbrilepis subsp. fimbrilepis. Although it is not known if the pathogen is prevalent in the area of populations, the subspecies is considered to be susceptible to the pathogen.

- Powerline maintenance is a potential threat to Populations 2 and 3. Disturbance during maintenance may encourage weed invasion and also directly damage plants. Western Power has been notified of the populations.

- Salinity is a potential threat to Population 3. The vegetation in the reserve where the subspecies occurs is being impacted by salinity with EM38 readings ranging from 52 to 92 (slightly saline). It is not known how Verticordia fimbrilepis subsp. fimbrilepis will respond to changes in soil salt levels.

- Farming activities including fence maintenance and spray drift are a threat to Populations 4 and 12. Part of Population 4 is located near a property gate and maintenance may damage the population. Herbicide and fertilizer applied on properties adjacent to Populations 4 and 12 have the potential to drift onto the road reserve.

- Gravel extraction is a threat to Population 13 as it occurs in an active gravel pit. The subspecies may be damaged or completely removed during this process, and the risk of increasing the spread of dieback disease through the area is increased. Gravel extraction is also a potential risk to Subpopulation 8c as the area is a possible future source of gravel for the Shire.

The intent of this plan is to provide actions that will deal with immediate threats to Verticordia fimbrilepis subsp. fimbrilepis. Although climate change may have a long-term effect on the subspecies, actions taken directly to prevent the impact of climate change are beyond the scope of this plan.

Table 2. Summary of population information and threats

| Pop. No. & Location | Land Status | Year / No. of plants |  | Current Condition | Threats |
| --- | --- | --- | --- | --- | --- |
| 1. West of Woodanilling | Shire Road Reserve | 1984 1987 1991 1996 1998 1999 | 53 17 13 11 4 [1] 6 [2] | Poor | Weeds, road maintenance |
| 2. West of Woodanilling | Shire Road Reserve | 1984 1987 1988 1991 1996 1997 1998 1999 | 20 7 10 0 0 0 0 0 | Population extinct | Road maintenance, weeds, powerline maintenance |
| 3. South of Arthur River | Nature Reserve | 1987 1991 1994 1996 1998 1999 2000 | 1 28 6 3 [2] 4 (1) 3 [1] 0 [4] | Poor | Powerline maintenance, salinity, weeds, grazing, trampling |
| 4. SE of Aldersyde | Shire Road Reserve | 1993 1995 1997 1998 2005 | 50 46 83 (7) 83 61 | Poor | Road maintenance, farming activities, grazing (rabbits), weeds |
| 5a. NE of Kojonup | Shire Road Reserve | 1992 1996 1999 | 2 2 0 | Poor | Road maintenance, weeds |
| 5b. NE of Kojonup | Private Property | 1999 2000 2001 | 95 100 25 | Healthy |  |
| 6. East of Narrogin | Shire Road Reserve | 1992 1995 1997 2003 | 17 13 1 0 | Poor | Road maintenance, weeds |
| 7a. SE of Aldersyde | Shire Road Reserve | 1995 1996 1998 | 100 (230) 330 796+ | Healthy | Road maintenance, weeds, grazing (rabbits) |
| 7b. SE of Aldersyde | Nature Reserve | 1995 1998 | 2 305+ | Healthy | Grazing (rabbits) |
| 8a. Aldersyde | Shire Road Reserve | 1995 1996 1998 2005 | 0 1 0 0 | Disturbed | Road maintenance, weeds, grazing (rabbits) |
| 8b. West of Aldersyde | Shire Road Reserve | 1997 1998 | 40 40 | Moderate | Road maintenance, weeds |
| 8c. West of Aldersyde | Shire Reserve (Parklands and Recreation) | 1995 1998 2006 | 23 27 2 [1] | Healthy | Weeds, grazing, gravel extraction |
| 8d. West of Aldersyde | Shire Reserve | 1995 1998 2005 | 17 10 12 [2] | Healthy | Weeds, grazing |
| 8e. West of Aldersyde | Shire Reserve | 1999 2005 | 43 30 | Healthy | Weeds, grazing |
| 9. West of Brookton | Water Reserve | 1970 | 0 | Population extinct | Phytophthora dieback |
| 10. NE of North Bannister | State Forest | 2000 2003 | 757 (100+) 10040 | Healthy |  |
| 11. NE of North Bannister | State Forest | 2000 2003 | 2000+ (2000+) 19120 | Healthy |  |
| 12. West of Woodanilling | Shire Road Reserve | 1999 2005 | 185 (6) 77 [5] | Moderate | Road maintenance, weeds, farming activities |
| 13. East of Aldersyde | Shire Reserve (Gravel pit) | 2005 | 0 |  | Road maintenance, weeds, grazing, gravel extraction |
| 14a. South of Pingelly | Nature Reserve | 2001 | 482 | Healthy | Phytophthora dieback |
| 14b. South of Pingelly | Nature Reserve | 2001 | 12 | Healthy | Phytophthora dieback |
| 14c. South of Pingelly | Nature Reserve | 2004 | 110+ (9) [1] | Healthy | Phytophthora dieback, grazing (rabbits) |
| 15. North of Kojonup | MRWA Road Reserve | 2003 | 10 | Moderate | Road maintenance |
| 16. SE of Armadale | State Forest | 2009 | 5000+ | Healthy | Feral pigs |

Note: * = total for both subpopulations, ( ) = number of seedlings, [ ] = number dead, MRWA = Main Roads Western Australia.

### Guide for decision-makers

Section 1 provides details of current and possible future threats. Actions for development and/or land clearing in the immediate vicinity of Verticordia fimbrilepis subsp. fimbrilepis may require assessment.

Actions that could result in any of the following may potentially result in a significant impact on the species:

- Damage or destruction of occupied or potential habitat

- Alteration of the local surface hydrology or drainage of occupied or potential habitat

- Reduction in population size of any population

- a major increase in disturbance in the vicinity of a population

Habitat critical to the survival of the species, and important populations

It is considered that the habitat for populations 4, 5, 7, 8, 10, 11, 12, 14 and 16 is critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis and that these populations are important populations. Habitat critical to the survival of V. fimbrilepis subsp. fimbrilepis includes the area of occupancy of these populations, areas of similar habitat surrounding these populations (these providing potential habitat for population expansion and for pollinators), additional occurrences of similar habitat that may contain undiscovered populations of the subspecies or be suitable for future translocations, and the local catchment of these populations for the surface and/or groundwater that maintains the habitat of the subspecies.

Benefits to other species or ecological communities

Recovery actions implemented to improve the quality or security of the habitat of Verticordia fimbrilepis subsp. fimbrilepis will also improve the status of other rare species and associated native vegetation. Four Declared Rare Flora (DRF) species and 15 Priority flora taxa occur within 500 m of V. fimbrilepis subsp. fimbrilepis. These taxa are listed in the table below:

Table 3. Conservation–listed flora species occurring within 500m of Verticordia fimbrilepis subsp. fimbrilepis

| Species name | Conservation Status (WA) | Conservation Status (EPBC Act 1999) |
| --- | --- | --- |
| Banksia ionthocarpa subsp. chrysophoenix | DRF (CR) | Endangered |
| Hemigenia ramosissima | DRF (CR) | Critically Endangered |
| Conostylis drummondii | DRF (EN) | Endangered |
| Tribonanthes purpurea | DRF (VU) | Vulnerable |
| Banksia dallanneyi subsp. agricola | Priority 2 | - |
| Calytrix sp. Jingaring | Priority 2 | - |
| Leucopogon cymbiformis | Priority 2 | - |
| Stylidium emarginatum subsp. exappendiculatum | Priority 2 | - |
| Trichocline sp.Treeton (B.J. Keighery & N. Gibson 564). | Priority 2 | - |
| Acacia anarthros | Priority 3 | - |
| Anigozanthos bicolor subsp. exstans | Priority 3 | - |
| Brachyloma mogin | Priority 3 | - |
| Goodenia trichophylla | Priority 3 | - |
| Grevillea manglesii subsp. dissectifolia | Priority 3 | - |
| Stylidium marradongense | Priority 3 | - |
| Stylidium pseudohirsutum | Priority 3 | - |
| Synaphea drummondii | Priority 3 | - |
| Anthotium junciforme | Priority 4 | - |
| Calothamnus brevifolius | Priority 4 | - |
| Verreauxia verreauxii | Priority 4 | - |

For a description of the Priority categories see Atkins (2009).

Verticordia fimbrilepis subsp. fimbrilepis at Subpopulation 5b occurs within one kilometre of a Priority Ecological Community (PEC). This PEC is described as Claypans with mid dense shrublands of Melaleuca lateritia over herbs.

Table 4: Threatened Ecological Communities that Verticordia fimbrilepis subsp. fimbrilepis occurs near

| Community Name | Conservation status (WA) | Conservation Status (EPBC Act 1999) |
| --- | --- | --- |
| Claypans with dense shrublands of Melaleuca lateritia over herbs | Priority 1 | - |

For a description of the PEC categories see DEC (2007)

International obligations

This plan is fully consistent with the aims and recommendations of the Convention on Biological Diversity, ratified by Australia in June 1993, and will assist in implementing Australia’s responsibilities under that Convention. The subspecies is listed under Appendix II in the United Nations Environment Program World Conservation Monitoring Centre (UNEP-WCMC) Convention on International Trade in Endangered Species (CITES), however this plan does not affect Australia’s obligations under any other international agreements.

Indigenous Consultation

A search of the Department of Indigenous Affairs Aboriginal Heritage Sites Register has identified two sites of Aboriginal significance in the areas of Populations 3 and 7. These sites are listed as Measles Bridge Camp (#19933) a historical camp (open, no restrictions) and Nalya/Brookton (#5718) man-made structure (open, no restrictions).

Input and involvement has been sought through the South West Aboriginal Land and Sea Council (SWALSC) and Department of Indigenous Affairs to determine if there are any issues or interests. As this is not expected to be completed before adoption of the Recovery plan, further consultation has been included as a recovery action to ensure there has been Indigenous engagement in relation to the recovery actions proposed in this plan.

# Social and economic impacts

Subpopulation 5b occurs on private property; and Population 13 occurs on land where gravel is extracted and the protection of Verticordia fimbrilepis subsp. fimbrilepis may potentially affect development on these sites. Two sites of Aboriginal significance also occur in the areas of Populations 3 and 7 and recovery actions may potentially impact on Indigenous interests.

# Affected interests

Affected interests are relevant Indigenous groups, local Shires, Western Power, Main Roads WA, Department of Water and private landholders.

# Evaluation of the Plan’s Performance

The DEC in conjunction with the Swan Region Threatened Flora and Communities Recovery Team (SRTFCRT) and Great Southern Region Threatened Flora Recovery Team (GSRTFRT) will evaluate the performance of this plan. In addition to annual reporting on progress and evaluation against the criteria for success and failure, the plan will be reviewed following four years of implementation.

2.	RECOVERY OBJECTIVE AND CRITERIA

#### Objective

The objective of this Recovery Plan is to abate identified threats and maintain or enhance in situ populations to ensure the long-term preservation of the subspecies in the wild.

Criteria for success: The number of populations has increased and/or the number of mature individuals has increased by ten percent or more over the term of the plan.

Criteria for failure: The number of populations has decreased and/or the number of mature individuals has decreased by ten percent or more over the term of the plan.

#### 3.	RECOVERY ACTIONS

#### Existing recovery actions

Relevant stakeholders have been made aware of the existence of this subspecies and its locations. These notifications detail the current status of the species as Declared Rare Flora (DRF) and the associated legal obligations in regards to their protection.

Declared Rare Flora (DRF) markers have been installed at Populations 1, 2, 4, 6 and 12 and Subpopulations 5a and 5b. These serve to alert people working in the vicinity to the presence of the DRF and the need to avoid work that may damage plants or their habitat. Dashboard stickers and posters describing the significance of DRF markers have been produced and distributed.

In July 1998, 150 plants of Verticordia fimbrilepis subsp. fimbrilepis were translocated into a proposed Timber Reserve near Beaufort (Bone and Graham 1998). All plants were grown from cuttings taken from five plants in Population 3 and grown by the Botanic Gardens and Parks Authority (BGPA). The translocation was conducted on an experimental basis and has provided information about effective techniques for future translocations. Three treatments were tested: water, mulch and control (no watering or mulching). The number of surviving plants, height, crown width, reproductive state, number of inflorescences and follicles, and general health are being monitored. By March 1999, 56 of 150 introduced plants (37.3%) were dead. The least number of deaths (26%) were in watered plants and the most (44%) were in mulched plants. In March 2004, only five plants were still alive. Native grass had re-established at the site along with wild oats and veldt grass.

Weed control trials were conducted by DEC Katanning District at Population 1 following an uncontrolled fire in 1990. The population, located on a road reserve, was heavily infested with Veldt grass (Ehrharta longiflora) and the grass-selective herbicide, Fusilade®, was applied twice per year from 1993 to 1996. Initially, a smaller area of 200m2 was sprayed covering eight Verticordia plants. Then in 1994, the trial was expanded to include the whole population. During the three years of the trial, no detrimental effects were noted on any Verticordia plants. Although a reduction in grass mass was observed other bulbous and broadleaf weeds, which Fusilade® did not control, replaced them. Also Guildford grass (Romulea rosea) became abundant.

In 1997, Robert Buehrig conducted surveys for new populations of Verticordia fimbrilepis subsp. fimbrilepis. Over 40 waypoints were visited from Aldersyde southward to Woodanilling but no new populations were found (Buehrig 1997).

In 2009, a new population of Verticordia fimbrilepis subsp. fimbrilepis was found south east of Armadale by Fred and Jean Hort.

Some 31,535 Verticordia fimbrilepis subsp. fimbrilepis seeds collected between 1996 and 2004 are stored in DEC’s Threatened Flora Seed Centre at –18C and 4C (Table 5). The TFSC test the viability of the seed and the initial germination rate was found to range from 29 to 92%, averaging 53% (A. Cochrane unpublished data).

Table 5: DEC’s Threatened Flora Seed Centre collections for Verticordia fimbrilepis subsp. fimbrilepis

| Date | Population No. | No. seeds | Germination (%) |
| --- | --- | --- | --- |
| 24 January 1996 | 6 | 670 | 38 |
| 24 January 1996 | 4 | 2988 | 92 |
| 24 January 1996 | 7 | 5242 | 86 |
| 20 February 1996 | 4 | 1945 | 48 |
| 20 February 1996 | 7 | 2437 | 39 |
| 20 February 1996 | 8 | 723 | 64 |
| 2 March 1997 | 7 | 3462 | 77 |
| 2 March 1997 | 4 | 1228 | 62 |
| 2 March 1997 | 8 | 227 | 30 |
| 20 January 1998 | 4 | 946 | 29 |
| 21 January 1998, 3 February 1998, 2 February 1998 | 1 | 228 | 35 |
| 4 February 1998 | 7 | 5255 | 83 |
| 4 February 1998 | 8 | 405 | 38 |
| 9 February 2000 | 5 | 488 | 31 |
| 11 February 2000 | 10 | 668 | 38 |
| 12 February 2004 | 14 | 4623 | Test not complete |

A further collection of approximately 9.6 g of Verticordia fimbrilepis subsp. fimbrilepis seed from 20 plants at Subpopulation 7b was made in January 2000 by DEC’s Colin Yates. The seed was forwarded to the Botanic Gardens and Parks Authority (BGPA) for storage.

Cutting material from Population 3 was collected in 1994, 1997, 1998, 1999 and 2000 and forwarded to the BGPA at Kings Park for propagation. Of the 3,061 propagules (eight from graftings; 3,053 from cuttings), 702 struck, with an average propagation rate of approximately 25%. The majority of the material grown between 1999 and 2000 was used for a translocation with the remainder since dying. The only living specimens currently at Kings Park are two plants, approximately 12 months old, which were germinated by the TFSC from seed collected at Population 14 on February 2004.

Staff from DEC’s Perth Hills and Great Southern Districts regularly monitor populations.

The SRTFCRT and GSDTFRT are overseeing the implementation of this recovery plan and will include information on progress in their annual report to DEC’s Corporate Executive and funding bodies.

#### RECOVERY ACTIONS

Where recovery actions occur on lands other than those managed by DEC, permission has been or will be sought from appropriate owners/land managers prior to recovery actions being undertaken. The following recovery actions are generally in order of descending priority, influenced by their timing over the life of the plan. However this should not constrain addressing any of the actions if funding is available and other opportunities arise.

#### 1.	Coordinate recovery actions

The SRTFCRT and GSDTFRT will continue to oversee the implementation of recovery actions for Verticordia fimbrilepis subsp. fimbrilepis and will include information on progress in their annual report to DEC's Corporate Executive and funding bodies.

Action:	Coordinate recovery actions

Responsibility:	DEC (Swan Region and Great Southern District) through the SRTFCRT and GSDTFRT

Cost:		$6,000 per year

#### 2.	Stimulate germination

- Verticordia fimbrilepis subsp. fimbrilepis appears to germinate well following smoke water treatment or fire. Further treatments will be undertaken at senescing populations. Records will need to be maintained for future research. Any disturbance trials will need to be undertaken in conjunction with weed control.

Action:	Stimulate germination

Responsibility: 	DEC (Science Division, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$7,000 in years 1 and 3, $2,000 in years 2, 4 and 5

#### 3.	Install Declared Rare Flora (DRF) markers or replace where necessary

DRF markers are required at Population 15 and need to be replaced at Population 4.

Action:	Install DRF markers or replace where necessary

Responsibility:	DEC (Great Southern District) through the GSDTFRT

Cost:		$3,000 in year 1

#### 4.	Undertake weed control and follow up with additional control if required

Weeds are a major threat to most populations and control is required. The following tasks will be undertaken:

- Determine which weeds are present and map them.

- Select appropriate technique; herbicide, mowing or hand weeding.

- Control invasive weeds by hand removal and/or spot spraying around the Verticordia fimbrilepis subsp. fimbrilepis plants when weeds first emerge.

- Revegetation with site-specific species is required (in Autumn) to maintain low weed levels.

- Monitor the success of the treatment on weed death, and the tolerance of Verticordia fimbrilepis subsp. fimbrilepis and associated native plant species to the treatment.

- Report on the method and success of the threatment, and effect on Verticordia fimbrilepis subsp. fimbrilepis plants and associated species.

Action:	Undertake weed control and follow up with additional control if required

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$6,000 per year, as required

5.	Maintain disease hygiene

Verticordia fimbrilepis subsp. fimbrilepis is susceptible to dieback caused by Phytophthora cinnamomi. Dieback hygiene (outlined in CALM 2003 (now DEC)) will be followed for activities such as installation and maintenance of firebreaks and when walking into populations in wet soil conditions. Purpose built signs advising of the dieback risk and high conservation values of the sites will be installed where required.

Action:	Maintain disease hygiene

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$2,000 per year

#### 6.	Monitor populations

Monitoring of factors such as weed invasion, habitat degradation, hydrology (including salinity), population stability (expansion or decline), pollinator activity, seed production, recruitment, and longevity is essential. The populations will be inspected and an accurate location recorded.

Action:	Monitor populations

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$10,000 per year

7.	Rehabilitate habitat

Once gravel extraction has finished at the site, disturbed areas in the habitat containing Population 13 should be deep ripped and allowed to regenerate naturally.

Action:	Rehabilitate habitat

Responsibility:	DEC (Great Southern District) through the GSDTFRT

Cost:		$5,000 in first year

#### 8.	Collect seed and other material to preserve genetic diversity

Although a large number of seeds have been collected, the subspecies is not well represented in the seed store. The germination rate for most of the seed collected is relatively low so the actual number of germinants that can be produced is also quite low. Populations 10, 11 and 16 will be the priority for seed collection as they account for a large percentage of known plants.

Action:	Collect seed and other material to preserve genetic diversity

Responsibility:	DEC (Perth Hills and Great Southern Districts, TFSC), BGPA through the SRTFCRT and GSDTFRT

Cost:		$5,000 per year

#### 9.	Implement rabbit control where necessary

The level of threat posed by rabbits in Populations 4, 7, 8, 13 and 14 appears to vary from year to year. When monitoring ascertains the threat is high, control measures may be required. Control should be undertaken in summer when less green feed is available as an alternative food source.

Action:	Implement rabbit control where necessary

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT; relevant land managers

#### Cost:	$7,000 in years 1, 3 and 5

10.	Implement feral pig control where necessary

Feral pigs can damage threatened flora and its habitat when digging in search of food. Pigs can also introduce weed seeds and nutrients and the soil disturbance encourages establishment of weeds. Feral pig activity has been recorded at Population 16 and control may be necessary.

Action:	Implement feral pig control where necessary

Responsibility:	DEC (Perth Hills District) through the SRTFCRT

Cost:	$5,000 per year

#### 11.	Develop and implement a fire response strategy

Fire will be prevented from occurring in the habitat of populations, except where it is being used experimentally as a recovery tool. A fire response strategy will be developed that recommends fire frequency, intensity, season, and control measures.

Action:	Develop and implement a fire response strategy

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$10,000 in first year and $2,000 in subsequent years

#### 12.	Conduct further surveys

It is recommended that areas of potential habitat be surveyed for the presence of Verticordia fimbrilepis subsp. fimbrilepis during its flowering period between July and December.

All surveyed areas will be recorded and the presence or absence of the subspecies documented to increase survey efficiency and reduce unnecessary duplicate surveys. Where possible, volunteers from the local community, Landcare groups, wildflower societies and naturalists clubs will be encouraged to be involved.

Action:	Conduct further surveys

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$5,000 in years 1, 3 and 5

### 13.	Achieve long-term protection of habitat

DEC will investigate the possibility of land containing populations of Verticordia fimbrilepis subsp. fimbrilepis being declared as reserves.

Action:	Achieve long-term protection of habitat

Responsibility:	DEC (Perth Hills and Great Southern Districts, Land Unit); Department of Planning (DoP); Department of Mines and Petroleum (DMP), through the SRTFCRT and GSDTFRT

Cost:		$3,000 per year

#### 14.	Map habitat critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis

Although habitat critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis is alluded to in Section 1, it has not yet been mapped. If additional populations are located, then habitat critical to their survival will also be determined and mapped.

Action:	Map habitat critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis

Responsibility:	DEC (SCB, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:	$6,000 in year 2

15.	Liaise with relevant land managers and Indigenous groups

Staff from DEC’s Perth Hills and Great Southern Districts will liaise with relevant land managers to ensure that populations of Verticordia fimbrilepis subsp. fimbrilepis are not accidentaly damaged or destroyed. Indigenous consultation will also take place to determine if there are any issues or interests in areas that are habitat for V. fimbrilepis subsp. fimbrilepis.

Action:	Liaise with relevant land managers and Indigenous groups

Responsibility:	DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$2,000 per year

#### 16.	Promote awareness

The importance of biodiversity conservation and the protection of Verticordia fimbrilepis subsp. fimbrilepis will be promoted to the public. This will be achieved through an information campaign using local print and electronic media and by setting up poster displays. An information sheet that includes a description of the plant, its habitat type, threats and management actions, and photos will be produced. Formal links with local naturalist groups and interested individuals will also be encouraged.

Action:	Promote awareness

Responsibility:	DEC (Perth Hills and Great Southern Districts, SCB, Strategic Development and Corporate Affairs Division) through the SRTFCRT and GSDTFRT

## Cost:	$4,000 in year 1 and $2,000 in years 2-5

#### 17.	Review the recovery plan and assess the need for further recovery actions

If Verticordia fimbrilepis subsp. fimbrilepis is still listed as Threatened in WA under IUCN (2001) at the end of the five-year term (WA) of this recovery plan, the need for further recovery actions, or a review will be undertaken and a revised plan prepared if necessary.

Action:	Review the plan and assess the need for further recovery actions

Responsibility:	DEC (SCB, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT

Cost:		$3,000 in year 5

Total DEC:	$172,500

Total Other:	$13,000

Total External Funding:	$112,500

Total Costs: 	$298,000

Table 6. Summary of Recovery Actions

| Recovery Action | Priority | Responsibility | Completion Date |
| --- | --- | --- | --- |
| Coordinate recovery actions | High | DEC (Swan Region and Great Southern District) through the SRTFCRT and GSDTFRT | Ongoing |
| Stimulate germination | High | DEC (Science Division, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | 2015 |
| Install DRF markers or replace where necessary | High | DEC (Great Southern District) through the GSDTFRT | 2011 |
| Undertake weed control and follow up with additional control if required | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Ongoing |
| Maintain disease hygiene | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Ongoing |
| Monitor populations | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Ongoing |
| Rehabilitate habitat | High | DEC (Great Southern District) through the GSDTFRT | 2011 |
| Collect seed and other material to preserve genetic diversity | High | DEC (Perth Hills and Great Southern Districts, TFSC), BGPA through the SRTFCRT and GSDTFRT | 2015 |
| Implement rabbit control where necessary | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT; relevant land managers | Ongoing |
| Implement feral pig control where necessary | High | DEC (Perth Hills District) through the SRTFCRT | Ongoing |
| Develop and implement a fire management strategy | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Developed by 2011 with implementation ongoing |
| Conduct further surveys | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Ongoing |
| Achieve long-term protection of habitat | High | DEC (Perth Hills and Great Southern Districts, Land Unit); Department of Planning (DoP); Department of Mines and Petroleum (DMP), through the SRTFCRT and GSDTFRT | Ongoing |
| Map habitat critical to the survival of Eremophila glabra subsp. chlorella | High | DEC (SCB, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | 2012 |
| Liaise with relevant land managers and Indigenous groups | High | DEC (Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | Ongoing |
| Promote awareness | Medium | DEC (Perth Hills and Great Southern Districts, SCB, Strategic Development and Corporate Affairs Division) through the SRTFCRT and GSDTFRT | Ongoing |
| Review the plan and assess the need for further recovery actions | Medium | DEC (SCB, Perth Hills and Great Southern Districts) through the SRTFCRT and GSDTFRT | 2015 |

#### 4.	TERM OF PLAN

Western Australia

This IRP will operate from December 2010 to November 2015 but will remain in force until withdrawn or replaced. If the taxon is still ranked Vulnerable (IUCN) by the WA Government after five years, the need for further recovery actions and an update of the IRP will be assessed.

Commonwealth

In accordance with the provisions of the Commonwealth Environment Protection and Biodiversity Conservation Act 1999 (EPBC Act) once adopted, this recovery plan will remain in force until revoked.

The recovery plan must be reviewed at intervals of not longer than 5 years.

#### 5.	references

Atkins, K. (2009) Declared Rare and Priority Flora List for Western Australia. Department of Environment and Conservation, Perth, Western Australia.

Bone, B. and Graham, M. (1998) Translocation Proposal: Shy Featherflower, Verticordia fimbrilepis subsp. fimbrilepis. Department of Conservation and Land Management, Katanning.

Brown, A., Thomson-Dans, C. and Marchant, N. (Eds). (1998) Western Australia’s Threatened Flora. Department of Conservation and Land Management, Western Australia.

Buehrig, R.M. (1997) Verticordia fimbrilepis subsp. fimbrilepis Report. Department of Conservation and Land Management, Wanneroo.

Commonwealth Government of Australia (1999) Environment Protection and Biodiversity Conservation ACT 1999. Government Printer, Canberra.

Department of Conservation and Land Management (1992) Policy Statement No. 44 Wildlife Management Programs. Department of Conservation and Land Management, Western Australia.

Department of Conservation and Land Management (1994) Policy Statement No. 50 Setting Priorities for the Conservation of Western Australia’s Threatened Flora and Fauna. Department of Conservation and Land Management, Western Australia.

Department of Conservation and Land Management (2003) Phytophthora cinnamomi and disease caused by it Volume 1 – Management Guidelines. Department of Conservation and Land Management (now DEC), Perth, Western Australia.

Department of Environment and Conservation (2007) Definitions, categories and criteria for Threatened and Priority Ecological Communities. Department of Environment and Conservation, Western Australia. http://www.dec.wa.gov.au/management-and-protection/threatened-species/wa-s-threatened-ecological-communities.html.

George, A.S. (1991) New taxa, combinations and typifications in Verticordia (Myrtaceae: Chamelaucieae). Nuytsia 7 (3): 231–394.

George, A.S. (2002) Verticordia: the turner of hearts. University of Western Australia Press, Crawley.

Mitchell, M.(1997) Summary of weed control trials in a Declared Rare Flora population; Katanning District. Unpublished Report, Department of Conservation and Land Management, Katanning.

Western Australian Herbarium (1998−) FloraBase − The Western Australian Flora. Department of Environment and Conservation. http://florabase.dec.wa.gov.au/.

World Conservation Union (2001) IUCN Red List Categories: Version 3.1. Prepared by the IUCN Species Survival Commission. IUCN, Gland, Switzerland and Cambridge, UK.

Yates, C.J. and Ladd, P.G. (2005) Relative importance of reproductive biology and establishment ecology for persistence of a rare shrub in a fragmented landscape. Conservation Biology 19(1): 239-249.

### 6.	Taxonomic description

### Verticordia fimbrilepis subsp. fimbrilepis

George, A.S. (1991) New taxa, combinations and typifications in Verticordia (Myrtaceae: Chamelaucieae). Nuytsia 7 (3): 231–394.

Peduncles 2–4 mm long. Petal lamina 1.3–1.5 mm wide, fimbriate. Staminodes fimbriate across broad apex, one cilium much longer than the others.

Recovery Plan for Shy Feather Flower Verticordia fimbrilepis subsp. fimbrilepis

SUMMARY OF RECOVERY ACTIONS AND INDICATIVE COSTS

|  | Year 1 |  |  | Year 2 |  |  | Year 3 |  |  | Year 4 |  |  | Year 5 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Recovery Action | DEC | Other | Ext. | DEC | Other | Ext. | DEC | Other | Ext. | DEC | Other | Ext. | DEC | Other | Ext. |
| Coordinate recovery actions | 3000 | 1000 | 2000 | 3000 | 1000 | 2000 | 3000 | 1000 | 2000 | 3000 | 1000 | 2000 | 3000 | 1000 | 2000 |
| Stimulate germination | 5000 |  | 2000 | 1000 |  | 1000 | 5000 |  | 2000 | 1000 |  | 1000 | 1000 |  | 1000 |
| Install DRF markers or replace where necessary | 1500 |  | 1500 |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake weed control and follow up with additional control if required | 3000 |  | 3000 | 3000 |  | 3000 | 3000 |  | 3000 | 3000 |  | 3000 | 3000 |  | 3000 |
| Maintain disease hygiene | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 |
| Monitor populations | 6000 |  | 4000 | 6000 |  | 4000 | 6000 |  | 4000 | 6000 |  | 4000 | 6000 |  | 4000 |
| Rehabilitate habitat | 5000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect seed and other material to preserve genetic diversity | 2000 | 1000 | 2000 | 2000 | 1000 | 2000 | 2000 | 1000 | 2000 | 2000 | 1000 | 2000 | 2000 | 1000 | 2000 |
| Implement rabbit control where necessary | 3500 |  | 3500 |  |  |  | 3500 |  | 3500 |  |  |  | 3500 |  | 3500 |
| Implement feral pig control where necessary | 3000 |  | 2000 | 3000 |  | 2000 | 3000 |  | 2000 | 3000 |  | 2000 | 3000 |  | 2000 |
| Develop and implement a fire response strategy | 6000 |  | 4000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 |
| Conduct further surveys | 3000 | 1000 | 1000 |  |  |  | 3000 | 1000 | 1000 |  |  |  | 3000 | 1000 | 1000 |
| Achieve long-term protection of habitat | 3000 |  |  | 3000 |  |  | 3000 |  |  | 3000 |  |  | 3000 |  |  |
| Map habitat critical to the survival of Verticordia fimbrilepis subsp. fimbrilepis |  |  |  | 2000 |  | 4000 |  |  |  |  |  |  |  |  |  |
| ##### Liaise with relevant land managers and Indigenous groups | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 | 1000 |  | 1000 |
| ##### Promote awareness | 2000 |  | 2000 | 2000 |  |  | 2000 |  |  | 2000 |  |  | 2000 |  |  |
| ##### Review this IRP |  |  |  |  |  |  |  |  |  |  |  |  | 1500 |  | 1500 |
| ##### Total | 48000 | 3000 | 29000 | 28000 | 2000 | 21000 | 36500 | 3000 | 22500 | 26000 | 2000 | 17000 | 34000 | 3000 | 23000 |
| ## Yearly Total | 80,000 |  |  | 51,000 |  |  | 62,000 |  |  | 45,000 |  |  | 60,000 |  |  |

Ext. = External Funding (funding to be sought), Other = funds already contributed by NHT, volunteer input and BGPA in-kind contribution.

Total DEC:	$172,500

Total Other:	$13,000

Total External Funding:	$112,500

Total Costs: 	$298,000