## Progress on NPOA Sharks
|  |  |  | Primary focus |  |  | Secondary focus |  |  | Day to day management where applicable to the jurisdiction |  |  |  |  | ü – Action item has been implemented or is ongoing
In progress – Action item has commenced implementation Yet to initiate – Action item has not yet been initiated
Issue | Priority of issue | Action | Jurisdiction
|  |  | Commonweath |  |  |  | NSW | NT | QLD | SA | TAS | VIC | WA | WA | Reporting notes:
|  |  | AFMA | Agriculture / ABARES | Environment | GBRMPA
1 | High | 1. Review existing shark species identification guides (and any in development), implementing the best available identification guides in all relevant fisheries: |  |  |  |  | ü | ü | ü |  |  | ü | ü | Completed | Shark and Ray handling and identification guides have been developed by a number of jurisdictions to help commercial fishers return live sharks to the ocean and increase their survival. QLD: The shark logbooks and the species identification guide were reviewed as part of the hammerhead shark reform. On 1 January 2018 QLD implemented an expanded shark monitoring program and provided all net and line operators with an updated and waterproof copy of the shark and ray identification guide. Going forward, the suitability and applicability of the current catch and monitoring regime will be reviewed (when applicable) as part of a broader Monitoring and Research Plan. NT: A review of the management arrangements of the Offshore Net and Line Fishery (ONLF) has been finalised and drafting of amended Regulations for the fishery nearly completed. NT, in consultation with the Offshore Net and Line Advisory Group have developed a new management framework and associated harvest strategy. The management framework and associated harvest strategy have incorporated specific performance indicators and trigger points to help ensure that species specific reporting is accurate and the data collected though the fisheries logbook system is robust. VIC: Victoria reviews and updates annually the section of its recreational fishing guide that is related to sharks, skates and rays. The 2018 guide was published in December 2017. WA: Water-proof ID guide to WA Sharks and Shark-like rays distributed to all shark fishers in 2002.
- ensure guides are culturally appropriate, including the use of Indigenous species names where appropriate. | bar: NSW to QLD; VIC
|  | - ensure the best available guides have been provided to relevant user groups, including fishers, processors, compliance officers, observers and scientists. | [12 empty] | QLD: The shark logbooks and the species identification guide were reviewed as part of the hammerhead shark management reform. On 1 January 2018 QLD implemented an expanded shark monitoring program and provided all net and line operators with an updated and waterproof copy of the shark and ray identification guide. VIC: Victoria also has a recreational fishing smart phone app (iPhone/Android) which to date has been downloaded approximately 100 thousand times. Both the app and the hard copy contain hand drawn colour diagrams of recreationally important and protected shark, skate and ray species. WA: WA works with commercial fisheries on an ongoing basis to ensure the correct identification and reporting of shark and other species of fish. | bar: NSW to QLD; VIC
|  | 2. Monitor the effectiveness of identification guides. | [12 empty] | Jurisdictions have engaged in projects aiming to determine misreporting by observers and has also undertaken reviews of ID guides where required. WA: Fisheries' Compliance Officers conduct regular checks of recreational anglers to ensure they are aware of and can correctly identify different shark species and are complying with relevant legislation. QLD: This issue will continue to be addressed and monitored as part of the QLD Sustainable Fisheries Strategy 2017-2017. NT: Feedback on the effectiveness of guides is obtained from scientific staff carrying out at sea scientific monitoring and more formally through the annual Offshore Net and Line Fishery (ONLF) licensee committee general meeting. To help understand identification errors, the department participated in a project to determine misreporting by observers. | bar: NSW to QLD; WA to WA
|  | 3. Investigate the potential for additional tools for shark identification, such as morphological diagnostic tools or DNA identification kits. |  |  |  |  | NSW: ü; NT: ü; WA: ü; WA: Completed | NSW: Genetic analysis is being undertaken to assist identification of the species of hammerhead sharks caught in the NSW Shark Meshing Program. NSW is involved in several genetic research projects for sharks. NT: NT completed a research project to determine a morphological method that can be used in the field to separate between the cryptic species C. tilstoni and C. limbatus, key target species in the ONLF. NT is also participating the development of morphological techniques to identify shark species from fins alone. In partnership with AFMA, NT determined the elasmobranch species composition on board vessels operating in the MoU box shark fishery. NT is also participating in trialling and development of the Food and Agriculture Organization (FAO) "ISharkFin" program. WA: WA has developed a deoxyribonucleic acid (DNA) based identification process for sharks: the Fisheries Research and Development Corporation (FRDC) Project 2003/067 looked at the development of a DNA Database for Compliance and Management of West Australian sharks – completed in 2005.
2 | High | 4. Develop and implement national minimum data standards for all commercial, recreational, bather protection and Indigenous fishing operations that take sharks. |  | In progress | ü | [9 empty] | A number of jurisdictions have systems in place for the collection of data on recreational and commercial fishing of shark species. NT: NT has systems in place for the collection of data for recreational and commercial fishing. These processes (being statutory fishing returns for commercial fishers and a recreational fishing survey) are ongoing and information needs are reviewed regularly. The Department also pioneered a methods of collecting information about Indigenous take. Agriculture: The draft final report for ‘Shark Futures: A Report Card for Australia’s Shark and Rays’ is being finalised. Environment: The Department of the Environment and Energy (Environment) continues to work with Agriculture and other Commonwealth agencies and state and territory jurisdictions to help ensure these actions are undertaken. TAS: Tasmania does not have a dedicated commercial shark fishery so commercially caught sharks must be recorded in commercial catch, effort and disposal book. Recreational statewide surveys undertaken every five years with the 2012/13 report the latest publically available. This provides estimates of recreationally taken shark and ray species. The next recreational statewide survey started on 1 November 2017 and will be completed in mid-2019. WA: WA has systems in place for the collection of data for recreational and commercial fishing. These systems (being statutory fishing returns for commercial fishers and “iSurvey”: a comprehensive biennial state-wide survey of boat-based recreational fishing) are supported by best practice processes including independent external review and Marine Stewardship Council (MSC) assessment. | bar: NSW to NT; TAS; WA to WA
|  | 5. Obtain better understanding of illegal, unregulated and unreported shark catch. | ü | ü | [10 empty] | Australia has run an active campaign to deter illegal foreign fishing regionally. AFMA: AFMA responsible for the delivery of the fisheries element of Australia's border protection program through the enforcement of the provisions of the Fisheries Management Act 1991 against operators of unlicensed foreign fishing vessels. Numbers of apprehended foreign fishing vessels targeting shark continue to decline. Agriculture: Australia's Second National Plan of Action (NPOA) to Prevent, Deter and Eliminate Illegal, Unreported, and Unregulated (IUU) Fishing outlines the national, regional and international actions Australia will take to combat IUU fishing. NPOA refers to the release of Shark Plan 2 which is used to coordinate action Australia wide, including against IUU activities and shark conservation and management. Australia is working to strengthen fisheries governance and fisheries management in South East Asia. Australia continue to work with regional fisheries management organisations to improve the level and detail of reporting of shark catch, to provide better data and transparency in support of shark conservation. WA: WA is continually working to improve its understanding of all forms of shark catch. Effective compliance, fishery monitoring and assessments and other processes such as the MSC initiative and development of harvest strategies drives progress in this area. | bar: NSW; WA to WA
|  | 6. Develop and implement data verification systems with clear objectives and performance measures. | [12 empty] | A number of jurisdictions are working to introduce fine-scale catch information along with seeking to assess performance of shark fisheries against their respective management targets. NT: NT introduced fine scale statutory returns that document catch number and species and location for every shot. Returns are temporarily and spatially precise and provide fine-scale information to improve stock assessments and assess the performance of the shark fisheries against the respective management targets. WA: WA introduced fine-scale statutory returns (daily trip catch and effort) for the Temperate Demersal Gillnet and Demersal Longline Fishery (TDGDLF) in June 2006. The returns are temporally and spatially more precise and provide additional fine-scale information to improve stock assessments and assess the performance of the shark fisheries against the respective management targets. WA has implemented and uses catch and effort data validation protocols for the statutory returns. Statutory catch and effort data are maintained in Fisheries’ Catch and Effort statistics database. These are summarised and reported annually in the Department’s annual Status Reports of the Fisheries and Aquatic Resources (SRFAR). | bar: NSW to NT; WA to WA
3 | Medium – high | 7. Implement anti-finning measures for all Australian fisheries and assess their effectiveness across jurisdictions. Measures should be promoted for adoption regionally and internationally. |  | Completed | Completed |  | ü |  | ü | Completed |  |  | ü | ü | Shark finning at sea is illegal in all Commonwealth fisheries and a number of state fisheries. Shark catches in some fisheries are managed through ratios to ensure carcasses are not discarded at sea. Australia also promotes the adoption of anti-finning measures through regional fisheries management organisations and international bodies such as the Food and Agriculture Organisation’s Committee on Fisheries. SA: Legislation implemented that requires shark fins to be landed with carcasses (Regulation 18(5)(b) of the Fisheries Management (General) Regulations 2017). QLD: Finning or the taking of shark fins and discarding the body is already prohibited in QLD water. However, shark fins do not need to be naturally attached. Under the current system, commercial line fishers and net operators without an S-fishery symbol can remove the fins providing they are secured directly to the trunk. Net fishers operating with an S-fishery symbol do not need to secure the fins to the trunk and filleting is permitted providing the number of fin-sets can be easily matched to the number of trunks or fillets. The removal of fins is not permitted in the recreational fishing sector. The above measures have not changed since the last meeting of SRG and officers from the QLD Boating and Fisheries Patrol continue to monitor/ enforce this provision through their broader program. Agriculture: Shark finning illegal in all Commonwealth fisheries. It is an offence under fisheries management regulation 9Z0 to remove the caudal lobe, pectoral fin and dorsal fin before the shark is in possession of a fish receiver. Australia advocates for the implementation of anti-finning measures including banning the use of wire traces and the landing of sharks with their fins naturally attached to the carcass. Environment: Environment continues to work with Agriculture and other Commonwealth agencies to advocate at regional fisheries management organisations the implementation of anti-finning measures incl. the use of wire traces and landing sharks with fins attached to the carcass. WA: WA introduced anti-finning legislation in November 2006.
|  | 8. Assess the potential for more comprehensive trade data collection and analysis to improve shark conservation and management outcomes and implement a more comprehensive trade data collection system as appropriate. |  | Completed | ü |  | WA: Yet to initiate; WA: Yet to initiate | Customs and Border Protection Service officials attended the World Customs Organization (WCO) meeting in March 2014, to discuss changes to the Harmonized System (HS) coding system. Unfortunately, despite Australia’s support for the proposal to harmonise and adopt species specific shark codes the vote did not gain the two-thirds majority (23-for and 17-against) required for amendment. Australia's position is to promote this issue at the next meeting of the WCO meeting, likely to be in 2019. Environment: As a Party to CITES, Australia contributes to meetings concerning the implementation of the CITES listings, such as the species of sharks. This includes on issues of identification of shark product and traceability, and trade data collection. Agriculture: Agriculture examined the existing arrangements for recording and analysing shark and trade data - this encompassed the existing World Customs Organisation (WCO) HS coding system. Agriculture concluded that a change to the WCO HS would need to drive any changes to the domestic coding system. WA: This is not considered to be a high priority for WA noting fins are not exported and flesh supplies local and domestic markets.
4 | High | 9. Support the FRDC National Research, Development and Extension Framework 'Shark futures'. | [12 empty] | The FRDC considers all proposals received for funding of shark-related research against the framework developed by the shark futures project. VIC: Victoria supports the FRDC Research, Development and Extension framework where there is an identified benefit to the state. WA: WA supports the need for a coordinated approach to shark research through the FRDC Shark Futures program. | bar: SA; VIC to WA
|  | 10. Investigate opportunities for collaborative research initiatives to address the aims and objective of Shark-plan 2. |  |  |  | ü | [8 empty] | There are a number of shark-related projects funded under the National Environmental Science Programme (NESP) such as determining the population status of white sharks and hammerhead sharks, determining research priorities for Australia's shark species, and initiatives to mitigate risk of human-shark interactions. QLD: QLD provides support for shark and ray research through direct funding and in-kind contributions (i.e. QLD shark stock assessment, projects examining the life-history constraints, distributions and movement of the tiger shark and bull shark and gear evaluations through the QLD Shark control program). QLD in conjunction with the Commonwealth Scientific and Industrial Research Organisation (CSIRO) are in the process of finalising a FRDC project which will quantify elasmobranch bycatch survival rates in East Coast Trawl Fishery and assesses the risk posed to elasmobranchs by this fishery. NT: NT continues to identify opportunities to collaborate with other partners to address the aims and objectives of Shark Plan 2. SA: Two research projects were completed in 2018 including: “Movement, residency and habitat use of pelagic sharks in Spencer Gulf: resolving overlaps with marine industries and community activities”, and “Assessment of the South Australian Marine Scalefish Fishery in 2016”. WA: WA continues to identify opportunities to collaborate with other partners to address the aims and objectives of Shark-plan 2. The following collaborative projects have been completed: towards a National Strategy for Understanding Movements of Cross-Jurisdictional Species: aligning management needs with the goals of IMOS (led by CSIRO via IMOS); white shark initiatives including assessing the impact on fisheries management changes on the western white shark population; in 2018 WA commenced a FRDC funded project using remote camera approaches to assess and the monitor population status. | bar: NSW to SA; WA to WA
5 | High | 11. Maintain and/or improve stock assessments, risk assessments and status determination processes for target, bycatch and byproduct species. | ü |  |  | ü | [8 empty] | A number of jurisdictions with targeted-shark fisheries have moved to undertaking stock assessments for species. QLD: On 9 June 2017 QLD released the Queensland Sustainable Fisheries Strategy 2017-2027. A number of reform areas deal specifically with improving the level of information on key stocks and quantifying the level of risk posed to both target and non-target species. QLD has commenced work on a set of guidelines that will outline how ecological risk assessments will be undertaken for both target and non-target species. Outside of the Sustainable Fisheries Strategy, QLD continues to review the status of a number of shark species through the National SAFS and the QLD stock status assessment processes. NSW: NSW contributes to the Status of Australian Fish Stocks reviews of sharks and continues discussions about status determination processes with adjacent jurisdictions and the Commonwealth. NT: NT undertook major stock assessments for key shark species, C. sorrah, C. tilstoni and C. limbatus. A risk assessment has been carried out for all of the significant bycatch and by product species. ONLF scientific monitoring program continues to collect information that will inform assessments on all target, bycatch and byproduct species. SA: catch and effort trends for combined whaler shark are monitored and reported annually in the commercial Marine Scalefish Fishery (MSF). Framework of the MSF status report has been updated to report on annual catches of all shark species. ESD risk assessments are undertaken for all commercial and recreational fisheries as part of the development of fishery management plans. Data describing trends in shark, ray and skate catches in the MSF were summarised in the report by Steer et al. (2018). Assessment of the South Australian Marine Scalefish Fishery in 2018. AFMA: Harvest strategies are in place for shark species managed under quota in the Southern Eastern Scalefish and Shark Fishery. Gulper sharks (dogfish) are not managed under a combined quota and in February 2013 AFMA implemented a revised upper slope dogfish management strategy. The management strategy is due to be reviewed. A work to establish an alternative index of abundance of school shark using close kin mark recapture has now been completed and an updated stock assessment is being considered by the Shark Resource Assessment Group in late 2018. TAS: All commercial shark catch is recorded in the annual scalefish fishery assessment— noting the 2017/18 assessment is currently underway and will be available in early 2019. Tasmanian recreational fishing survey provides an estimate of recreational shark and ray captures for both kept and released. WA: WA undertakes stock assessments for key shark species and secondary target/byproduct species as set out by the Department's annual Status Reports of the Fisheries and Aquatic Resources (SRFAR). The 2017-18 SRFAR is in the final stages of completion and will be published and publicly available before the end of 2018. Department undertook an FRDC funded research project to examine the movements of the shark fisheries' four indicator sharks stocks. Results from this study are being used to reassess the status of these stocks. Further to this, Fisheries’ stock assessments, independent MSC pre-assessment of the northern and Temperate Demersal Gillnet and Demersal Longline Fisheries (TDGDLF) have been completed. In June 2018, WA implemented a compressive network of Australian Sea Lion (ASL) Gillnet Exclusion Zones to provide protection to ASL colonies. NSW: NSW DPIF contributes to the Status of Australian Fish Stocks reviews of sharks and continues discussions about status determination processes with adjacent jurisdictions and the Commonwealth. | bar: NSW to TAS; WA to WA
|  | 12. Assess the need for implementation of formal harvest strategies to manage shark catch. | ü |  |  | ü | ü | Completed | ü | ü |  | ü | In progress | In progress | QLD: The Queensland Sustainable Fisheries Strategy 2017-2027 identified 'Harvest Strategies' as one of the 10 major areas of reform which includes a number of key action items. QLD has already commenced work on these action items and on 5 October 2017 released the Queensland Harvest Strategy Policy and Guidelines for Implementing the QLD Harvest Strategy Policy. Outside the Sustainable Fisheries Strategy, QLD continues to address the harvesting of sharks through ancillary processes like threatened species assessments and Wildlife Trade Operation approvals under the EPBC Act. NT: A review of the management arrangements of the ONLF has been completed and the Management Plan is currently being implemented. A formal management frame work, incorporating formal harvest limits to manage shark catch has been approved by industry and community and is being drafted into legislation. SA: Combined bronze whaler and dusky (whaler sharks) are considered secondary species in the Marine Scalefish Fishery, and a broad harvest strategy has been developed in Management Plan for the South Australian commercial marine scalefish fishery. Shark catches are monitored and reported on an annual basis via the stock status report. Legislative requirement under the Fisheries Management Act 2007 that management plan, including harvest strategy within the management plan must be reviewed every 5 years. AFMA: Agriculture published the Commonwealth Harvest Strategy and Bycatch Policies. Harvest Strategies are in place for all shark species managed under quota in the SESSF. VIC: Victoria doesn't have a dedicated commercial shark fishery but authorised commercial fishers harvested an average of 39 tonnes of sharks, rays, elephant fish and other chondrichthyans annually between 2012 and 2017. Victoria does not currently have an estimate of recreational shark harvest although angler diary monitoring in selected Victorian estuaries indicates that catch as a percentage of total recreational catch is low. WA: In 2015, WA published its overarching Harvest Strategy Policy and has an agreed harvest strategy with the NT and QLD via the Northern Australian Fisheries Committee relating for northern shark species, namely black-tip and sandbar shark. A science review of the Northern Shark Fisheries has been completed and has been used to inform the Draft Northern Shark Discussion Paper. The Department will, as part of the Joint Authority Southern Demersal Gillnet and Demersal Longline Managed Fishery transitioning to sole WA management, develop a complementary harvest strategy, scheduled to be completed by 2020.
6 | Medium | Covered under Issue 5
7 | High | 13. Iterative/ongoing jurisdictional assessment of the adequacy of shark management including the implementation of harvest strategies and compliance, enforcement and education strategies to support sustainability objectives for sharks. | ü |  | ü | ü | [8 empty] | Harvest strategies in place for all Commonwealth shark species under quota, all other species assessed and managed under the Ecological Risk Management program. AFMA has in place a comprehensive intelligence driven, risk based targeted domestic compliance program. QLD: QLD boating and fisheries patrol undertake compliance risk assessments for all of Queensland's fisheries with the outputs being used to define compliance priorities including for sharks. Shark catch in the commercial and recreational sector is monitored via the QLD Boating and Fisheries Patrol. Educational programs including on-line guides and the distribution of shark ID booklets are an important part of managing shark bycatch. AFMA: Harvest Strategies are in place for all shark species managed under quota in the Southern Eastern Scalefish and Shark Fishery. AFMA provides formal reports on the implementation of the SESSF harvest strategy framework in the AFMA annual reports and Wildlife Trade Operation (WTO) strategic assessments. This includes the number of species/ stocks as being subject to overfishing or overfished. Environment: Environment continues to work with Agriculture to ensure relevant actions are undertaken. WA: WA has internal processes in place to review the adequacy of shark (and other fisheries) management including the implementation of harvest strategies and compliance, enforcement and education strategies to support sustainability objectives for sharks. As part of the transition of the Joint Authority Southern Demersal Gillnet and Demersal Longline Managed Fishery to sole WA management, the Department will be developing, with DoEE input, a complementary harvest strategy for shared shark and demersal scalefish stocks off WAs south coast. The department promotes community and stakeholder awareness of the management of, and rules relating to, sharks in Western Australia. Further, WA's MSC initiative has seen all of the State’s fisheries, including the TDGDLF, subject to independent third party assessment against MSC guidelines. The pre-assessment of the northern and temperate shark fisheries has been completed. NSW: The ‘large shark permit fishery’ component of the NSW Ocean Trap and Line Fishery, which harvests the majority of sharks in NSW, remains inactive. The NSW Government continues to implement its $16M Shark Management Strategy (launched in October 2015), the key objective of which is to increase protection for swimmers and surfers from shark interactions while minimising harm to sharks and other marine animals. The existing recreational fishing rules that apply to several Greynurse Shark aggregation sites in NSW (specifically a prohibition on all line fishing with animal based baits) were extended for another 5 years in September 2017. | bar: NSW; QLD; WA to WA
|  | 14. Explore mechanisms for greater collaboration between jurisdictions regarding research, assessment and management of shared stocks. | [12 empty] | This an ongoing action for jurisdictions who continue to engage with others regarding the management of shark fisheries and related matters. QLD: QLD continues to collaborate with adjacent jurisdictions including through species workshops. QLD involved with a number of regionally specific committees aimed at improving cooperation between adjacent jurisdictions including the Northern Australia Fisheries Committee which includes WA, NT, QLD and Cth agencies. These committees address a wide range of issues including targeted and non-targeted interactions with shark and ray species. NT: NT continues to engage with other jurisdictions regarding the management of shark fisheries. WA: WA engages with other jurisdictions regarding the management of the shark fisheries and related and will, where appropriate, explore opportunities to collaborate with those jurisdictions with respect to the management and research of shared stocks. Fisheries sought a review of the current science knowledge associated with Western Australia’s northern shark stocks. The completed review is assisting with consideration of future harvest and management strategies for Northern shark. The draft Paper was provided to NT and AFMA for review and preliminary comment. WA is currently updating and finalising the Paper for publishing as a Fisheries Occasional Publication in 2019. | bar: NT to QLD; WA to WA
8 | Medium | 15. Review the effectiveness of management measures for recreational and game fishing in achieving sustainability objectives for shark species and develop recommendations for future management approaches, should this be found to be necessary. | [12 empty] | A number of jurisdictions have undertaken reviews of management measures for recreational and game fishing, such as the appropriateness of boat limits and trigger limits. Research into post-release mortality or survival of shark species has also been prioritised. QLD: In 2009, QLD introduced significant restrictions on the take of shark and rays within the recreational fishing sector which included max size limits, in possession limits and no-take species. When and where applicable, these management arrangements will be reviewed to ensure that they cover ancillary decisions e.g. decisions relating to the listing of species under the EPBC Act. The management of sharks of QLD, when appropriate, will also be reviewed by the Fisheries Working Groups. NT: NT has released the results of the recreational fishing survey which will update and improve the information on shark harvest by the recreational fishing sector. Recreational fishing surveys are now be carried out annually. Recreational fishing bag limits have been modified limiting recreational fishers to three sharks in possession. TAS: The Tasmanian Recreational Fishing Survey 2012/13, provides insight into the trends in the recreational take and release of shark and ray species. The scalefish fishery management plan introduced new and or/extended no gillnetting areas; a reduction of hook numbers on recreational set lines and the prevention of the use of burley for any other purpose other than fishing. Reduced recreational catch limits for mako and blue shark were also implemented. WA: In addition to commercial fishing, WA monitors recreational catch and effort through surveys. Last survey confirmed that there is minor targeting of sharks by the recreational fishing sector and limited recreational shark game fishing in WA. VIC: In 2017, the VFA put in place rules to increase protection for skates, rays and guitarfish in response to community concern about disrespectful treatment by a small proportion of fishers. These rules have recently been continued through implementation of the Fisheries (Ray Protection) Notice 2018. | bar: NT to QLD; TAS to WA
|  | 16. Assess the findings of the review under action 16 and relevant recreational and Indigenous fishing surveys to: |  | Completed | [10 empty] | The Australian Government has recently released a report that provides a survey methodology framework to be used as a basis for developing a national recreational fishing survey which will begin in late 2018. States and territories continue to undertake recreational fishing surveys where appropriate. TAS: The annual IMAS hosted Resource Assessment Group (RAG) for scalefish and minor species meeting is usually held in November. This meeting provides the opportunity to put forward research related projects identifying gaps in knowledge, data collection and stock and effort related issues. A new Statewide Recreational Survey commenced on 1 November 2017 and this data will be available in 2019. Another specific project is assessing the Post Release Survival of Mako Shark. WA: WA continues to use a number of means to educate fishing sectors (including recreational and game fishing) in relation to sharks. Fisheries adopts a risk based approach to compliance and enforcement and directs resources towards these activities in relation to sharks as appropriate based on the risk rating. The last information on indigenous fishing occurred in 2000/01 as part of the national survey. Catches are likely to be relatively minor. | bar: TAS; WA to WA
- identify gaps in existing monitoring and data collection programs for recreational, charter and Indigenous fishing. | bar: TAS; WA to WA
- determine the nature and role of state and territory recreational fishing surveys. | bar: TAS; WA to WA
- determine the required frequency of future national surveys. | bar: TAS; WA to WA
- determine adequacy of reporting on recreational and Indigenous fishing issues at national level. | bar: TAS; WA to WA
- where necessary, update existing survey methodologies or introduce effective supplementary or alternative data collection mechanisms. | bar: TAS; WA to WA
- review and where necessary revise recreational and game fishing management arrangements to ensure impacts on sharks are sustainable. | bar: TAS; WA to WA
- where necessary, increase education and enforcement programs in recreational and gamefishing sectors. | bar: TAS; WA to WA
9 | Medium – low | 17. Improve understanding of the cryptic mortality of high risk sharks in commercial, recreational and Indigenous fisheries. | Yet to initiate |  |  | ü | [8 empty] | WA: WA works with various fishing sectors and fishers to gain a better understanding of any issues or gaps with respect to the fishing they undertake. These discussions are critical to gaining a better understanding of, and working out how to collect information on cryptic mortality. Trial of in-net and on deck cameras in the Pilbara Trawl Fishery was taken in 2013 with the goal of monitoring and detecting the reduction in megafauna bycatch including sharks and rays. Condition of all megafauna at release was recorded which will provide information on cryptic mortality. The MSC assessment process examines ecosystem impacts from fishing and may improve understanding of cryptic fishing mortality over time. | bar: TAS; WA to WA
|  | 18. Implement strategies to reduce cryptic mortality, noting the link with Theme 2 of Shark Futures which has a focus on minimising the environmental impacts of fisheries on sharks. | Yet to initiate |  |  | ü | NT: ü; QLD: Not commenced; WA: ü; WA: ü | While jurisdictions in the past have reduced the potential for cryptic mortality to sharks through the use of bycatch reduction devices, it is acknowledged there is still further work that could potentially be undertaken in this space. QLD: While this was initially identified as a primary focus, QLD now considers this to be one of the alternate shark-specific initiatives. NT: Strategies to reduce cryptic have been investigated. In the new management plan, performance measures have been implemented and increased levels of monitoring will determine if cryptic mortality is indeed occurring and if so, levels will be quantified.
|  | 19. Ensure cryptic mortality is accounted for in the setting of catch quotas (where information is available). | Yet to initiate |  |  |  | TAS: N/A; WA: ü; WA: ü | Where stock assessments for sharks are undertaken, jurisdictions aim to account for all sources of mortality. In some jurisdictions, major shark-target fisheries will include uncertainty in mortality rates which will implicitly include cryptic mortality. AFMA: AFMA estimates discards for species subject to total allowable catch limits in the SESSF. These discards are deducted from the recommended biological catch along with state catches to calculate the resulting catch limit. WA: All sources of mortality are considered in shark stocks assessments. As part of FRDC 2010/003, models for the major target fisheries will include uncertainty in mortality rates which will implicitly include cryptic mortality.
10 | Medium – low | 20. Investigate shark handling practices to identify any areas of concern. | [12 empty] | TAS: TAS is conducting a project to assess the Post Release Survival of Mako Sharks. WA: Commercial fishers in WA's TDGDLF have codes of conduct that relate to handling practices for shark species. These assist commercial fishers in returning bycatch and byproduct to the water alive and unharmed and ensure maximum quality of the retained product. Recreational fishers are advised via “Care for your catch” and other similar programs on the general handing of fish to maximise survival rates if returning to the water and to maximise table quality and encourage better use of fish resources if fish are being kept. | bar: TAS; WA to WA
|  | 21. Implement solutions as required, with consideration given to increased training and enforcement requirements. | [12 empty] | WA: WA maintains dialogue with the WA Fishing Industry Council & Recfishwest, the peak stakeholder bodies for commercial and recreational sectors, regarding fish handling practices and investigates specific matters if required. | bar: WA to WA
11 | Medium | 22. Assess the extent of Indigenous fishing for sharks and incorporate into overall management arrangements. Identify gaps in knowledge about Indigenous shark fishing and, where a need is identified, develop research proposals to address these gaps. | [12 empty] | NT: WA has undertaken a pilot project which has developed a model which can be used to collect information from indigenous communities about the levels of chondrichthyan catch. WA has a strong relationship with the network of marine rangers groups around the Territory and will continue to work collaboratively with these groups. Where possible WA will continue to work to identify knowledge gaps with concerns to indigenous shark fishing and develop research proposals to address those knowledge gaps. | bar: NT; WA to WA
|  | 23. Assess the impact of existing management measures for sharks on Indigenous subsistence fishing practices. |  |  |  |  | NT: Yet to initiate; WA: Yet to initiate | WA: The last information on indigenous fishing occurred in 2000/01 as part of the national survey. Catches are likely to be relatively minor.
12 | Medium – high | 24. Implement management responses for species (or species groups) already assessed as high risk. | ü |  |  | ü | ü | ü |  | ü (as needed) |  | ü | ü | ü | Across all jurisdictions a range of strategies are in place to manage high risk species. High-risk species are identified through ecological risk assessment processes, listing under national and state environmental legislation and listing through international conventions. NT: NT has implemented legislation that prevents the take of pristis sawfish and glyphis sharks. SA: No shark species identified as high risk. SA has commercial and recreational management controls in place to ensure that the harvest of sharks in SA waters is sustainable. Controls are periodically reviewed and changed where required. AFMA: ERM guide includes a timetable for undertaking ERAs and the development of Fishery Management Strategies (FMS), which draw all major management tools and strategies for a fishery into one document and also assist in streamlining reporting arrangements. The guide outlines a fisheries management framework and a major element of this is the development of a fishery management strategy for each fishery. VIC: Current level of shark and ray harvest not seen as a key threat to sustainability and VIC has placed commercial and recreational management controls to ensure that the harvest of sharks is sustainable. WA: WA has implemented management responses for shark (and byproduct and bycatch species in the TDGDLF) assessed as high risk incl. dusky, sandbar and whiskery shark stocks. Effort reductions implemented in the TDGDLF have been determined as appropriate to deliver sustainable harvest of the key target shark species and also acceptably low levels of byproduct, bycatch and protected species interactions. NSW: The strategies for threatened sharks in the Priorities Action Statement were formally adopted and are now available on NSW DPIF website. The existing recreational fishing rules that apply to several Greynurse Shark aggregation sites in NSW were extended for another 5 years in September 2017.
|  | 25. Undertake best practice risk assessments for shark species not already assessed. |  |  |  | ü | [8 empty] | QLD: The use, suitability and applicability of risk assessments are being reviewed by QLD DAF as part of the broader Queensland Sustainable Fisheries Strategy 2017-2027. The strategy included two actions items that relate specifically to the development of ERAs in QLD: Action 4.1 Publish a guideline on assessing the ecosystem impact of fishing activities including the process for prioritising and undertaking ERAs; Action 4.2 ERA to be undertaken for priority fisheries by the end of 2020, followed by the remaining fisheries. Action item 4.1 was completed with the release of the ERA Guidelines on 22 March 2018. QLD has made significant progress on action item 4.2 including the development of preliminary/ draft ERAs for fisheries that target and retain shark in larger quantities. NT: NT has undertaken a risk assessment process for species caught in the ONLF. SA: ESD risk assessments undertaken for all fisheries as part of the development of fishery management plans. WA: WA manages WA's shark stocks through the use of indicator species. Risk assessments have been completed for these indicator species. | bar: NSW to SA; WA to WA
|  | 26. Continue to refine risk assessment processes for target, bycatch and byproduct shark stocks, seeking to include all available data and to include consideration of cumulative impacts. Collection of data on species biology and human impacts will be foundational to the success of this action. |  |  |  | ü | [8 empty] | WA: WA's assessment processes will continue to be based on multiple years of detailed stock assessments and outcomes of formal ESD risk assessments. Current management setting is considered likely to deliver sustainable catches of target, byproduct and bycatch species. | bar: NSW; WA to WA
|  | 27. Evaluate the methodologies for risk assessment and assess the need for national risk assessment guidelines. |  | In progress |  | ü | NSW: Completed; WA: ü; WA: ü | Agriculture: All shark species taken in Commonwealth fisheries are subject to ecological risk assessment. Species considered to be at greater than low risk (medium or high) are considered under ecological risk management (ERM) processes. AFMA has implemented an ERM Guide for managers to assist in the consistent application of risk assessment processes across Commonwealth fisheries. ABARES, in collaboration with other international scientists, have recently applied the above risk assessment methodologies to shark species encountered in a number of high seas fisheries. WA: WA's risk assessments are conducted with best practice standards evidenced by the 2018 re-approval of the TDGDLF under Part 13 and Part 13a of EPBC Act. Notwithstanding the above, the risk assessments were reviewed as part of the MSC pre-assessment process and the Department also consistently applies the ERA framework and Weight of Evidence Approach.
|  | 28. Implement management measures for any subsequent high risk species. |  |  |  | ü | [8 empty] | WA: WA sought a review of current science knowledge associated with Western Australia's northern shark stocks. Review has been completed and is informing decisions and assisting in consideration of future harvest and management strategies. | bar: NSW; WA to WA
|  | 29. Identify important habitat and broader environmental and habitat requirements for shark species and appropriate protection and management of these areas. |  |  | ü | ü | [8 empty] | Environment: DoEE has been conducting several projects on habitat mapping and appropriate protection for sharks and rays under NESP including for hammerhead sharks, whitefin swellshark, grey skate, eastern angelshark, greeneye spurdog, sawfish and rivershark. Some specific shark research and monitoring projects currently being undertaken within Australian Marine Parks including for Galapagos sharks, grey nurse sharks, Great and Scalloped Hammerheads, Silvertip Reef Shark, Leopard Shark, Grey Reef Shark, White tipped Reef Shark and Tiger Shark. WA: WA manages fish resources in accordance with Ecosystem Based Fisheries Management principles. NSW: The NSW Shark Management Strategy has installed 21 VR4G listening stations in 2015-2018 and to date tagged 300 White Sharks. The program also plans to tag 100 Tiger Sharks and 100 Bull Sharks. This is providing new data to better understand the movements and distributions and habitats of those species to inform risk assessment and management options. | bar: NSW; WA to WA
13 | Medium – high | 30. For species designated as requiring recovery, implement recovery strategies. Recovery strategies should be monitored and revised as appropriate to ensure effectiveness. |  |  | ü | Yet to initiate | NSW: ü; SA: ü(as needed); WA: ü; WA: ü | Environment: Eleven shark species included in the EPBC Act. All except the conservation dependent species and the Whale Shark have active recovery plans. Since 15 March 2018, Scalloped Hammerhead has been listed as conservation dependent under the EPBC Act. Harrisson’s Dogfish and Southern Dogfish are also shark species listed as conservation dependent. In February 2018, CSIRO completed a study on White Shark population abundance and survival rates for both eastern and southern-western populations using novel genetic research and data analysis. CSIRO estimates put the eastern population between 470-1,030 adults and the southern-western population between 750-2,250. WA: WA has implemented management arrangements to provide for the recovery of relevant shark species and continues to conduct stock assessments for key shark species. SA: No species under SA jurisdiction have been identified as requiring recovery. Where needed PIRSA will develop harvest strategies aimed at rebuilding stocks.
14 | Medium – high | 31. Initiate action (as required) to ensure effective bycatch reduction methods for sharks have been developed for all fisheries in which shark are caught as bycatch, giving priority to species identified through risk assessment as ‘high risk’. | ü |  |  | ü | [8 empty] | AFMA: AFMA has developed Bycatch and Discarding Workplans in consultation with industry and research partners to find practical and affordable solutions to minimising bycatch and the discarding of target species. These fishery specific workplans focus on ‘high risk’ bycatch and threatened, endangered and protected species identified though the ecological risk assessment process and in accordance with the AFMA Bycatch Strategy: Mitigating protected species interactions and general bycatch 2017-2022. AFMA has developed extensive resource to minimise and avoid interaction with sharks and other species. Details on guides and protocols can be found at http://www.afma.gov.au/sustainability-environment/bycatch-discarding/bycatch-reports-publications-id-guides/. WA: WA has implemented management arrangements to ensure shark bycatch reduction in WA commercial fisheries. Addressed via a number of legislative arrangements. | bar: NSW; WA to WA
|  | 32. Assess the effectiveness of current shark bycatch reduction measures in reducing shark mortality (including cryptic mortality) and develop performance measures for shark bycatch reduction. |  |  |  | ü | [8 empty] | WA: WA monitors the effectiveness of bycatch reduction measures through its commercial monitoring program and works closely with various fishing sectors and fishers to gain a better understanding of any issues or gaps with respect to the effectiveness of shark bycatch reduction measures. | bar: NSW; WA to WA
|  | 33. Promote adoption of effective shark bycatch reduction measures internationally. |  | ü | [10 empty] | Agriculture: Australia continues to promote scientifically rigorous shark bycatch mitigation measures through our engagement at regional fisheries management organisations and associated organisations such as the Pacific Islands Forum Fisheries Agency. Australia has continued to push for a strengthened conservation and management measure for the conservation of sharks in the Indian Ocean Tuna Commission including a requirement that sharks be landed with their fins attached to the carcass. WA: WA promotes the adoption of effective shark bycatch reduction measures if and when required. | bar: WA to WA
15 | Medium – low | 34. Undertake periodic assessment/support research of the impact of targeted shark fishing on non-target species (particularly threatened species) and identify priority issues for management. |  |  |  | ü | [8 empty] | WA: WA reports the TDGLF threatened endangered and protected species interactions annually in the Department's status reports of fisheries and aquatic resources and is in the process of developing a Memorandum of Understanding (MOU) with Environment. | bar: WA to WA
|  | 35. Undertake periodic assessment/support research of the impact of fishing operations on structure and function of shark species/stocks and identify priority issues for management. |  |  |  | ü | [8 empty] | WA: WA undertakes periodic stock assessments. Furthermore, the department supports research on the impact of fishing operations on the structure and function of shark species and stocks, and has completed a FRDC project (2010/003) looking at the spatial and temporal dynamics of the four TDGLF target species (gummy, whiskery, sandbar and dusky sharks). | bar: WA to WA
|  | 36. Periodic assessment of the ecological impacts of shark control programs for bather protection. |  |  |  |  | NSW: ü; WA: ü; WA: Ongoing | A number of jurisdictions have undertaken reviews of shark control programs over the life of this plan, and continue to consider and undertake research into new technologies and non-lethal bather protection initiatives. WA: Independent review was completed that assessed the effectiveness and merit of using shark nets in WA to address white shark public safety issues. NSW: The 2017-18 Annual Performance Report for the NSW Shark Meshing Program was reviewed by the Fisheries Scientific Committee and the NSW Scientific Committee and the annual reports and comments were made publicly available. The 5-year Review of the 2009 Joint Management Agreements (JMA) for the NSW Shark Meshing (Bather Protection) Program was completed in 2016-17 and a new JMA was enacted in July 2017. The NSW North Coast shark net trials management plan and reports are publically available.
|  | 37. Investigate methods for modelling the population ecology of sharks and distinguishing between natural vs fishing induced variation, so as to better understand population status and rates of recovery. | [12 empty] | WA: WA undertakes periodic stock assessments. Furthermore, the department supports research on the impact of fishing operations on the structure and function of shark species and stocks, and has completed a FRDC project (2010/003) looking at the spatial and temporal dynamics of the four TDGLF target species (gummy, whiskery, sandbar and dusky sharks). A recent review of the effects of fishing (Hall and Wise 2011) showed that there was no significant change in trophic levels after 40 years of fishing. This implies that the ecosystem functions and roles of top predators, including sharks, have not significantly changed over past decades. | bar: WA to WA
|  | 38. Consider ecosystem structure and function in the development and implementation of management measures, including trophic system interactions and how changes in systems may be measured |  |  |  | ü | [8 empty] | WA: WA manages fish resources in accordance with Ecosystem Based Fisheries Management principles and therefore closures have been implemented to protect identified breeding areas and periods (such as closure to shark fishing from Shark Bay to Exmouth) and the closure of the TDGDLF for the past 8 years during the peak whiskery shark pupping period. | bar: WA to WA
# Commonwealth focus