## Progress on NPOA Sharks
|  |  |  | Primary focus |  |  | Secondary focus |  |  | Day to day management where applicable to the jurisdiction |  |  |  |  | ü – Action item has been implemented or is ongoing
In progress – Action item has commenced implementation Yet to initiate – Action item has not yet been initiated
Issue | Priority of issue | Action | Jurisdiction
|  |  | Commonweath |  |  |  | NSW | NT | QLD | SA | TAS | VIC | WA | WA | Reporting notes:
|  |  | AFMA | Agriculture / ABARES | Environment | GBRMPA
1 | High | 1. Review existing shark species identification guides (and any in development), implementing the best available identification guides in all relevant fisheries: | [12 empty] | Shark and Ray handling and identification guides have been developed by a number of jurisdictions to help commercial fishers return live sharks to the ocean and increase their survival. QLD: QLD is reviewing the suitability and applicability of the shark logbooks and the species identification guides as part of the broader Monitoring and Research Plan. NT: A review of the management arrangements of the offshore net and line fishery is in progress and is nearly completed. With the implementation of the management plan, current identification (ID) guides will be reviewed and updated as necessary. VIC: Victoria reviews and updates annually the section of its recreational fishing guide that is related to sharks, skates and rays. The 2018 guide was published in December 2017. WA: Water-proof ID guide to WA Sharks and Shark-like rays distributed to all shark fishers in 2002. | bar: NSW to QLD; VIC to WA
- ensure guides are culturally appropriate, including the use of Indigenous species names where appropriate. | bar: NSW to QLD; VIC
|  | - ensure the best available guides have been provided to relevant user groups, including fishers, processors, compliance officers, observers and scientists. | [12 empty] | QLD: Fishers in key net and line fisheries interacting with shark and ray species will need to complete a shark-specific logbook from January 2018. QLD is providing fishers with a water-proof copy of the shark identification guide along with the revised SR05 logbook. Fishers can also access a series of on-line identification guides. VIC: Victoria has a recreational fishing smart phone app (iPhone/Android) which to date has been downloaded approximately 100 thousand times. The app contains information on species, bag and size limits. Both the app and the hard copy contain hand drawn colour diagrams of recreationally important and protected shark, skate and ray species. WA: WA works with commercial fisheries on an ongoing basis to ensure the correct identification and reporting of shark and other species of fish. | bar: NSW to QLD; VIC
|  | 2. Monitor the effectiveness of identification guides. | [12 empty] | Jurisdictions have engaged in projects aiming to determine misreporting by observers and has also undertaken reviews of ID guides where required. WA: Fisheries' Compliance Officers conduct regular checks of recreational anglers to ensure they are aware of and can correctly identify different shark species and are complying with relevant legislation. QLD: Monitoring the effectiveness of identification guides will be undertaken as part of a broader review into how shark/ ray catch is monitored and reported in QLD. NT: Feedback on the effectiveness of guides is obtained from scientific staff carrying out at sea scientific monitoring and more formally through the annual Offshore Net and Line Fishery (ONLF) licensee commitee general meeting. To help understand identification errors, the department participated in a project to determine misreporting by observers. | bar: NSW to QLD; WA to WA
|  | 3. Investigate the potential for additional tools for shark identification, such as morphological diagnostic tools or DNA identification kits. | [12 empty] | NT: NT completed a research project to determine a morphological method that can be used in the field to separate between the cryptic species C. tilstoni and C. limbatus, key target species in the ONLF. NT is also participating the development of morphological techniques to identify shark species from fins alone. In partnership with AFMA, NT determined the elasmobranch species composition on board vessels operating in the MoU box shark fishery. NT is also participating in trialling and development of the Food and Agriculture Organization (FAO) "ISharkFin" program. WA: WA has developed a deoxyribonucleic acid (DNA) based identification process for sharks: FRDC Project 2003/067 looked at the development of a DNA Database for Compliance and Management of West Australian sharks – completed in 2005. | bar: NSW to NT; WA to WA
2 | High | 4. Develop and implement national minimum data standards for all commercial, recreational, bather protection and Indigenous fishing operations that take sharks. |  | In progress | ü | [9 empty] | A number of jurisdictions have systems in place for the collection of data on recreational and commercial fishing of shark species. NT: NT has systems in place for the collection of data for recreational and commercial fishing. These processes (being statutory fishing returns for commercial fishers and a recreational fishing survey) are ongoing and information needs are reviewed regularly. Agriculture: The draft final report for ‘Shark Futures: A Report Card for Australia’s Shark and Rays’ has been provided and reviewed. Over 40% of the 194 report cards were selected and externally reviewed. Environment: The Department of the Environment and Energy continues to work with Agriculture and other Commonwealth agencies and state and territory jurisdictions to help ensure these actions are undertaken. Tasmania: Tasmania does not have a dedicated commercial shark fishery so commercially caught sharks must be recorded in commercial catch, effort and disposal book. Recreational statewide surveys undertaken every five years available now. WA: WA has systems in place for the collection of data for recreational and commercial fishing. These systems (being statutory fishing returns for commercial fishers and “iSurvey”: a comprehensive biennial state-wide survey of boat-based recreational fishing) are supported by best practice processes including independent external review and Marine Stewardship Council (MSC) assessment. | bar: NSW to NT; TAS; WA to WA
|  | 5. Obtain better understanding of illegal, unregulated and unreported shark catch. | ü | ü | [10 empty] | Australia has run an active campaign to deter illegal foreign fishing regionally. AFMA: responsible for the delivery of the fisheries element of Australia's border protection program through the enforcement of the provisions of the Fisheries Management Act 1991 against operators of unlicensed foreign fishing vessels. Numbers of apprehended foreign fishing vessels targeting shark continue to decline. Agriculture: Australia's Second National Plan of Action (NPOA) to Prevent, Deter and Eliminate Illegal, Unreported, and Unregulated (IUU) Fishing outlines the national, regional and international actions Australia will take to combat IUU fishing. NPOA refers to the release of Shark Plan 2 which is used to coordinate action Australia wide, including against IUU activities and shark conservation and management. Australia is working to strengthen fisheries governance and fisheries management in South East Asia. Australia is also working with regional fisheries management organisations to improve the level and detail of reporting of shark catch, to provide better data and transparency in support of shark conservation. WA: WA is continually working to improve its understanding of all forms of shark catch. It is likely the MSC third party assessment process for Western Australia’s commercial fisheries and the finalisation of a Harvest Strategy Policy will drive further progress in this area. | bar: NSW; WA to WA
|  | 6. Develop and implement data verification systems with clear objectives and performance measures. | [12 empty] | A number of jurisdictions are working to introduce fine-scale catch information along with seeking to assess performance of shark fisheries against their respective management targets. NT: NT introduced fine scale statutory returns that document catch number and species and location for every shot. Returns are temporarally and spatially precise and provide fine-scale information to improve stock assessments and assess the performance of the shark fisheries against the respective management targets. WA: WA introduced fine-scale statutory returns (daily trip catch and effort) for the Temperate Demersal Gillnet and Demersal Longline Fishery (TDGDLF) in June 2006. The returns are temporally and spatially more precise and provide additional fine-scale information to improve stock assessments and assess the performance of the shark fisheries against the respective management targets. WA has implemented and uses catch and effort data validation protocols for the statutory returns. Statutory catch and effort data are maintained in Fisheries’ Catch and Effort statistics database. These are summarised and reported annually in the Department’s annual Status Reports of the Fisheries and Aquatic Resources (SRFAR). | bar: NSW to NT; WA to WA
3 | Medium – high | 7. Implement anti-finning measures for all Australian fisheries and assess their effectiveness across jurisdictions. Measures should be promoted for adoption regionally and internationally. |  | ü | ü | [9 empty] | Shark finning at sea is illegal in all Commonwealth fisheries and a number of state fisheries. Shark catches in some fisheries are managed through ratios to ensure carcasses are not discarded at sea. Australia also promotes the adoption of anti-finning measures through regional fisheries management organisations and international bodies such as the Food and Agriculture Organisation’s Committee on Fisheries. SA: Legislation in place that requires fins to be landed with carcasses (Regulation 18(5)(b) of the Fisheries Management (General) Regulations 2017). QLD: Finning or the taking of shark fins and discarding the body is already prohibited in QLD water. However, shark fins do not need to be naturally attached. Under the current system, commercial line fishers and net operators without an S-fishery symbol can remove the fins providing they are secured directly to the trunk. Net fishers operating with an S-fishery symbol do not need to secure the fins to the trunk and filleting is permitted providing the number of fin-sets can be easily matched to the number of trunks or fillets. The removal of fins is not permitted in the recreational fishing sector. The above measures have not changed since the 2016 meeting of Shark-plan Representative Group (SRG) and officers from the QLD Boating and Fisheries Patrol continue to monitor/ enforce this provision through their broader program. Agriculture: Shark finning illegal in all Commonwealth fisheries. It is an offence under fisheries management regulation 9Z0 to remove the caudal lobe, pectoral fin and dorsal fin before the shark is in possession of a fish receiver. Australia advocates for the implementation of anti-finning measures including banning the use of wire traces and the landing ofsharks with their fins naturally attached to the carcass. Environment: Department of the Environment and Energy continues to work with the Department of Agriculture and Water Resources and other Commonwealth agencies to advocate at regional fisheries management organisations the implementation of anti-finning measures incl. the use of wire traces and landing sharks with fins attached to the carcass. WA: WA introduced anti-finning legislation in November 2006. | bar: NSW; QLD to SA; WA to WA
|  | 8. Assess the potential for more comprehensive trade data collection and analysis to improve shark conservation and management outcomes and implement a more comprehensive trade data collection system as appropriate. |  | ü | ü |  | WA: Yet to initiate; WA: Yet to initiate | Customs and Border Protection Service officials attended the World Customs Organization (WCO) meeting in March 2014, to discuss changes to the Harmonized System (HS) coding system. Unfortunately, despite Australia’s support for the proposal to harmonise and adopt species specific shark codes the vote did not gain the two-thirds majority (23-for and 17-against) required for amendment. Australia's position is to promote this issue at the next meeting of the WCO meeting, likely to be in 2019. Agriculture: The Department of Agriculture and Water Resources examined the existing arrangements for recording and analysing shark and trade data - this encompassed the existing WCO HS coding system. Department concluded that a change to the WCO HS would need to drive any changes to the domestic coding system. WA: This is not considered to be a high priority for WA noting fins are not exported and flesh supplies local and domestic markets.
4 | High | 9. Support the FRDC National Research, Development and Extension Framework 'Shark futures'. | [12 empty] | The FRDC considers all proposals received for funding of shark-related research against the framework developed by the shark futures project. SA: Shark futures project completed - Tactical research fund: using molecular techniques to improve the ecologically sustainable fisheries management of shortfin makos. VIC: Victoria supports the FRDC NRDE framework where there is an identified benefit to the state. WA: WA supports the need for a coordinated approach to shark research through the FRDC Shark Futures program. | bar: SA; VIC to WA
|  | 10. Investigate opportunities for collaborative research initiatives to address the aims and objective of Shark-plan 2. |  |  |  | ü | [8 empty] | There are a number of shark-related projects funded under the National Environmental Science Programme (NESP) such as determining the population status of white sharks and hammerhead sharks, determining research priorities for Australia's shark species, and initiatives to mitigate risk of human-shark interactions. QLD: DAF provides support for shark and ray research through direct funding and in-kind contributions (i.e. QLD shark stock assessment, projects examining the life-history constraints, distributions and movement of the riger shark and bull shark and gear evaluations through the QLD Shark control program). QLD in conjunction with CSIRO are in the process of finalising a FRDC project which will quantify elasmobranch bycatch survival rates in East Coast Trawl Fishery and assesses the risk posed to elasmobranchs by this fishery. NT: NT continues to identify opportunities to collaborate with other partners to address the aims and objectives of Shark Plan 2 (e.g.collaborative research initiatives with CSIRO, Charles Darwin University, NTDPIF, AIMS, NERP etc). Research areas include the development of tools for effective identification of sharks as well as collaborative shark stock assessments and tagging projects. SA: FRDC project: application of tracking technologies to understand explicit patterns of movement, residency and habitat use of pelagic sharks in Spencer Gulf: resolving overlaps with key community activities and marine industries. WA: WA continues to identify opportunities to collaborate with other partners to address the aims and objectives of Shark-plan 2. The following collaborative projects have been completed: towards a National Strategy for Understanding Movements of Cross-Jurisdictional Species: aligning management needs with the goals of IMOS (led by CSIRO via IMOS); white shark initiatives including assessing the impact on fisheries management changes on the western white shark population. | bar: NSW to SA; WA to WA
5 | High | 11. Maintain and/or improve stock assessments, risk assessments and status determination processes for target, bycatch and byproduct species. | ü |  |  | ü | [8 empty] | A number of jurisdictions with targeted-shark fisheries have moved to undertaking stock assessments for species. QLD: On 9 June 2017 the Goverment released the Queensland Sustainable Fisheries Strategy 2017-2027. A number of reform areas deal specifically with improving the level of information on key stocks and quantifying the level of risk posed to both target and non-target species. DAFF has commenced work on a set of guidelines that will outline how ecological risk assessments will be undertaken for both traget and non-targed species. Outside of the Sustainable Fisheries Strategy, QLD continues to review the status of a number of shark species through the National SAFS and the QLD stock status assessment processes. NT: NT undertook major stock assessments for key shark species, C. sorrah, C. tilstoni and C. limbatus. A risk assessment has been carried out for all of the significant bycatch and by product species. ONLF scientific monitoring program continues to collect information that will inform assessments on all target, bycatch and byproduct species. SA: catch and effort trends for combined bronze whaler and dusky shark catches monitored and reported annually. ESD risk assessments are undertaken for all commercial and recreational fisheries as part of the development of fishery management plans. AFMA: Harvest strategies are in place for shark species managed under quota in the Southern Eastern Scalefish and Shark Fishery. Gulper sharks (dogfish) are not managed under a combined quota and in February 2013 AFMA implemented a revised upper slope dogfish management strategy. In June 2017 the guide to AFMA’s Ecological Risk Management was released. TAS: All commercial shark catch is recorded in the annual scalefish fishery assessment. Tasmanian recreational fishing survey provides an estimate of recreational shark and ray captures for both kept and released. WA: WA undertakes stock assessments for key shark species as set out by the Department's annual status reports of the fisheries and aquatic resources (SRFAR). Department undertook an FRDC funded research project to examine the movements of the shark fisheries' four indicator sharks stocks. Results from this study are being used to reassess the status of these stocks. Further to this, Fisheries’ stock assessments, independent MSC pre-assessment of the northern and Temperate Demersal Gillnet and Demersal Longline Fisheries (TDGDLF) have been completed. NSW: NSW DPIF contributes to the Status of Australian Fish Stocks reviews of sharks and continues discussions about status determination processes with adjacent jurisdictions and the Commonwealth. | bar: NSW to TAS; WA to WA
|  | 12. Assess the need for implementation of formal harvest strategies to manage shark catch. | ü |  |  | ü | ü | ü | ü | ü |  | ü | In progress | In progress | QLD: The Queensland Sustainable Fisheries Strategy 2017-2027 identified 'Harvest Strategies' as one of the 10 major areas of reform which includes a number of key action items. QLD has already commenced work on these action items and on 5 October 2017 released the Queensland Harvest Strategy Policy and Guidelines for Implementing the QLD Harvest Strategy Policy. Outside the Sustainable Fisheries Strategy, QLD continues to address the harvesting of sharks through ancillary processes like threatened species assessments and Wildlife Trade Operation approvals under the EPBC Act. NT: A review of the management arrangements of the ONLF has been completed and the Management Plan is currently being implemented. A formal management frame work, incorporating formal harvest limits to manage shark catch has been approved by industry and community and is being drafted into legislation. SA: Combined bronze whaler and dusky (whaler sharks) considered secondary species in the Marine Scalefish Fishery, and a broad harvest strategy has been developed in Management Plan for the South Australian commercial marine scalefish fishery. Shark catches are monitored and reported on an annual basis via the stock status report. AFMA: On 29 and 30 November 2017 the Department of Agriculture and Water Resources held a stakeholder workshop to consider draft guidelines for both the draft Commonwealth Bycatch Policy and draft Harvest Strategy Policy. Recommendations of these reviews will influence the need for implementation of formal harvest strategies to manage shark catch. Harvest Strategies are in place for all shark species managed under quota in the SESSF. VIC: Victoria doesn't have a dedicated commercial shark fishery but authorised commercial fishers harvested an average of 41 tonnes of sharks between 2012 and 2016 with gummy shark being the primary species harvested. Victoria does not have an estimate of recreational shark harvest but angler diary monitoring in selected Victorian estuaries indicates that catch as a percentage of recreational catch is low. WA: In 2015, WA published its overarching Harvest Strategy Policy and has an agreed harvest strategy with the NT and QLD via the Northern Australian Fisheries Committee relating for northern shark species, namely black-tip and sandbar shark. A science review of the Northern Shark Fisheries has been completed and has been used to inform the Draft Northern Shark Discussion Paper. The MSC assessment process will drive further development and implementation of harvest strategies for WA’s fisheries, including the Northern Shark and TDGDLF.
6 | Medium | Covered under Issue 5
7 | High | 13. Iterative/ongoing jurisdictional assessment of the adequacy of shark management including the implementation of harvest strategies and compliance, enforcement and education strategies to support sustainability objectives for sharks. | ü |  | ü | ü | [8 empty] | Harvest strategies in place for all Commonwealth shark species under quota, all other species assessed and managed under the Ecological Risk Management program. AFMA has in place a comprehensive intelligence driven, risk based targeted domestic compliance program. The Department of the Environment and Energy is continuing to collect and analyse national harvest, import and export data for the CITES Appendix II listed scalloped, smooth and great hammerhead sharks. This will inform future reviews of the current non-detriment finding for hammerheads sharks. QLD: Queensland boating and fisheries patrol undertake compliance risk assessments for all of Queensland's fisheries with the outputs being used to define compliance priorities including for sharks. Shark catch in the commercial and recreational sector is monitored via the Queensland Boating and Fisheries Patrol. Educational programs including on-line guides and the distribution of shark ID booklets are an important part of managing shark bycatch. AFMA: Harvest Strategies are in place for all shark species managed under quota in the Southern Eastern Scalefish and Shark Fishery. AFMA provides formal reports on the implementation of the SESSF harvest strategy framework in the AFMA annual reports and Wildlife Trade Operation (WTO) strategic assessments. This includes the number of species/ stocks as being subject to overfishing or overfished. Environment: Department of the Environment and Energy continues to work with DAWR to ensure relevant actions are undertaken. WA: WA has internal processes in place to review the adequacy of shark (and other fisheries) management including the implementation of harvest strategies and compliance, enforcement and education strategies to support sustainability objectives for sharks. The department promotes community and stakeholder awareness of the managmement of, and rules relating to, sharks in Western Australia. Further, WA's MSC initiative has seen all of the State’s fisheries, including the TDGDLF, subject to independent third party assessment against MSC guidelines. The pre-assessment of the northern and temperate shark fisheries has been completed. NSW: The ‘large shark permit fishery’ component of the NSW Ocean Trap and Line Fishery, which harvests the majority of sharks in NSW, remains inactive. The NSW Government continues to implement its $16M Shark Management Strategy (launched in October 2015), the key objective of which is to increase protection for swimmers and surfers from shark interactions while minimising harm to sharks and other marine animals. | bar: NSW; QLD; WA to WA
|  | 14. Explore mechanisms for greater collaboration between jurisdictions regarding research, assessment and management of shared stocks. | [12 empty] | This an ongoing action for jurisdictions who continue to engage with others regarding the management of shark fisheries and related matters. QLD: QLD continues to collaborate with adjacent jurisdictions including through species workshops. QLD involved with a number of regionally specific committees aimed at improving cooperation between adjacent jurisdictions including the Northern Australia Fisheries Committee which includes WA, NT, QLD and Cth agencies. These committees address a wide range of issues including targeted and non-targeted interactions with shark and ray species. NT: NT continues to engage with other jurisdictions regarding the management of shark fisheries. WA: WA engages with other jurisdictions regarding the management of the shark fisheries and related and will, where appropriate, explore opportunities to collaborate with those jurisdictions with respect to the management and research of shared stocks. Fisheries sought a review of the current science knowledge associated with Western Australia’s northern shark stocks. The completed review is assisting with consideration of future harvest and management strategies for Northern shark. | bar: NT to QLD; WA to WA
8 | Medium | 15. Review the effectiveness of management measures for recreational and game fishing in achieving sustainability objectives for shark species and develop recommendations for future management approaches, should this be found to be necessary. | [12 empty] | A number of jurisdictions have undertaken reviews of management measures for recreational and game fishing, such as the appropriateness of boat limits and trigger limits. Research into post-release mortality or survival of shark species has also been prioritised. QLD: In 2009, QLD introduced significant restrictions on the take of shark and rays within the recreational fishing sector which included max size limits, in possession limits and no-take species. When and where applicable, these management arrangements will be reviewed to ensure that they cover ancillary decisions e.g. decisions relating to the listing of species under the EPBC Act. The management of sharks of QLD, when appropriate, will also be reviewed by the Fisheries Working Groups. NT: NT has released the results of the recreational fishing survey which will update and improve the information on shark harvest by the recreational fishing sector. Recreational fishing surveys are now be carried out annually. Recreational fishing bag limits have been modified limiting recreational fishers to three sharks in possession. TAS: Recreational fishing survey provides insight into the recreational take and release of shark and ray species. The scalefish fishery management plan introduced new and or/extended no gillnetting areas; a reduction of hook numbers on recreational set lines and the prevention of the use of berkey for any other purpose other than fishing. WA: In addition to commercial fishing, WA monitors recreational catch and effort through surveys. Last survey confirmed that there is minor targeting of sharks by the recreational fishing sector and limited recreational shark game fishing in WA. VIC: The VFA has recently put in place rules to protect skates and rays in response to community concern about cruel treatment by a small proportion of fishers. The VFA is currently discussing with VRFish, the Victorian recreational fishing peak body, a change to the recreational bag, boat and minimum size limits for game sharks | bar: NT to QLD; TAS to WA
|  | 16. Assess the findings of the review under action 16 and relevant recreational and Indigenous fishing surveys to: |  | ü | [10 empty] | The Australian Government has recently released a report that provides a survey methodology framework for conducting regular recreational fishing surveys. States and territories continue to undertake recreational fishing surveys where appropriate. TAS: IMAS hosted resource assessment group for scalefish and minor species meeting held in November- meeting provides opportunity to put forward research-related projects identifying gaps in knowledge, data collection and stock and effort related issues. WA: WA continues to use a number of means to educate fishing sectors (including recreational and game fishing) in relation to sharks. Fisheries adopts a risk based approach to compliance and enforcement and directs resources towards these activities in relation to sharks as appropriate based on the risk rating. The last information on indigenous fishing occurred in 2000/01 as part of the national survey. Catches are likely to be relatively minor. | bar: TAS; WA to WA
- identify gaps in existing monitoring and data collection programs for recreational, charter and Indigenous fishing. | bar: TAS; WA to WA
- determine the nature and role of state and territory recreational fishing surveys. | bar: TAS; WA to WA
- determine the required frequency of future national surveys. | bar: TAS; WA to WA
- determine adequacy of reporting on recreational and Indigenous fishing issues at national level. | bar: TAS; WA to WA
- where necessary, update existing survey methodologies or introduce effective supplementary or alternative data collection mechanisms. | bar: TAS; WA to WA
- review and where necessary revise recreational and game fishing management arrangements to ensure impacts on sharks are sustainable. | bar: TAS; WA to WA
- where necessary, increase education and enforcement programs in recreational and gamefishing sectors. | bar: TAS; WA to WA
9 | Medium – low | 17. Improve understanding of the cryptic mortality of high risk sharks in commercial, recreational and Indigenous fisheries. |  |  |  | ü | [8 empty] | WA: WA works with various fishing sectors and fishers to gain a better understanding of any issues or gaps with respect to the fishing they undertake. These discussions are critical to gaining a better understanding of, and working out how to collect information on cryptic mortality. Trial of in-net and on deck cameras in the Pilbara Trawl Fishery was taken in 2013 with the goal of monitoring and detecting the reduction in megafauna bycatch including sharks and rays. Condition of all megafauna at release was recorded which will provide information on cryptic mortality. | bar: TAS; WA to WA
|  | 18. Implement strategies to reduce cryptic mortality, noting the link with Theme 2 of Shark Futures which has a focus on minimising the environmental impacts of fisheries on sharks. |  |  |  | ü | NT: ü; QLD: Yet to initiate; WA: ü; WA: ü | While jurisdictions in the past have reduced the potential for cryptic mortality to sharks through the use of bycatch reduction devices, it is acknowledged there is still further work that could potentially be undertaken in this space. QLD: While this was initially identified as a primary focus, QLD now considers this to be one of the alternate shark-specific initiatives. NT: Strategies to reduce cryptic have been investigated. In the new management plan, performance measures have been implemented and increased levels of monitoring will determine if cryptic mortality is indeed occurring and if so, levels will be quantified.
|  | 19. Ensure cryptic mortality is accounted for in the setting of catch quotas (where information is available). |  |  |  |  | TAS: N/A; WA: ü; WA: ü | Where stock assessments for sharks are undertaken, jurisdictions aim to account for all sources of mortality. In some jurisdictions, major shark-target fisheries will include uncertainty in mortality rates which will implicitly include cryptic mortality. WA: All sources of mortality are considered in shark stocks assessments. As part of FRDC 2010/003, models for the major target fisheries will include uncertainty in mortality rates which will implicitly include cryptic mortality.
10 | Medium – low | 20. Investigate shark handling practices to identify any areas of concern. | [12 empty] | Another specific project is assessing the post release survival of mako sharks with the ultimate goal of developing best practice fishing techniques to reduce stress levels and maximising post-release survival. WA: Commercial fishers in WA's TDGDLF have codes of conduct that relate to handling practices for shark species. These assist commercial fishers in returning bycatch and byproduct to the water alive and unharmed and ensure maximum quality of the retained product. Recreational fishers are advised via “Gently Does It” and other similar programs on the general handing of fish to maximise survival rates if returning to the water and to maximise table quality and encourage better use of fish resources if fish are being kept. | bar: TAS; WA to WA
|  | 21. Implement solutions as required, with consideration given to increased training and enforcement requirements. | [12 empty] | WA: WA maintains dialogue with the WA Fishing Industry Council & Recfishwest, the peak stakeholder bodies for commercial and recreational sectors, regarding fish handling practices and investigates specific matters if required. | bar: WA to WA
11 | Medium | 22. Assess the extent of Indigenous fishing for sharks and incorporate into overall management arrangements. Identify gaps in knowledge about Indigenous shark fishing and, where a need is identified, develop research proposals to address these gaps. | [12 empty] | NT: WA has undertaken a pilot project which has developed a model which can be used to collect information from indigenous communities about the levels of chondrichthyan catch. WA has a strong relationship with the network of marine rangers groups around the Territory and will continue to work collaboratively with these groups. Where possible WA will continue to work to identify knowledge gaps with concerns to indigenous shark fishing and develop research proposals to address those knowledge gaps. | bar: NT; WA to WA
|  | 23. Assess the impact of existing management measures for sharks on Indigenous subsistence fishing practices. |  |  |  |  | NT: Yet to initiate; WA: Yet to initiate | WA: MSC assessment process likely to inform the need to assess the impact of management arrangements on Indigenous fishers.
12 | Medium – high | 24. Implement management responses for species (or species groups) already assessed as high risk. | ü |  |  | ü | ü | ü |  | ü (as needed) |  | ü | ü | ü | Across all jurisdictions a range of strategies are in place to manage high risk species. High-risk species are identified through ecological risk assessment processes, listing under national and state environmental legislation and listing through international conventions. NT: NT has implemented legislation that prevents the take of pristis sawfish and glyphis sharks. SA: No shark species identified as high risk. SA has commercial and recreational management controls in place to ensure that harvest of sharks in SA waters is sustainable. AFMA: ERM guide includes a timetable for undertaking ERAs and the development of Fishery Management Strategies (FMS), which draw all major management tools and strategies for a fishery into one document and also assist in streamlining reporting arrangements. The guide outlines a fisheries management framework and a major element of this is the development of a fishery management strategy for each fishery. VIC: Current level of shark and ray harvest not seen as a key threat to sustainability and VIC has placed commercial and recreational management controls to ensure that the harvest of sharks is sustainable. WA: WA has implemented management responses for shark (and byproduct and bycatch species) assessed as high risk incl. dusky, sandbar and whiskery shark stocks. NSW: The strategies for threatened sharks in the Priorities Action Statement were formally adopted and are now available on NSW DPIF website. The existing recreational fishing rules that apply to several Greynurse Shark aggregation sites in NSW were extended for another 5 years in September.
|  | 25. Undertake best practice risk assessments for shark species not already assessed. |  |  |  | ü | [8 empty] | QLD: The use, suitability and applicability of risk assessments are being reviewed by QLD DAF as part of the broader Queensland Sustainable Fisheries Strategy 2017-2027. The strategy included two actions items that relate specifically to the development of ERAs in QLD: Action 4.1 Publish a guideline on assessing the ecosystem impact of fishing activities including the process for prioritising and undertaking ERAs; Action 4.2 ERA to be undertaken for priority fisheries by the end of 2020, followed by the remaining fisheries. QLD has commenced work on ERA guidelines and shark and ray specis will be a prominent component of the risk assessment framework. Risk assessments for shark and ray species will be undertaken in key fisheries. NT: NT has undertaken a risk assessment process for species caught in the ONLF. SA: ESD risk assessments undertaken for all fisheries. WA: WA manages WA's shark stocks through the use of indicator species. Risk assessments have been completed for these indicator species. | bar: NSW to SA; WA to WA
|  | 26. Continue to refine risk assessment processes for target, bycatch and byproduct shark stocks, seeking to include all available data and to include consideration of cumulative impacts. Collection of data on species biology and human impacts will be foundational to the success of this action. |  |  |  | ü | [8 empty] | WA: WA's assessment process will continue to be based on multiple years of detailed stock assessments and outcomes of formal ESD risk assessments. Current management setting is considered likely to deliver sustainable catches of target, byproduct and bycatch species. | bar: NSW; WA to WA
|  | 27. Evaluate the methodologies for risk assessment and assess the need for national risk assessment guidelines. |  | In progress |  | ü | [8 empty] | Agriculture: All shark species taken in Commonwealth fisheries are subject to ecological risk assessment. Species considered to be at greater than low risk (medium or high) are considered under ecological risk management (ERM) processes. AFMA is currently finalising a guide for ERM that will asisst in the consistent application of RA processes in Commonwealth fisheries. ABARES, in collaboration with other international scientists, have recently applied the above risk assessment methodologies to shark species encountered in a number of high seas fisheries. WA: WA's risk assessments are conducted with best practice standards evidenced by the 2015 re-approval of the of the Temperate Demersal Gillnet and Demersal Longline Fishery (TDGDLF) under Part 13 and Part 13a of EPBC Act. | bar: NSW; WA to WA
|  | 28. Implement management measures for any subsequent high risk species. |  |  |  | ü | [8 empty] | WA: WA sought a review of current science knowledge associated with Western Australia's northern shark stocks. Review has been completed and is informing decisons and assisting in consideration of future harvest and management strategies. | bar: NSW; WA to WA
|  | 29. Identify important habitat and broader environmental and habitat requirements for shark species and appropriate protection and management of these areas. |  |  | ü | ü | [8 empty] | WA: WA manages fish resources in accordance with Ecosystem Based Fisheries Management principles. On this basis, closures have been implemented to protect identified breeding areas and periods. NSW: The NSW Shark Management Strategy has installed 21 VR4G listening stations in 2015-2017, and aims to tag 100 of each of White Sharks, Tiger Sharks and Bull Sharks. This will provide data to better understand the movements and distributions and habitats of those species to inform risk assessment and management options. There are NSW research projects examining the environmental and habitat requirements of Greynurse Sharks and juvenile White Sharks. | bar: NSW; WA to WA
13 | Medium – high | 30. For species designated as requiring recovery, implement recovery strategies. Recovery strategies should be monitored and revised as appropriate to ensure effectiveness. |  |  | ü | Yet to initiate | NSW: ü; SA: ü(as needed); WA: ü; WA: ü | Environment: Eight shark species included in the EPBC Act. Of all species, all but the whale shark have active management plans. A review of the whale shark recovery plan was finalised in 2004. WA: WA has implemented management arrangements to provide for the recovery of relevant shark species and continues to conduct stock assessments for key shark species. SA: Where needed, PIRSA will develop harvest strategies aimed at stock rebuilding.
14 | Medium – high | 31. Initiate action (as required) to ensure effective bycatch reduction methods for sharks have been developed for all fisheries in which shark are caught as bycatch, giving priority to species identified through risk assessment as ‘high risk’. | ü |  |  | ü | [8 empty] | AFMA: AFMA is currently reviewing its approach to addressing bycatch of a number of species including sharks. AFMA management had been developing a strategy to manage general bycatch and protected species in Commonwealth fisheries. Further, the AFMA Bycatch and Discard team will focus on the development of a combined strategy to manage Bycatch of Protected and General Bycatch Species in Commonwealth Fisheries including two supporting sub strategies for seabirds and mammals. Following the development of these two sub strategies AFMA will focus on other outstanding high risk species including sharks. WA: WA has implemented management arrangements to ensure shark bycatch reduction in WA commercial fisheries. Addressed via a number of legislative arrangements incl. state-wide protection on the commercial take of sharks and rays as well as protection of dusky sharks and white sharks. | bar: NSW; WA to WA
|  | 32. Assess the effectiveness of current shark bycatch reduction measures in reducing shark mortality (including cryptic mortality) and develop performance measures for shark bycatch reduction. |  |  |  | ü | [8 empty] | WA: WA monitors the effectiveness of bycatch reduction measures through its commercial monitoring program and works closely with various fishing sectors and fishers to gain a better understanding of any issues or gaps with respect to the effectiveness of shark bycatch reduction measures. | bar: NSW; WA to WA
|  | 33. Promote adoption of effective shark bycatch reduction measures internationally. |  | ü | [10 empty] | Agriculture: Australia continues to promote scientifically rigorous shark bycatch mitigation measures through our engagement at regional fisheries management organisations and associated organisations such as the Pacific Islands Forum Fisheries Agency. Australia has continued to push for a strengthened conservation and management measure for the conservation of sharks in the Indian Ocean Tuna Comission including a requirement that sharks be landed with their fins attached to the carcass. WA: WA promotes the adoption of effective shark bycatch reduction measures if and when required. | bar: WA to WA
15 | Medium – low | 34. Undertake periodic assessment/support research of the impact of targeted shark fishing on non-target species (particularly threatened species) and identify priority issues for management. |  |  |  | ü | [8 empty] | WA: WA reports the TDGLF threatened endangered and protected species interactions annually in the Department's status reports of fisheries and aquatic resources and is in the process of developing a Memorandum of Understanding (MOU) with DoEE. | bar: WA to WA
|  | 35. Undertake periodic assessment/support research of the impact of fishing operations on structure and function of shark species/stocks and identify priority issues for management. |  |  |  | ü | [8 empty] | WA: WA undertakes periodic stock assessments. Furthermore, the department supports research on the impact of fishing operations on the structure and function of shark species and stocks. E.g. WA is currently undertaking a FRDC project looking at the spatial and temporal dynamics of four TDGLF targett species (gummy, whiskery, sandbar and dusky sharks). | bar: WA to WA
|  | 36. Periodic assessment of the ecological impacts of shark control programs for bather protection. | [12 empty] | A number of jurisdictions have undertaken reviews of shark control programs over the life of this plan, and continue to consider and undertake research into new techonlogies and non-lethal bather protection initiatives. WA: Independent review was completed that assessed the effectiveness and merit of using shark nets in WA to address white shark public safety issues. NSW: The 2015-16 and 2016-17 Annual Performance Reports for the NSW Shark Meshing Program were reviewed by the Fisheries Scientific Committee and the NSW Scientific Committee and the annual reports and comments were made publicly available. The 5-year Review of the 2009 Joint Management Agreements (JMA) for the NSW Shark Meshing (Bather Protection) Program was completed in 2016-17 and a new JMA was enacted in July 2017. | bar: NSW; WA to WA
37. Investigate methods for modelling the population ecology of sharks and distinguishing between natural vs fishing induced variation, so as to better understand population status and rates of recovery. | bar: WA to WA
|  | 38. Consider ecosystem structure and function in the development and implementation of management measures, including trophic system interactions and how changes in systems may be measured |  |  |  | ü | [8 empty] | WA: WA manages fish resources in accordance with Ecosystem Based Fisheries Management principles and therefore closures have been implemented to protect identified breeding areas and periods (such as closure to shark fishing from Shark Bay to Exmouth) and the closure of the TDGDLF for the past 8 years during the peak whiskery shark pupping period. | bar: WA to WA
# Commonwealth focus